## Slide 1: DFH-DFM meetings
7 Nov. #1: Conceptual Specifications
14 Nov. #2: DFHx : Layout & Splices
21 Nov. #3: Thermo-mechanical engineering
        Thermal Contraction Strategy
        Convective Heat Transfer : Fluid↔Splice
28 Nov. #4: DFM concept & pre-design
5 Dec. #5: DFHx assembly : choices and consequences
Topics:
DFH concept
Conceptual specifications
Technical specifications
DFH design
Specification drawings
Manufacture
Assembly & QA test
Installation
Operation
Maintenance
Conceptual sketches

## Slide 2: Proposed conceptual installed configuration
Guidelines for the assembly:
  MgB2 cable protected at all times
  MgB2-HTS splices fixed to He vessel
  Orientate angularly the MgB2 leads to the corresponding HTS leads
DSHx
2 x 18 kA
2 x 13 kA
3 x 7 kA
12 x 2 kA
DFHx1
DFHx2
Superfluid @ 1.9K
Liquid He @ 4.5 K
Gaseous He
Heater
Vacuum barrier
HTS
MgB2
NbTi
Warm cable
Splice
DFHx layout for analysis
DFHx 3D pre-design for illustration

## Slide 3: Proposal installation sequence
DFHx1
DFHx2
DFHx1
DFHx2
Protected MgB2 ends
MgB2 cables in flexibles
Cable opening in rigid structure
SCLink end preparation for SM18 test
  He vessels pre-mounted once for all before SM18 test
  Only MGB2 ends (temporary protected are visible)
  Only final welds around splices will be further performed
SM18 test installation (DFH proto)
  90% of He vessels are done
  Insertion DFHx1 VV
  Insertion of Interlink
  Insertion of DFHx2
  Opening of flexibles + angular orientation
  Splicing + Current leads
Transport configuration
  Procedure backward
  2 x 1m rigid section
SCLink installation (same as SM18)

## Slide 4: Key influencing parameters
The pre-opening of the MgB2 cables directly influences:
  The rigid boxes 10m distant to be installed in the turret for transport
  The SCLink vacuum jacket interface flange diameter
  The openings in the vacuum vessels
     increase radial distance to splices  length of DFH due to bending radius of MgB2
  The interlink vacuum jacket ID (could use it for waving only inner pipe)
Today orders of magnitudes:
  DFHx length ≈ 4m (bending radius 1.5m)
  DFHx Vacuum vessels OD ≈ up to 1.5m
  Interlink OD ≈ 400mm
DSHx
2 x 18 kA
2 x 13 kA
3 x 7 kA
12 x 2 kA
DFHx1
DFHx2
Superfluid @ 1.9K
Liquid He @ 4.5 K
Gaseous He
Heater
Vacuum barrier
HTS
MgB2
NbTi
Warm cable
Splice
DFHx layout for analysis
DFHx 3D pre-design for illustration
Ø
Ø
10 m
Ø
Ø

## Slide 5: Spare slides

## Slide 6: Overview
Each IP1 and IP5 sides equipped with 2 cold powering chains of cryostats
Triplet insertion : DFHx – SC Link (DSH) – DFX
Matching sections : DFHm – SC Link - DFM
DFX/DFM basic functions:
Electrical interface between SC Link and superconducting magnets
Supply cryogenics to the SCLink
MBXF
D1
DFX
DSHx
MgB2
NbTi
Jumper D1
Jumper DFX
Splice
Beam
Jumper DFM
D2
Jumper D2
MBCRD
MBRD
DSHm
DFM
2 x 18 kA
2 x 13 kA
3 x 7 kA
12 x 2 kA
DFHx1
DFHx2
2 x 13 kA
8 x 0.6 kA
DFHm
HTS
MgB2
PT
PT
PT
PT
PT
PT
PT
LHC tunnel
UR: Service tunnel
D1
CP
Q3
Q2b
Q2a
Q1
IP
Power converters
DSHx
DFHx1
DFX
DFHx2
D2
≈45m
DFHM
DFM
DSHm
≈80m
≈50m
≈8m
Service tunnel
Transverse tunnel
LHC tunnel


Ghe <17K
Ghe <17K
Ghe @4.5K
Lhe @4.5K
SFHe @1.9K
SFHe @1.9K
Ghe @4.5K
Lhe @4.5K
UL: Transverse tunnel
Superfluid @ 1.9K
Liquid He @ 4.5 K
Gaseous He
Heater
Vacuum barrier
HTS
MgB2
NbTi
Warm cable
Splice