## Slide 1
Experimental vacuum upgrade project – LS2 preparation & planning
ATLAS EXPERIMENTAL VACUUM UPGRADE
Main VSC deliverables:
Removal of IP1.X vacuum layout
Installation of IP1.X vacuum layout
New JTT plug 1 and modified VC1TB supporting system
Version - 10/10/2018
Josef Sestak
2018
2021
Today
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
2018
2019
2020
2021
Start of LS2
Dec 3, 2018
End of LS2
Feb 20, 2021
Venting of the IP1.X
Dec 10
Intermediate neon injection
Dec 21
Final neon pump-down
Feb 15
10 days
Feb 20 - Mar 5
Machine check-out
14 days
Jan 7 - Jan 24
Removal of A-side layout
30 days
Jan 21 - Mar 1
Removal of C-side layout
42 days
Oct 1 - Nov 27
Installation of A-side layout
37 days
Oct 26 - Dec 15
Installation of C-side layout
11 days
Dec 16 - Dec 31
Bake-out of the IP1.X
7 days
Oct 28 - Nov 7
Modification of the JTT - supporting system on A-side
9 days
Jan 30 - Feb 12
Modification of the JTT - supporting system on C-side

## Slide 2
Experimental vacuum upgrade project – LS2 preparation & planning
ALICE EXPERIMENTAL VACUUM UPGRADE
Main VSC deliverables:
Removal of (RB24) A1L2.X vacuum chambers
Removal of existing central vacuum chamber
Installation of a new central vacuum chamber
Installation and upgrade of (RB24&RB26) A1L2.X and A1R2.X
Version - 01/06/2018
Josef Sestak
2018
2021
Today
Q1
Q3
Q1
Q3
Q1
Q3
Q1
2018
2019
2020
2021
Start of LS2
Dec 3, 2018
End of LS2
Feb 20, 2021
Recommissioning with beam
Mar 5
Venting the IP2.X; A1L2.X and A1R2.X
Dec 3
Intermediate neon injection (IP2.X and A1R2.X)
Feb 24
Final neon pump-down
Aug 17
Central chamber ready for installation
Jul 31
10 days
Feb 20 - Mar 5
Machine check-out
2 days
Dec 4 - Dec 5
Removal of (RB24) A1L2.X vacuum chambers - 1st part
1 day
Dec 11
Removal of (RB24) A1L2.X vacuum chambers - 2nd part
30 days
Jan 14 - Feb 22
Removal of the existing central chamber
5 days
Nov 25 - Dec 2
Upgrade of (RB26) A1R2.X vacuum sector
21 days
Jan 6 - Feb 3
Installation of the new central chamber
15 days
Feb 3 - Feb 21
Bake-out of the IP2.X and A1R2.X
3 days
Jul 1 - Jul 3
Installation of the (RB24) A1L2.X vacuum chambers
9 days
Jul 6 - Jul 17
Bake-out of the (RB24) A1L2.X
304 days
Jan 1 - Feb 28
Central chamber production (MATERION)
87 days
Mar 1 - Jul 1
Central chamber post-production actions, coating and acceptance
245 days
Jan 1 - Dec 10
Production of the components for RB24 & RB26 upgrade

## Slide 3
Experimental vacuum upgrade project – LS2 preparation & planning
CMS EXPERIMENTAL VACUUM UPGRADE
Main VSC deliverables:
Removal of IP5.X vacuum chambers up to ± 18m from IP5
Installation of IP5.X vacuum layout
Production of a new central chamber
Production of new aluminium chambers for forward layout
Version – 27/06/2018
Josef Sestak
2018
2021
Today
Q1
Q3
Q1
Q3
Q1
Q3
Q1
2018
2019
2020
2021
Start of LS2
Dec 3, 2018
End of LS2
Feb 20, 2021
Venting the IP5.X
Dec 5
Recommissioning with beam
Mar 5
Intermediate neon injection
Oct 12
Final neon pump-down
Feb 15
Central chamber VC5C - contract signed
Jun 11
Central chamber VC5C - installation
Jun 29, 2020
New layout - installation
Jul 6
10 days
Feb 20 - Mar 5
Machine check-out
15 days
Feb 6 - Feb 27
Removal of IP5.X vacuum chambers
60 days
Jun 29 - Sep 20
Installation of a new IP5.X vacuum layout
15 days
Sep 20 - Oct 9
Bake-out of IP5.X
415 days
Jun 11 - Jan 13
Central chamber VC5C - production
120 days
Jan 13 - Jun 28
Central chamber VC5C - acceptance and NEG coating
109 days
Jan 1 - May 31
New layout - qualification tests and order preparation
174 days
Jun 1 - Jan 31
New layout - production (external)
261 days
Feb 1 - Jan 31
New layout - production (in-house assembly)
360 days
Nov 15 - Apr 1
New layout - acceptance and NEG coating

## Slide 4
Experimental vacuum upgrade project – LS2 preparation & planning
LHCb EXPERIMENTAL VACUUM UPGRADE
Main VSC deliverables:
Removal of IP8.X vacuum layout including RB84 drift chamber (LHC access)
Installation of UX85 vacuum chambers
VELO Mk2 RF boxes etching, leak detection, vacuum acceptance and NEG coating
New vacuum sector A1L8 upstream of VELO
Version - 27/06/2018
Josef Sestak
2018
2021
Today
Q1
Q3
Q1
Q3
Q1
Q3
Q1
2018
2019
2020
2021
Intermediate neon injection
Mar 30
Final neon-pump-down
Jan 8
Recommissioning with beam
Mar 5
End of LS2
Feb 20, 2021
Venting the IP8.X
Dec 6
Start of LS2
Dec 3, 2018
VELO Mk2 RF boxes - installation
Jan 6
8 days
Jan 7 - Jan 16
UX85 vacuum chambers - removal
34 days
Dec 17 - Jan 31
Control rack movement & VELO vacuum control tests
10 days
Jan 20 - Jan 31
UX85 vacuum chambers - installation (UX85-1)
10 days
Feb 17 - Feb 28
UX85 vacuum chambers - installation (UX85-2/3/4)
15 days
Mar 9 - Mar 27
Bake-out of the IP8.X
10 days
Feb 20 - Mar 5
Machine check-out
163 days
Sep 2 - Apr 15
VELO Mk2 - upgrade (VSC support only)
91.4 wks
Apr 1 - Dec 31
2/4 RF boxes available for test and NEG coating
196 days
Apr 1 - Dec 31
4/4 RF boxes available for test and NEG coating
348 days
Aug 1 - Dec 1
Equipment for a new A1L8 layout - Ordering, Fabrication, Testing
3 days
Jan 6 - Jan 8
Installation of a new layout in A1L8 - (to be coordintaed with VELO activities)