## Slide 2: SPS LS2 2019-2020 - aC coating campaign - flange impedance reduction
What are we going to coat
Where are we coating
When => planning
Some Slides from: P. Cruikshank LIU & TE/VSC activities, 23/6/2016

## Slide 3: What are we going to coat: - QF - SSS QF - LSS Drifts tubes
NO MBB and QD

## Slide 4
SSS
1 cell = 63.995 m
Coating lab in surface building
MBB
MBB
MBA
MBA
MBA
MBB
MBB
MBA
MBA
QF
SSS
SSS
QD
QF
What are we going to coat
+ drifts to 181

## Slide 5: What are we going to coat
BA1
BA2
BA3
BA4
BA5
BA6
Meyrin, P1 LHC
(magnet lift)
Prevessin site
(magnet lift)
RF
TT40 ext
TT20 ext
Future
dump
Injection
& Dump
TT60 ext
ECX5
BHA5
(magnet lift)
9 QF (EYETS 2016)
QF activity includes QF & SSS QF treatment (aC & IR) LS2: 87 QF to be coated in SPS !
87 SSS QF to be coated in 867
(LS2)
(LS2)
(LS2)
(LS2)
(LS2)
Mandate QF and SSS QF aC coated:
EYETS/YETS – up to 1 ARC
SPS
LS2 – complete 6 arcs

## Slide 6: What are we going to coat: ECR: SPS amorphous carbon coating in LS2 2019-2020 WPA: Amorphous carbon coating and vacuum flange impedance reduction in SPS during the long shutdown 2 WDP: 1429 in work Impact (once WDP finished)

## Slide 7: Dose Analysis based on EYETS “Real doses”
0.43 mSv
4.7 mSv
From analysis:
With some assumptions for higher dose

## Slide 8: Planning
Treatment zone | Transport via | 2019 |  |  |  | 2020 | 
 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
arc 5- | BA3 | X |  |  |  |  | 
arc 4- | BA3 | X |  |  |  |  | 
arc 3+ | BA3 |  | X |  |  |  | 
arc 3- | BA3 |  | X |  |  |  | 
arc 2+ | BA3 |  |  | X |  |  | 
arc 5+ | BA6 |  |  | X |  |  | 
arc 6- | BA6 |  |  |  | X |  | 
arc 6+ | BA6 |  |  |  | X |  | 
arc 1- | BA6 |  |  |  |  | X | 
arc 1+ | BA6 |  |  |  |  | X | 
arc 2- | BA6 |  |  |  |  | X | 
closure | - |  |  |  |  |  | 
Planning sequence for aC coating and flange impedance reduction during LS2
Acces BA6 !!

## Slide 9
Planning
Week 3-4: dismounting 5- + transport to 867 + equipment to TNL
Access SPS 21 January => 14 January = week 3
01/11/2018

## Slide 10: 5- coating activities
EDMS link: Detailed list of LS2 aC coating
QF’s to be coated in tunnel
SSS QF’s to be:
Dismounted
Transported to 867
Coated in 867 or 181
Reinstalled in SPS
2 magnets on girder
magnets stand alone
magnets + QF drift
QF drift stand alone
SSS QF elements
name
weight
length

## Slide 11: EYETS 2016-2017
  In parallel with a-C coating:
  Impedance reduction (I.R.) campaign for QF-SSS
INCLUDED IN LS2
project

## Slide 12
Planning
Week 3-4: dismounting 5-
Week 8: re-mounting 5- and dismounting 4-
Access SPS 21 January => 14 January = week 3
181 and 867; Coating + I.R.
SPS; Coatings + I.R. at the end

## Slide 13: Coating process
Training sessions in the next few week, already started => end of year
Both for SSS QF (867 set-up) and QF (Tunnel set-up)
867; 2 coating systems:
Basis sequence: 1 coating/ week/system (in EYETS: 1.5 /week/system)
Now: 5 coating runs in 3 weeks
SPS; 2 coating systems
Basic seq: 1 coating/week/system (in EYETS: 1.5 /week/system)
Now: 4 coating runs in 3 weeks
Mounting and coating procedure is under progress
Database for project: under construction ( Ole)
SEY measurements: Danilo …..

## Slide 14: Who
Location | Man power for coating activities |  |  | 
181 | Process engineer + 1 FSU |  |  | 
SPS | Process engineer + 1 technicien + 1 FSU |  |  | 
867 | Process engineer + 1 technicien + 1 FSU |  |  | 
Dismounting / re-installation: Tony Mongelluzzo + 1 person
SEY measurements: Danilo Zanin …….

## Slide 15: MERCI Question? Remarks ?

## Slide 16: Who
Location | Man power
181 | P.E. + 1 FSU
SPS | P.E. + 1 mech. + 1 FSU
867 | P.E. + 1 mech. + 1 FSU
Location | Man power
181 | Antonios Sapountzis
SPS | Wil / Harold
867 | Wil / Harold
Process engineer (during first period *)
*: more people trained during starting phase
Mechanics
Spyros Fiotakis
Paul Garritty
Ludovic Mourier
Giovanni Marinaro
Tony Mongelluzzo (reduced act.)
New TTE (03/04 2019, as G.M. => LHC)
Ole Gunnar Sveen *
FSU
Jerome Gremion
Charles Erik Moreillon
3rd FSU
Joker *
Pedro
Alban

## Slide 17: SPS LS2 2019-2020 - aC coating campaign - flange impedance reduction
What are we going to coat
Where are we coating
When => planning
Who => planning
How => Training
Safety and Access issues

## Slide 18: General Access Injectors
Acknowledgements: T.Otto, M.Tavlet
Please CHECK in ADaMS !!!
* See next slide
*
01/11/2018

## Slide 19: Safety electrical safety requirements
Additional requirement according to WPA:
Habilitation Electric-Person making Test in Labs or on Test Bench- Initial (10250) 1 OR
Habilitation Electric Electrician low Voltage 1
Habilitation Electric for non Electrician 2
1: for persons cabling power supply to cathode assembly and start coating process.
2: for persons making mechanical assembly of coating set-up.
01/11/2018

## Slide 20: General safety/ RP remarks:
01/11/2018
Several other equipment in environment where we are working:
  We don’t touch equipment that we don’t know
In SPS: red/white band + flash light around magnet + coating set-up
Info attached to system who is responsible for the coating + tel. nr.
- In 867: stay in our “zone” + info above
Lots of co-activity:
  Keep working place clean *
  Keep an eye on other activities: can they have an impact on our work?
  Please react if co-activities don’t go together !
* Cleaning working place:
When dismounting gaskets that have seen the beam: radioactive waste !
collect together in one bag => TREC
All other waste: select / separate and take away => No TREC.
  BE SURE NOT TO MIX UP !!!!!

## Slide 21: Access rights and safety equipment
EVERYONE who enters the SPS MUST have the following:
Completed the correct courses. See previous slides
The correct access authorisation (via EDH). CHECK YOUR ACCESS RIGHTS HAVE NOT EXPIRED!!!!
  Zone Code “SPS” for access into the SPS
  Zone Code “SPS-KN-000” for “Autorisation conduite RTL”
  Zone Code “SPS-KN-001” for “SPS Shutdown Padlock” (only used during Long Shutdowns)
  P.P.E.
Safety shoes.
Biocell. (next slide)
Electronic dosimetre.
Passive dosimetre. (All contractors must have an additional company passive dosimetre!!)
Helmet plus Light.
A valid approved IMPACT. (with their name included on this IMPACT)
They must know the number of this IMPACT.
Please note that personnel are not allowed to work in the tunnel alone!!
RTL training not longer required for staff, for driving without lorry
01/11/2018

## Slide 22: Access rights and safety equipment
EVERYONE who enters Building 867 MUST have the following:
Completed the correct courses: electrical courses / radiation protection course
The correct access authorisation (via EDH). CHECK YOUR ACCESS RIGHTS HAVE NOT EXPIRED!!!!
  0867
  0867-R ALL
  0867-R-W25
  P.P.E.
Safety shoes.
Electronic dosimetre.
Passive dosimetre. (All contractors must have an additional company passive dosimetre!!)
A valid approved IMPACT. (with their name included on this IMPACT)
They must know the number of this IMPACT.
Please note that personnel are not allowed to work in building 867 alone!:
For aC coating process: process regulation/ check during day-time: OK
mounting / dismounting: always be two
Weekend: no Access !! (in case of “urgent issues”: two people to come during W,E.)

## Slide 23: Not possible without….
TE-MSC
  SSS & QD electrical & hydraulic disconnection/reconnection
  SSS dismantling and reinstallation
EN-HE
  SSS dismantling, tunnel & surface transport, reinstallation
BE-BI
  Instrumentation cabling disconnection/reconnection
EN-ACE
  Planning framework and advice
  Realignment of displaced magnets & BPH/BPV
HSE
  Guidance & preparation of the safety file
  Radiation surveys & Work & Dose Planning advice