## Slide 1: LS2 preparatory meeting
A.Tauro

## Slide 2: General information
LS2 duration: 27 months
Access mode: general
Underground visits: possible from 16 December 2018 (no visits during Xmas closure)
IMPACT requests: possible to make one request per activity (e.g. TPC disconnection). Not possible to make generic request to cover 1 year…
RP: personal dosimeter needed (no declassification)

## Slide 3: LS2 master plan

## Slide 4: December timeline
3 Dec ‘18
LS2 starts
Open L3 doors
Remove shieldings
Extract TRD SM6
10 Dec
19 Dec
Disconnect PP0/PP1
Remove forward detectors and beampipe
21 Dec ‘18
13 Dec

## Slide 5: December key dates
ZEM removal: 3 Dec
BLM removal: 4 Dec
PMD removal: 7 Dec
FMD1-V0A and T0A removal: 10 Dec
ADA removal: 10 Dec
TPC disconnection: from 3 Dec
ITS disconnection: from 11 Dec
Open L3 doors: Friday 14 Dec
TRD6 disconnection: 17-18 Dec
TRD6 extraction: 19 Dec
Please make sure you are available on these dates!

## Slide 6: LS2 planning meetings
Daily meetings from 3rd Dec at 16h30 (P2) – No Vidyo unless specifically requested
Weekly meetings, every Friday at 10:00 (P2) – Vidyo and INDICO

## Slide 7: Underground access in December
w49:
  No access between 6:00 AM and 10:00 AM (ALTEAD only)
  Restricted access between 10:00 AM and 17:00 PM (Miniframe disconnection)
  Normal access after 17:00 PM
w50:
  No access between 6:00 AM and 10:00 AM (ALTEAD only)
  Normal access after 10:00 AM
w51:
  Normal access
No activities foreseen during Xmas closure

## Slide 8: EN-EL interventions
Test secours: 19 Dec 2018 6:00 AM to 6:10 AM – no access from 5:00 AM to 8:00 AM
AUG on Monday 25 March 2019 - no access on site (both surface and underground)
Diesel maintenance: 1 Apr 2019
CERN wide 66kV maintenance: 28 May 2019 to 19 July 2019 – reduced consumption (i.e. no magnets)
18kV, 3.3kV and LV network maintenance:
  Mon 20 to Wed 22 Jan 2020: 3 days no general services - no access on site (both surface and underground)
  Thu 23 to Fri 24 Jan 2020: 2 days ‘’Limited access’’  details being worked out
AUG on Monday 27 January 2020 - no access on site (both surface and underground)
Auto transfer test: 11 Apr 2020
BIW test: 5 and 6 Oct 2020 from 18:00 to 00:00 – no access underground

## Slide 9: EN-CV interventions
Big maintenance:
  SF: from Nov 2019 to mid Jan 2020. NO impact on ALICE as both magnets will be OFF.
  UW: stop UX mixed water for 2 days in week 40/2019 (October).
  SU: various small perturbations + 1 day stop all cooling UX + 1 day stop all cooling SXL2 in week 16/2020 (April).
Small maintenance:
  UW: from mid Aug 2020 to mid Sep 2020. Stop mixed water UX for 1 day in week 37/2020 (September).
  SF+SU: weeks 45-47/2020: cleaning towers (stop SF 1 week) + 1 day stop all cooling UX.
Ventilation:
  Maintenance SXL2 cleanroom before April 2019. Procedure to be established (CV).
  SG2: w7/2019
  Gas extraction: w8/2019
  UX25 cavern: May 2020 (tbc)
  MCH and MTG: Apr 2020 (tbc)
  L3: Apr 2020 (tbc)
  ITS: Apr 2020 (tbc)
Raw water:
  Test after Apr 2019. Short interruption (1 day), can be used tap water during the test.

## Slide 10: Gas systems status
 | Xmas status | LS2 status
TPC | TPC disconnected | Detailed plan exists
TRD | Xe recuperation early Jan-19 | Run CO2 till Oct-19, and with Xe from Nov-19
TOF | Back-up with R134a | Back-up with R134a until late 2020. Need a few weeks with system ON in late 2019 or 2020 (tbc)
HMP | Always under Ar backup; stop CH4 3-Dec-18 | Always under Ar backup
PHO | Keep N2 until 14-Dec-18, then OFF | OFF till Oct-19, then need N2
CPV | OFF | OFF till Oct-19, then need gas (Ar/CO2 80/20) Need humidifier in RUN3
PMD | OFF | Dismounting
MCH | OFF | OFF till May-19, then need gas (Ar/CO2 80/20)
MTR | OFF; stop i-buthane 3-Dec-18 | missing info

## Slide 11: Safety systems maintenance
Fire detection: w2-3/2019
Gas detection: w7/2019 (in parallel to SG2 ventilation maintenance)
Red emergency phones: 20/2/2019
Fire detection (racks): w10/2019

## Slide 12: CERN Open Days
14 and 15 September 2019

## Slide 13: Optical fibers installation
Planning copper cables (EN-EA)
Mar to Aug: pull cables
ALICE tech.
EN-EA

## Slide 14: Planning optical fibers (EN-EL)
Feb to October: install and test all trunk cables
April 2019: install TPC/ITS fibers after Miniframe installation

## Slide 15: Miniframe planning (rework in SX2)
ALICE tech.
EN-EL
EN-EA
Details about ITS PP1-PP2 cables missing

## Slide 16: Day-by-day sequence w49
ALICE technicians
Institutes
Transport
Other CERN groups
Scaffolding

## Slide 17: UX25 activities w49 – Mon 3 Dec 2018
ALTEAD: open PX24 plug
Close sector valves and vent vacuum sector with air (TE-VSC), access at 8:00 AM (start injection at 9:00)
TE-VSC
Remove TPC gas battery (plug). Disconnect at 8:00 (Chilo)
RP+CV analysis cooling fluids
Start racks lockout
Unrestricted cavern access starting at 8:30 (RP check)
Stop flammable gases
TRD work in SXL2 (whole week)
EN-CV: put ITS cooling plant in Stand-by
Stop beam Sunday 2nd at 18:00
Surface: SX2-CR0 asphalt – until 7 Dec
PMD crates
PMD CROCUS
Klaus: electrical lockout L3 + Dipole
Start warming-up PHOS (10 days)
Remove TPC gas lines
(L3-MNF)
Reinstall crane electronics

## Slide 18
PP0
TPC
MCTS
Miniframe activities w49 – Mon 3 Dec 2018 AM
Remove GEM chambers
Close GEM gas lines (Chilo at 8:00)
Miniframe access from 10:00
After GEM removal: remove winches and reinstall ladder

## Slide 19
PP0
TPC
MCTS
Miniframe activities w49 – Mon 3 Dec 2018 PM
Remove ZEM
Remove BCM
Miniframe access from 10:00
Start at 14:00
TE-VSC: close manual valve (around 15:00)

## Slide 20: UX25 activities w49 – Tue 4 Dec 2018
ALTEAD: open PX24 plug
PMD crates
PMD CROCUS
ALTEAD (SX2): start bringing concrete blocks outside
After 17:30
Cavern access from 10:00, restricted access until 17:00
No access CR1-5 and Exhibition
TOF FW upgrade: 4 to 7 Dec
Electrical lock-out compensator magnet (TE-MSC)
ALTEAD (SX2): move TRD rotator (10:00)
ST2

## Slide 21
Miniframe activities w49 – Tue 4 Dec 2018
Cavern access from 10:00, restricted access until 17:00
Disconnect PMD
After 17:30

## Slide 22: UX25 activities w49 – Wed 5 Dec 2018
ALTEAD: MNF roof
Cavern access from 10:00, restricted access until 17:00
Bring down cherry pickers and transport boxes
ST2
Install 7 ‘pallets grillagées’ for TPC (A-side)
TPC/FMD cooling water evacuation
VIC at 15:00
Start at 17:00: remove all MANU cards and CROCUS boxes of ST2
Transport GEMs to GIF++

## Slide 23
Miniframe activities w49 – Wed 5 Dec 2018
Remove RB24 beampipe and cables (TE-VSC)
Disconnect TPC-A
Cavern access from 10:00, restricted access until 17:00
Remove beampipe protection
Remove BLM + cables
Remove BLM + cables

## Slide 24: UX25 activities w49 – Thu 6 Dec 2018
ALTEAD: MNF roof
Cavern access from 10:00, restricted access until 17:00
ST2
After 17:00
ST1
Delivery 11 cable drums (ITS)

## Slide 25
Miniframe activities w49 – Thu 6 Dec 2018
Disconnect TPC-A
Remove ZEM table
Protect beampipe
Remove PMD/FOCal ventilation ducts
Cavern access from 10:00, restricted access until 17:00
Remove yellow support

## Slide 26: UX25 activities w49 – Fri 7 Dec 2018
MNF wall
Remove Stabilizers
ST2
After 17:00
Cavern access from 10:00, restricted access until 17:00
ST1
VIP visit (Luciano, 10:45 to 11:45) – surface only
ALICE TC + TPC: cut 150mm2 cable for EN-EA test
ALTEAD: bring VSC transportation box and put 2 beampipe elements inside

## Slide 27
Miniframe activities w49 – Fri 7 Dec 2018
Disconnect TPC-A
Remove
PMD + CROCUS support
Cavern access from 10:00, restricted access until 17:00
Remove ADA shielding
And remove beampipe protection
Start at 10:00. Pieter: disconnect gas pipes
After PMD removal: install wooden access
Remove
MCTS beam

## Slide 28
Miniframe activities w49 – Sat 8 and Sun 9 Dec
Disconnect TPC-A
Disconnect FMD1-2 services
Borge + Jimmy: Sunday PM
Remove
ADA + cables
Possible on weekend? TBC

## Slide 29: P2 status as of today
Shieldings: 12/13 beams PX24 removed, Miniframe roof opened
RB24 beampipe removed (along with cables)
Detectors: BLM, BCM, ZEM removed (along with cables). PMD being removed now. Disconnection of ST2 started (FE electronics, CROCUS modules and patch cables removed)
TPC disconnection (A-side) started on Wednesday
ADA shielding being removed now

## Slide 30: Photos w49

## Slide 31: Photos w49

## Slide 32: Photos w49

## Slide 33: Day-by-day sequence w50
ALICE technicians
Institutes
Transport
Other CERN groups
Scaffolding

## Slide 34: UX25 activities w50 – Mon 10 Dec 2018
Cavern access from 10:00
Start emptying CR1, switch off CR1 by end week
ST2
MNF wall
EN-CV: empty ITS/SPD cooling plant tanks + lockout
ST1
All racks locked-out
Guide training (15:00 to 16:00)
Remove green fences (Didier)
Removal of the four quadrants from the Cradle  ALTEAD + Jaap
ALTEAD transport 4 ST2 quadrants to SX2
LV busbar

## Slide 35
Miniframe activities w50 – Mon 10 Dec 2018
Disconnect TPC-A
Remove
FMD1-V0A and T0A
Cavern access from 10:00
Remove
ADA + cables
Install temporary protection (net)
Remove Radmon
T0A: remove crates in racks C33-34

## Slide 36: UX25 activities w50 – Tue 11 Dec 2018
Ventilation (top+MNF)
Unbolt door
No access inside L3
No access Dipole/FASS
Unrestricted cavern access
Disconnect TPC laser cables
VIP visit (A.Knospe, 16:50 to 17:20) – surface only
Start at 6:00 (Didier + ALTEAD)
ALTEAD transport 4 ST2 quadrants to SX2

## Slide 37
Miniframe activities w50 – Tue 11 Dec 2018
Disconnect ITS PP1 (attach cables on TPC)
Disconnect power and cooling comp.magnet
Unrestricted cavern access
MCTS scaffolding
Remove comp. magnet
Disconnect TPC

## Slide 38: UX25 activities w50 – Wed 12 Dec 2018
No access inside L3
Open O-side door
Unrestricted cavern access
Remove Stabilizers
No access Dipole/FASS
ST3
VIC at 15:00. Dismantle the LV filter boxes of CH5 (and perhaps CH6)
Transport GEMs to GIF++
Start at 6:00

## Slide 39
Miniframe activities w50 – Wed 12 Dec 2018
Disconnect ITS PP1 (attach cables on TPC)
Unrestricted cavern access
Remove power/control cables comp.magnet
(store in UX cavern) (EN-EL)

## Slide 40: UX25 activities w50 – Thu 13 Dec 2018
MNF wall
Transfer blocks from I to O-side
L3 access bridge
Start L3 access without watcher
Cavern access from 10:00
ST3
Put TRD scaffolding
PHOS cooling
Clean the compressor and pump stations, collect and remove residual C6F14. RP check (Klaus)
Start LHC tunnel access

## Slide 41
Miniframe activities w50 – Thu 13 Dec 2018
Disconnect ITS PP1 (attach cables on TPC)
Cavern access from 10:00
Remove
beampipe shielding behind ADA
Remove cooling hoses comp.magnet
(store in UX cavern) (EN-CV)
Start at 8:30

## Slide 42: UX25 activities w50 – Fri 14 Dec 2018
Open I-side door
Unrestricted cavern access
Ventilation (bottom+ top)
Continue Saturday if not finished (2 people ALTEAD needed)
ST3
PHOS cooling
ALTEAD + P2 tech (SX2): load test Miniframe lifting jig

## Slide 43
Miniframe activities w50 – Fri 14 Dec 2018
Disconnect ITS PP1 (attach cables on TPC)
Install cable baskets
Install cable baskets
ALTEAD: bring compensator magnet to SX2
Disconnect PP0
Unrestricted cavern access
Remove beampipe sticking out from LHC tunnel
Put plate to close shielding opening
Remove beampipe beam

## Slide 44: Day-by-day sequence w51
ALICE technicians
Institutes
Transport
Other CERN groups
Scaffolding

## Slide 45: UX25 activities w51 – Mon 17 Dec 2018
Start UX visits (Sunday 16 December)
TRD wall
Disconnect
6 TRD SMs
Unrestricted cavern access
TOF: disconnect services in view of TRD6 extraction
Visit (77 people, 13:30): Despina
TRD survey
Noise measurement
Switch-off CTP crates
EN-CV: put TRD cooling plant in stand-by and drain water

## Slide 46
Miniframe activities w51 – Mon 17 Dec 2018
Disconnect TPC-A (after working hours)
Disconnect ITS PP1 (attach cables on TPC)
Disconnect PP0
(unfold cables into miniframe)
Disconnect ITS/SPD/TPC cooling hoses (nacelle)
Disconnect optical fibers (nacelle)
Unrestricted cavern access
See TRD patch panel (Kai, Arturo)

## Slide 47: UX25 activities w51 – Tue 18 Dec 2018
TRD platform and rotator
Disconnect TPC-C
Unrestricted cavern access
Cavern lift maintenance from 6:00 AM to 8:00 AM, cavern access after 8:00 AM
MTR
Nacelle
Noise measurement
Check of FE card extraction tools + visit of CERN EN-EA-CT team. Need to open one half plane of MTR

## Slide 48
Miniframe activities w51 – Tue 18 Dec 2018
Disconnect TPC-A (after working hours)
Disconnect ITS PP1 (attach cables on TPC)
Disconnect PP0
(unfold cables into miniframe)
Disconnect ITS/SPD/TPC cooling hoses (nacelle)
Disconnect optical fibers (nacelle)
Unrestricted cavern access
Cavern lift maintenance from 6:00 AM to 8:00 AM, cavern access after 8:00 AM

## Slide 49: UX25 activities w51 – Wed 19 Dec 2018
Extract TRD6
ALTEAD: bring TRD6 in SXL2 tent (transfer into blue frame)
Disconnect TPC-C
Unrestricted cavern access
MTR
Nacelle
Noise measurement
EN-EL: test secours. Cut general-services (6:00 AM - 6:10 AM). No access from 5:00 to 8:00
Transport GEMs to GIF++
Switch-over to ARCAL 10 (SG2)
ALTEAD (SX2): bring big PX24 beams outside

## Slide 50
Miniframe activities w51 – Wed 19 Dec 2018
Disconnect TPC-A (after working hours)
Disconnect ITS PP1 (attach cables on TPC)
Disconnect PP0
(unfold cables into miniframe)
Unrestricted cavern access

## Slide 51: UX25 activities w51 – Thu 20 Dec 2018
Remove TRD scaffolding
Remove TRD platform and walls
Disconnect TPC-C
Unrestricted cavern access
MTR
Nacelle

## Slide 52
Miniframe activities w51 – Thu 20 Dec 2018
Disconnect ITS PP1 (attach cables on TPC)
Disconnect PP0
(unfold cables into miniframe)
Unrestricted cavern access
Remove beampipe protection
between MNF and TPC

## Slide 53: UX25 activities w51 – Fri 21 Dec 2018
Remove TRD walls
No access cavern whole day (ALTEAD starts at 6:00 AM)

## Slide 54
Miniframe activities w51 – Fri 21 Dec 2018
No access cavern whole day (ALTEAD starts at 6:00 AM)
Remove MCTS scaffolding

## Slide 55: Activities Xmas closure

## Slide 56: Activities Xmas closure
No access to CERN during Xmas closure. Please send an email to us (Arturo/Andre) before Wednesday 19.12 if you plan to access CERN.
BE-ICS: evacuation sirens tests – 27.12 from 8:00 to 12:00

## Slide 57: Jan-Feb activities 1/2

## Slide 58: Jan-Feb activities 2/2

## Slide 59: TPC preparation (cleanroom)

## Slide 60: Day-by-day sequence w2
ALICE technicians
Institutes
Transport
EN-EA
Scaffolding
Other CERN groups
Pakistani team

## Slide 61: UX25 activities w2 – Mon 7 Jan 2019
Disconnect TPC-C
ST3
Arrival 5 Pakistani team
Install Solar crates, remove CROCUS, cables, boxes (nacelle, scaffolding)
Maintenance fire detection, whole week
Start removing ITS crates from racks (tbc)

## Slide 62
Miniframe activities w2 – Mon 7 Jan 2019
Remove MCTS

## Slide 63: UX25 activities w2 – Tue 8 Jan 2019
Disconnect TPC-C
ST3

## Slide 64
Miniframe activities w2 – Tue 8 Jan 2019
Miniframe lifting jig

## Slide 65: UX25 activities w2 – Wed 9 Jan 2019
Disconnect TPC-C
ST3

## Slide 66
Miniframe activities w2 – Wed 9 Jan 2019
Miniframe to surface
SX2: put Miniframe and MCTS on blocks

## Slide 67: UX25 activities w2 – Thu 10 Jan 2019
Remove laser platform
Disconnect TPC-C
ST3
Scaffolding ITS/SPD inox pipes
EN-EL: install CR0 UPS switchboard
Bring platform to SX2 and connect power to laser

## Slide 68: UX25 activities w2 – Fri 11 Jan 2019
TPC survey
TPC survey
ST3
Scaffolding PP0

## Slide 69: Storage in December

## Slide 70: SX2 in December, storage
PX24 beams
UX25 blocks
V0A-FMD1  3297
ADA  3297; ADA shielding  SU2
PMD ventilation pipes  bin
ZEM  3297; ZEM table  SU2
RB24 beampipe + vacuum equip. FLEX
Beampipe protection  SU2
BCM  Pieter
BLM  BLM team
TPC black hoses and supports  3297
ITS PP1 and PP0 services  bin
TRD table  outside behind tent
Detector crates  610
Comp.
magnet
PX24 beams
All blocks evacuated before Xmas
PX24 beams outside SXL2
UX25 blocks on the parking, next to SG2

## Slide 71: SXL2 in December, storage
TRD, EMCal rotators
Delphi frame
7-21 Dec: PMD dismantl.
L3 ventilation pipes  SXL2 ?
TRD6
Yellow platform