## Slide 2: Wi-Fi Service Enhancement at CERN Project overview
Adam SOSNOWSKI
adam.sosnowski@cern.ch
Vincent DUCRET
Vincent.ducret@cern.ch

## Slide 3: Agenda
Initial situation (before 2016)
WiSE project
Global project timeline
Pre-deployment site preparation
Tender process & Technical evaluation
Final technical setup overview
Deployment process & Communication with users
Project management
Problems and challenges
Next steps

## Slide 4: Initial situation (before 2016)
Wi-Fi service was provided in conference/meeting rooms and few buildings
No possibility of roaming between buildings, nor often between floors in a single building
No guest Wi-Fi
Autonomous access-point configured independently of each others
Power/frequency setting done manually
Not scalable for global campus deployment

## Slide 5: WiSE Project
= Wi-Fi Service Enhancement project
Goals of the project, launched in 2015:
  Provide high quality Wi-Fi coverage in all office buildings and public areas across the CERN campus (~200 buildings)
  Ensure seamless roaming within the Wi-Fi coverage area
  Support the latest available Wi-Fi standard 802.11ac
  Provide additional services such as Wi-Fi for visitors

## Slide 6: Global project timeline
2017
2018
2016
2015
Wi-Fi Planning and Validation
RF Simulation + Site survey
to validate the AP positions
Pilot implementation
3 buildings, including a restaurant
New Wi-Fi infrastructure deployed
Guest Wi-Fi pilot
Market Survey
Technical Evaluation
First activated building
Global deployment
New AP installation
Post deployment Site surveys
Tender Process
Cabling of the Buildings
Outdoor deployment

## Slide 7: Pre-deployment site preparation
Install the access-points where the users are located
Minimize the cell size to provide a better signal quality
before 2016 after 2016
1 Access-point per 3 offices on average, installed inside the office
1 new outlet per office for future proof (Cat6A cabling)

## Slide 8: Pre-deployment site preparation
For each building:
RF simulation to estimate the AP position
Site Survey to validate the deployment plan
Cabling (new outlets)

## Slide 9: Tender process
Tender process
  Five vendors contacted
  Three replied
  One bid was rejected based on the documents (technically not compliant)
  Equipment from two bidders were tested
Technical evaluation
  Trial devices, similar to the ones proposed in the bid
  Two months of tests
  Dedicated building (226)

## Slide 10: Technical evaluation
Test setup in a dedicated building
Detailed test book
Ixia Wifi client generator (rented)
Test overall behaviour + possible integration with our own tools

## Slide 11: Test environment
Controllers
Routers, switches and connection to GPN
Iperf/FTP server
Access-Point

## Slide 12: Test environment
Several Access-Points

## Slide 13: Test environment
“Office”
Access-Points

## Slide 14: Test environment
Ixia tests (in the basement)

## Slide 15: Final technical setup overview
Tender winner:
Aruba controller-based solution
  Traffic centralisation for seamless roaming
  Configuration centralisation
  Scalability and redundancy
  Radio Frequency settings automation
  Configuration automation using API

## Slide 16: Final technical setup overview

## Slide 17: Final technical setup overview
Configuration automation:
  Based on the API available on the Mobility Master
  Simplifies deployment process
LANDB
MM
CFMGR
NETMGR

## Slide 18: Deployment process
Preparation to RF simulation
FirstLine (EMTE)
CS-CE
RF simulation
CS-CE
Pre-deployment RF Survey
FirstLine (EMTE)
CS-DO
Starpoint review
CS-DO
Cabling
AP Deployment
EMTE
CS-DO
AP set up
FirstLine (EMTE)
CS-CE/DO
FirstLine (EMTE)
CS-DO
Switch installation & set up
CS-CE CS-DO
Post-deployment RF Survey

## Slide 19: Communication with users
Activated buildings
Buildings to be equipped with APs

## Slide 20: Project management
Example of Project report

## Slide 21: Problems and challenges
Planning and communication challenges
  Explain the disturbance to the end user (cabling inside the building, etc…)
  Scheduling and synchronizing all the works
Technical challenges
  New version = bugs
  Internally developed tools adaptation
  Managing the network – software upgrades and monitoring
Others
  Aesthetics (removing old APs)
  Some concerns about RF and AP inside the offices

## Slide 22: Problems and challenges
Planning and communication challenges
  Explain the disturbance to the end user (cabling inside the building, etc…)
  Scheduling and synchronizing all the works
Technical challenges
  New version = bugs
  Internally developed tools adaptation
Others
  Aesthetics (removing old APs)
  Some concerns about RF and AP inside the offices

## Slide 23: Next steps
Finish deployment in Office area and Outdoor coverage
Prepare plan to replace old HP infrastructure and provide coverage in technical areas
Add controllers to the cluster to keep initial redundancy level (>4.000AP)
Upgrade security of the Wi-Fi networks to WPA3 (when it will be standardize)
Test and evaluation of new APs with ZigBee radio

## Slide 24
Any questions?