## Slide 1: Report: 1 Activity: LHC Insulation Vacuum
Name Jaime Perez Espinos
Meeting 12/10/2018

## Slide 2: Performed activities during last 2 weeks
Preparations:
  Turbo mobile pumping groups fully assembled and being tested
  Dry mobile primary pumping groups: all parts procured
  Leak detection trolleys: first prototype already assembled; procurement of parts ongoing

## Slide 3: Planned activities for next 2 weeks
Preparations
  Finish validation of turbo mobile pumping groups (AL4030)
  Mechanical assembly and test of one complete dry mobile primary pumping group (Wim + AL4030)  mechanical assembly of the others (AL4030)
  Mechanical modification and assembly of LD trolleys (Wim+Alexis+FSU)
Maintenance of pumping groups (4+17 OFF), before Christmas period (CERN+AL4030); warm-up to be started after Christmas

## Slide 4: Resources distribution
Wim: preparations + maintenance
Natalia: preparations (documentation, data storage, etc.) + support maintenance
Jaime: follow-up preparations + planning
AL4030: 2 people allocated to LS2 preparations + 1 team (2 people) assigned to pumping group maintenance (TBC)

## Slide 5: Technical problems
Not directly related to LS2 activities but 17 pumping groups OFF following power cuts on Dec. 5th

## Slide 6: Dashboard and work evolution
-

## Slide 7: AOB
-

## Slide 8: Thank you !