## Slide 1
 | DFH-DFM meeting: List of on going Actions |  |  | Status
 | DFHx |  |  | 
Hx1 | Functional specifications need to be finalised with the given input and shared  EDMS 2052656 | YL | Dec. 2018 | Distributed TBD
Hx2 | Listing of instrumentations needs | JF | Q1 2019 | On going
Hx3 | Cost and feasibility analysis of using line D for he gas recovery instead of WRL  Not convenient in 2 boxes configuration | SC | Q1 2019 | Closed
Hx4 | List of instrumentation required by cryogenics | SC | Q1 2019 | 
Hx5 | Comparison on splice routing into single/multiple pipes  DFH-DFM meeting 16 Jan | YL | Dec. 2018 | On going
Hx6 | Studies on the pre-opening of the MgB2 splices | AB, JF | Dec. 2018 | 
Hx7 | Clarification of the SCLink inner/outer tubes mechanical interface (fixed, flexible, free)  independent | AB | ASAP | Fixed
Hx8 | Estimation of the splice and current leads cooling requirements in abnormal operation in the two splices configuration under study (in series with current leads vs in common environment)  DFH-DFM meeting 16 Jan | YL | Jan 2019 | 
Hx9 | Feasibility study of orienting angularly either the MgB2 or the HTS lead  Today’s JD presentation | YL, JD, RB | Jan-2019 | On going
Hx10 | Feedback on DFH proposal | AB,JF | Jan-2019 | 
Hx11 | Sharing of the functional specs of DFH and DFM  EDMS 2052656 & EDMS 2052614 | YL | Dec-2018 | 
Hx12 | Update of cryogenic layout with WRLas agreed upon during meetings  Done See TCC presentation | YL | Jan-2019 | Closed
 | DFM |  |  | 
M1 | SCLink helium tube end : study reduction of the 2m flexible length / study the safe handling of the end/splice box | YL, AK | Dec. 2018 | In progress
M2 | Integration: study 2 options of supporting onto D2 or to the wall/ground | YL, AK | Jan. 2019 | In progress
M3 | Contact transport to know the space required to install/uninstall the D2 on the jacks | YL, RB | Dec. 2018 | Done
M4 | Feedback on pre-design proposal from SCLink/cable point of view | AB, JF | Dec. 2018 | 
M5 | Trigger discussion with MPE to define overall protection strategy for D2-DFM-DSHm | AB | Q1 2019 | 
M6 | Give input on the volume occupied by the MgB2-HTS splices in DFM | JF, AB | Q1 2019 | 
M7 | Finalisation of DFM functional specifications EDMS 2052614 | YL | Dec. 2018 | To be distributed
 | DFHm |  |  | 

## Slide 2
 | DFH-DFM meeting: List of Actions COMPLETED |  |  | Status
 | DFHx |  |  | 
Hx8 | Cryogenic layout proposal for the integration of the two units DFH box | SC | ASAP | 
 | DFM |  |  | 
 | DFHm |  |  | 
5 | Comparison on One-module DFH vs Two-modules DFH solutions | YL | 14-09-18 | Done
7 | Splice geometry input | JF | 14-11-18 | Done
8 | Presentation on cooling of the splices in the DFH | YL | 21-11-2018 | Done
9 | Input on splices displacements | AB,JF |  | Done
10 | Clarify if the presence of CDB is a driving constrains | JF, YL | ASAP | On going