## BWS
STATUS
| Asset # | # | Prototype/Series | In Work (installation of optical disk, forks and lens tubes) | Ready for Vacuum Acceptance Test | Vacuum Acceptance Test | Ready for Calibration | Calibration | Ready for installation (Calibration OK) | Stored/Installed
| ok |  |  | 14 | 14 | 7 | 4 | 4 | 4 | 4
| in progress |  |  | 16 | 0 | 7 | 3 | 0 | 0 | 0
PS | PXBWSRB011-CR000001 | 8 | p | ok | ok | ok | ok | ok | ok | ok
| PXBWSRB011-CR000002 |  | p | ok | ok | ok | ok | ok | ok | ok
| PXBWSRB011-CR000003 |  | s | in progress
| PXBWSRB011-CR000004 |  | s | ok | ok | in progress
| PXBWSRB011-CR000005 |  | s | ok | ok | in progress
| PXBWSRB011-CR000006 |  | s | ok | ok | in progress
| PXBWSRB011-CR000007 |  | s | ok | ok | in progress
| PXBWSRB011-CR000008 |  | s | in progress
PSB | PXBWSRA005-CR000001 | 10 | p | ok | ok | ok | ok | ok | ok | ok
| PXBWSRA005-CR000002 |  | p | ok | ok | ok | ok | ok | ok | ok
| PXBWSRA005-CR000003 |  | s | ok | ok | ok | in progress
| PXBWSRA005-CR000004 |  | s | ok | ok | in progress
| PXBWSRA005-CR000005 |  | s | ok | ok | in progress
| PXBWSRA005-CR000006 |  | s | ok | ok | ok | in progress
| PXBWSRA005-CR000007 |  | s | in progress
| PXBWSRA005-CR000008 |  | s | in progress
| PXBWSRA005-CR000009 |  | s | ok | ok | in progress
| PXBWSRA005-CR000010 |  | s | ok | ok | ok | in progress
SPS | SPBWSRC006-CR000001 | 6 | s | in progress
| SPBWSRC006-CR000002 |  | s | in progress
| SPBWSRC006-CR000003 |  | s | in progress
| SPBWSRC006-CR000004 |  | s | in progress
| SPBWSRC006-CR000005 |  | s | in progress
| SPBWSRC006-CR000006 |  | s | in progress
ESS | PXBWSRB011-CR000009 | 6 | s | in progress
| PXBWSRB011-CR000010 |  | s | in progress
| PXBWSRB011-CR000011 |  | s | in progress
| PXBWSRB011-CR000012 |  | s | in progress
| PXBWSRB011-CR000013 |  | s | in progress
| PXBWSRB011-CR000014 |  | s | in progress

## Plan
CW48 (Monday) | Total | In work | Ready | To do | Rhythm
Number of BWS | 27 | 7 | 0 | 20
In work | 7
Ready for Vacuum Acceptance Test | 5 |  |  |  | 3 per week
Currently under Vacuum Acceptance Test | 1
Passed Vacuum Acceptance Test/Ready for calibration | 1 |  |  |  | 2 per week
Passed Calibration/Ready for installation | 0
CW49 (Monday) | Total | In work | Ready | To do | Rhythm
Number of BWS | 27 | 10 | 0 | 17
In work | 10
Ready for Vacuum Acceptance Test | 6 |  |  |  | 3 per week
Currently under Vacuum Acceptance Test | 1
Passed Vacuum Acceptance Test/Ready for calibration | 3 |  |  |  | 2 per week
Passed Calibration/Ready for installation | 0
CW50 (Monday) | Total | In work | Ready | To do | Rhythm
Number of BWS | 27 | 13 | 0 | 14
In work | 13
Ready for Vacuum Acceptance Test | 7 |  |  |  | 3 per week
Currently under Vacuum Acceptance Test | 1
Passed Vacuum Acceptance Test/Ready for calibration | 5 |  |  |  | 2 per week
Passed Calibration/Ready for installation | 0
CW50 (Monday) | Total | In work | Ready | To do | Rhythm
Number of BWS | 27 | 16 | 0 | 11
In work | 16
Ready for Vacuum Acceptance Test | 8 |  |  |  | 3 per week
Currently under Vacuum Acceptance Test | 1
Passed Vacuum Acceptance Test/Ready for calibration | 7 |  |  |  | 2 per week
Passed Calibration/Ready for installation | 0
CW1 (2019) | Total | In work | Ready | To do | Rhythm
Number of BWS | 27 | 19 | 0 | 8
In work | 19
Ready for Vacuum Acceptance Test | 9 |  |  |  | 3 per week
Currently under Vacuum Acceptance Test | 1
Passed Vacuum Acceptance Test/Ready for calibration | 9 |  |  |  | 2 per week
Passed Calibration/Ready for installation | 0
Note on B4: Dmitry Gudkov: install optical disk, forks, protection, adjust lens tube
Note on B13: Dmitry Gudkov: install optical disk, forks, protection, adjust lens tube
Note on B22: Dmitry Gudkov: install optical disk, forks, protection, adjust lens tube
Note on B31: Dmitry Gudkov: install optical disk, forks, protection, adjust lens tube
Note on B40: Dmitry Gudkov: install optical disk, forks, protection, adjust lens tube