## Slide 1: Items supplied by CERN and procurement plan
Y.Leclercq on behalf of the DF development team WP6a
31 Jan. 2019
Conceptual design review of the DFX

## Slide 2: Items supplied by CERN
Defined in DFX functional specification EDMS 1905633 §4
Insulation vacuum:
  Elastomer seals (specific to the integrated dose)
  Pumps, valves and pressure transducers
Cryogenics:
  Wired instrumentation and electrical feedthroughs
  Electrical heaters
  Safety relief pressure devices
Survey:
  External survey targets for installation.
Circuit protection:
  V-taps feedthroughs.
Test in SM18:
  Supporting structure and installation tooling.

## Slide 3: Procurement plan
Insulation vacuum:
Elastomer seals (specific to the integrated dose) No Yes String test 2021
Hardware (installed @ CERN) No Yes String test 2021
Cryogenics instrumentation, hardware Yes Yes Assy proto Q3 2019
Circuit protection: V-taps feedthroughs. Yes Yes Assy proto Q3 2019
Test in SM18: Supporting structure and installation tooling. Yes No SM18 test Q1 2020
Prototype Series 1st use 1st need
Conceptual design approved
Detailed design approved
Delivery DFX prototype
Cryogenics instru., hardware
Circuit protection hardware
SM18 test supports & tooling
2019 |  |  |  | 2020 |  |  |  | 2021
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | 
Proc. proto
Proc. series
Proc. proto
Proc. series
Design
Proc.
DFX series manufacturing period ???
Common procurement CRG ?