## Slide 1: LIU PS Commissioning Working Group: Scope of the meetings, Topics
D. Cotte, A. Lasheen, F. Tecker

## Slide 2: LIU Commissioning - Structure
Sub-working groups:
Re-commissioning coordinators, other key operators and machine coordinators with equipment/beam dynamics experts
= TEAM that will commission the machine
LIU Commissioning Coordination Committee
Chair team: V. Kain, G. Rumolo, A. Huschauer
Secretary and more: S. Albright
SPS C WG
Chair: K. Li
PS C WG
Chair: F. Tecker and D. Cotte
PSB C WG
Chair: G.P. Di Giovanni, C. Bracco
LEIR / Linac3 C WG
Chair: R. Alemany
Linac4 C WG
Chair: B. Mikulec, A. Lombardi
Commissioning WGs per machine
+ A. Lasheen

## Slide 3: LIU structure
LIU Project Executive committee
M. Meddahi G. Rumolo
LIU SPS LS2 Technical Coordination
Chair B. Goddard
Deputy E. Shaposhnikova
LIU Commissioning Coordination
V. Kain, G. Rumolo, A. Huschauer
LIU PS LS2 Technical Coordination
Chair K. Hanke
Deputy H. Damerau
LIU PSB LS2 Technical Coordination
Chair G.P. Di Giovanni
Deputy B. Mikulec
LIU ions PS Injectors Technical Coordination (Ad-Hoc)
Chair R. Scrivens
LIU Beam Dynamics Coordination
G. Rumolo, H. Bartosik
LIU SPS BD WG
E. Shaposhnikova/
H. Bartosik
LIU PSB BD WG
S. Albright/F. Antoniou/
C. Bracco
LIU PS BD WG
A. Huschauer/ H. Damerau/M. Fraser
LIU ions PS injectors BD WG
Chair N. Biancacci
LIU SPS Commissioning WG
Chair K. Li
LIU PSB Commissioning WG
Chair G.P. Di Giovanni
Deputy C. Bracco
LIU PS Commissioning WG D. Cotte, A. Lasheen, F. Tecker
LIU ions PS injectors Commissioning WG
Chair R. Alemany
ATS management
F. Bordry
Linac4 Commissioning WG
Chair B. Mikulec
Deputy A. Lombardi
Linac4 BD WG
A. Lombardi/J.B. Lallement/G. Bellodi
LIU Linac4 LS2 Technical Coordination (Ad-Hoc)
Chair J.B. Lallement
LIU/HL-LHC EC
IEFC
LS2C
LMC
Project Unit
Safety Officer: A. Funken
Budget Officer: S. Prodon
Installation Coordination Officer: J. Coupard (Dep. F. Pedrosa)
Admin. Support: L. Mainoli

## Slide 4: LIU Project: PS
LIU PS Technical Coordination
Chair K. Hanke
Deputy H. Damerau
LIU Executive Committee
IEFC
LS2C
LMC
LIU Commissioning Coordination
V. Kain, G. Rumolo, A. Huschauer
LIU PS Commissioning WG
D. Cotte, A. Lasheen, F. Tecker
Other projects in PS, as needed
PS Shutdown Coordination
Chair F. Pedrosa
LIU Beam Dynamics Coordination
H. Bartosik, G. Rumolo
LIU PS BD WG
Chairs A. Huschauer, H. Damerau, M. Fraser

## Slide 5: PS C WG members:
BALTASAR DOS SANTOS PEDROSA, Fernando (EN-ACE-OSS)
COTTE, Denis Gerard (BE-OP-PS)
DAMERAU, Heiko (BE-RF-FB)
DELRIEUX, Marc (BE-OP-PS)
DI GIOVANNI, Gian Piero (BE-OP-PSB)
EVRARD, Sebastien (EN-EA-PE)
FRASER, Matthew Alexander (TE-ABT-BTP)
GOURBER-PACE, Marine (BE-CO)
GUERRERO OLLACARIZQUETA, Ana (BE-BI-SW)
HANKE, Klaus (BE-OP-PS)
HANS, Oliver (BE-OP-PS)
HUSCHAUER, Alexander (BE-ABP-HSS)
JACQUET, Delphine (BE-OP-LHC)
LASHEEN, Alexandre (BE-RF-BR)
MIKULEC, Bettina (BE-OP-PSB)
MURILLO GARCIA, Raul (TE-EPC-CCS)
SALVANT, Benoit (BE-ABP-HSC)
SKOWRONSKI, Piotr Krzysztof (BE-ABP-HSS)
TECKER, Frank (BE-OP-PS)
Commissioning coordinators
EN-ACE shutdown coordination
Involved groups’ contacts (RF,BI,CO,ABP,ABT,TE-EPC)
Related PS/PSB meetings representatives
East Area
Specialists invited by topic

## Slide 6: Milestones for "sub" working groups
Finalize operational scenario of existing and new equipment + required tools/algorithms/parameter trees
  Track progress on software development, logging, analysis tools,…
Define date for FESA class/mock interface delivery per system
Define how to test: what can be done with/without beam; think of staged deployment
Define dry runs, reliability runs, hardware commissioning plans
  Prepare check lists and online planning
Define detailed beam commissioning plan: which cycles are needed, which beams, which equipment (when)
  Prepare check lists and online planning
Organize, execute beam commissioning; track progress

## Slide 7: Hardware commissioning period: IST, HWC, Check-out
Sub-working groups: collect from EN/ACE and complete IST list by July 2019
What | details | End date
IST | Definition Conditions, shifts/no shifts Lists per machine Planning by EN/ACE and OP | March 2019 September 2019 July 2019 September 2019
Switch yard | Several options plan with all experts | End of March 2019
Switch yard | Final plan with POPS capacitors | August 2019
HWC and dry runs planning | including resources | December 2019
HWC check lists |  | 3 months before HWC start

## Slide 8: Beam commissioning period – CCC planning
What | details | End date
Injector schedule with FT start up | First version | July 2019
Injector schedule | Refined version | December 2019
Christmas shutdown 2020/21 plan | Critical items; strategy for rapid start-up in January 2021 | December 2019
Feedback LBE run | Lessons learned and consequences for 2020 startup | January 2020
Beam commissioning details | Detailed planning with resources Experts shifts and piquets start dates Cross-machine interdependencies | February 2020 November 2019 March 2020

## Slide 9: Deadlines for Sub-working groups (1)
What | details | End date
Discussion on integration status and topics | Prepare lists per machine: new systems, processes to be defined, algorithms to be prepared,… | April 2019
List of software | Per machine (requires definition of integration, algorithms, processes  might be first version). Man power – collaboration? | June 2019
List of performance tracking parameters | Per machine (to start with) | June 2019
IST lists | Per machine; complete | July 2019
List of beam readiness dates  towards injector schedule | Focus on FT community. What is max intensity required in 2021? Readiness dates with initial beam parameters. When max intensity? | July 2019
to define series of integration talks

## Slide 10: Deadlines for Sub-working groups (2)
Disclaimer: LBE run line = special case
What | details | End date
FESA class readiness dates | Negotiate with groups (estimate for OP development required) per machine | August 2019
IST planning | EN-ACE + OP. Final lists and conditions (e.g. access system SPS) | September 2019
Feedback LINAC4 LBE: HWC | Planning, new check lists. Sufficient preparation for beam? | October 2019
Dry run and HWC planning | Plus DSO tests, power permits | December 2019
Christmas shutdown 2020/21 | List of critical items per machine. Piquet requirements. Which state of machine during X-mas. | December 2019

## Slide 11: PS Commissioning Working Group - Topics
PS interlocks => Denis today
New equipment:
  RF – HW / LLRF
  Inj. Kicker / Septum / Bumpers (inj./extr.)
  TFB
  Wire scanners / BGI (incl. WS bunch-by-bunch)
  BLMs (incl. TT2)
  SEM grids (incl. multi-turn)
  External conditions
  Internal dumps / ralentisseur
  Reference magnet B measurement / compensation cards

## Slide 12: PS Commissioning Working Group - Topics
New equipment: things to be covered
  Functional changes
  FESA software changes and readiness date
  Application software changes
  Procedures to test (IST – HWC – Beam Commissioning)
  Checklist changes
  How much time needed (IST – HWC – Beam Commissioning)
  from when and which other equipment/services/beams required
  Critical items

## Slide 13: PS Commissioning Working Group - Topics
Software / OP general infrastructure, tools
HW checklist
Short Christmas shutdown
Beam commissioning
East Area (incl. HW tests F61)
Any suggestions for topics are welcome

## Slide 14: Extra slides

## Slide 15: LIU CCC Mandate
Identify required checks/commissioning activities for old and LIU equipment across the injectors
Review past beam commissioning experience and define the overall methodology on the basis of lessons learnt;
Review the tools/applications/simulations/monitoring/pre-HW checks/CO required for the commissioning phase, identify outstanding/missing items and fix delivery deadlines, and follow-up progress
Establish the detailed commissioning time line for LHC and FT beams
  Define the LHC beam parameters to be reached throughout the injectors chain as a function of time for:
    LHC INDIV, LHC run2, each LIU commissioning step, LIU
Ensure definition of necessary LS2 dry runs and HWC, including planning of tests with EN/ACE
Establish a draft time line for the the beam commissioning to the final LIU beam performance
Report progress and problems
January 2019

## Slide 16: 4 aspects to cover
Hardware:
  address existing and new equipment
  RF, BI, new injection systems, transfer, EPC,…
  How to integrate, how to prepare, how to test
  New operational scenarios
Tools: next generation settings management, model based generation and correction, new timing approach
Planning for hardware checkout together with controls, special test of tools, new hardware, operational scenarios, DSO tests
  Re-commissioning coordinators putting it together
Beam commissioning time line
  What, how, tools, in which order
  Due dates for LHC and FT beams
October 2017
January 2019

## Slide 17: 2019 Deliverables (1)
Further improved check list and planning tool: requirements were transmitted
Final reference measurement system
Discuss LINAC4 and LBE beam line commissioning plan
  Procedures, required tools
  Use as test bed for new frameworks/tools: FEI, machine learning,…
LINAC4 and LBE beam line commissioning outcome and feed-forward to next commissioning
Define requirements(/implementation) of beam performance tracking tool across injectors
What would an adequate injector timing system look like?
Model based generation of machine settings and higher level parameters and more: super settings, settings per beam type,…
  = Feedback from Settings management working group

## Slide 18: 2019 Deliverables (2)
Need to define dates for dry runs during shutdown
  And prepare them: infrastructure availability,…
Hardware commissioning
  Deliver updated check-out check lists
  Establish planning of hardware tests and check-out
  IST tests
  DSO test with preparation tests and dates
Beam commissioning plans per machine
  Details for existing and new systems
  Which beams when?
  Cross-coordination between different machines. Signal exchange, energy matching,…
  "By product": 2021 injector schedule (start dates for all facilities and more)
Establish and apply strategy to critically review the different activities
  enough contingency, alternative methods,...
  Include ’external’ people such as Jorg, …
  To be further discussed