## Slide 1: Review of DFH key concepts
DFH-DFM meeting : 13 Feb. 2019
Installation general strategy
Leads layout in DFHx1 & DFHx2
Splices cooling principle

## Slide 2: 1. Installation general strategy
Option July 18. Shaping MgB2 cables in UR
  Test in SM18 with extra MgB2 length
  Transport & install compact unprepared MgB2 cables
  Shape, cut to length and prepare in UR
 handling of MgB2 cables in UR identified as critical
 new proposal
UL
UR
SCLink final cryostat
MGB2 cable protected
Interface flange with DFHx1
MgB2 cables with extra length
DFHx1
DFHx2

## Slide 3: 1. Installation general strategy Indico775038
Option November 18 :
No direct MgB2 handling
  Insertion of MgB2 cable in SCLink
  Pre-shape MgB2 ends in protective flexibles & reservoirs in laboratory
  Test of SCLink in SM18
  Transport configuration (on reel) with flexibles and reservoirs on
  Deploy in the tunnel (MgB2 cable untouched)
Cable opening in rigid structure
DFHx1
DFHx2
MgB2 cables in flexibles

## Slide 4: 1. Installation general strategy
3.5m
3.0m
1.0m
1.0m
Limited handling at a cost of:
  Transport of bigger Reel
  Slightly longer DFH cryostats
  DFH mechanical assembly higher complexity
July option not compatible with MgB2 handling limitations
Our proposal is the November option
July Option: Shaping MgB2 cables in UR
November Option: MgB2 cable untouched

## Slide 5: 1. Installation general strategy
3.5m
1.0m
No direct MgB2 handling in the tunnel has a (useful) cost
Is this approach compatible for the cables?
Do we go ahead with the next steps ?
  Move on with more detailed design work
  Prepare for a conceptual design review in march
  DDR by May (in view of FC in June)
November Option: MgB2 cable untouched
Nominal configuration
November Option: MgB2 cable untouched
Transport configuration

## Slide 6: 2. Leads distribution
Initial distribution
  DFHx1 : 2 x 18 kA + 2 x 13kA
  DFHx2 : 3 x 7 kA + 12 x 2 kA
 EM issues identified
Proposed new layout to be confirmed
  DFHx1 : 2 x 18kA + 2 x 13kA + 3 x 7kA
  DFHx2 : 12 x 2kA
  Do we go ahead with this layout for the DFH design ?

## Slide 7: 3. Splices forced cooling principle indico786623
  Splices in parallel circuits with same upstream & downstream pressures
  Pros:
    CL flows independent from splices needs
    ↗ Recovery line flow  ↗ Tinlet + flow around splices (limited effect though)
  Cons:
    Difficult to ensure equal parallel flows
    Limited margin to increase splice flow
    Small flowing sections around splices may limit transient and abnormal high total flows
2 discussed designs
  Splice in series with associated current lead + parallel bypass for transient and non nominal operation
  Pros:
    Abnormal splices needs << CL mass flow
    Mass flow around splice independent from local pressure drop
    Big bypass for transients and control
  Cons:
    ↗ bypass flow does not increase splice flow (only inlet temperature)
    If splices needs more than CL flow  CL may be overcooled (very high margin though)
P1, T1
Pc, Tc
Pa, Ta
P2, T2
P1, T1
P2, T2
Do we go ahead with this concept ?

## Slide 8: Spare slides

## Slide 9: Design MgB2 prepared in UR

## Slide 10: Design MgB2 prepared in SM18

## Slide 11: Sequence proposal
Matching lead with Current lead radial positions (opening of cables bundle)
The MgB2 cables are internally routed and fixed in radial position in the DFHx1 to match the current leads interfaces. (+ installation instrumentation)
Insertion module 2 (sleeves opened)
Installation interfaces with current leads
Environment : no racks installed
SCLink cables ends on supports
SCLink is pre-assembled before all other components. Fixed in position on DFX side. Interface with DFHx1 located within cm. The cable bundle is reduced to minimum diameter for transport purposes.
Insertion module 1: VV1+HeV1
The DFHx1 module is “rolled” around the SCLink cable all the way from DFHx2.
UL
UR
SCLink final cryostat
MGB2 cable protected
Interface flange with DFHx1
MgB2 cables with extra length
DFHx1
DFHx2
Few cm positioning flexibility
Once cables are radially positioned, the internal helium vessel is closed with MgB2 extra length going out in individual tubes (to ease access to individual splice, ease welding, perform clean splice, increase & individualise turbulent flow locally at splice level).
Installation of interface with DFHx2 and interface flange with current leads.

## Slide 12: Sequence proposal
Assembly current leads
Racks and current leads are installed around the DFHx1. flexible ends of current leads are connected to DFHx1 interface flange.
Adjust MgB2 leads to length
HTS end lengths of current leads are fixed, in order to face few cm positioning of the SCLink in the tunnel + solder on “fresh unsoldered MgB2 + to optimise the splice performance, it is suggested to cut the extra length of MgB2 at this stage.
Splice
Splices are independent (for DFHx1 18kA and 13 kA leads). Other splices can be independently protected when working around. Installation of V-taps
Close sleeves
It is suggested to use standard interconnection sleeves with standard tooling for cutting and welding.
Close vacuum vessel
The vacuum vessel is a sleeve itself closed with standard elastomer O-rings (LHC type connection).
Transient phase
The insulation vacuum is common with current leads and SCLink. Pumps and relief plates are assembled on module1.
During cool down, the internal helium vessel is fixed in the middle, splices are longitudinally fixed relatively to the helium vessels.
Thermal contraction of the cable is covered form the entry in the DFHx1. The helium vessels contractions is covered on SCLink side by bellows, on current leads side by current leads internal bellows.
The geometry allow to individually control each mass flow around splices.
← to DFHx2

## Slide 13: Sequence proposal
Operation:
A gaseous helium mass flow up to 10 g.s-1 enters the DFHx. The flow is separated for allowing individual splice, current leads cooling.
Leads are routed and fixed inside the helium vessel and longitudinally fixed at the splice level.
Helium vessel fixed point
Connection to ground to design
Connection to ground to design
Vacuum bellows rigid fix.
DN100 relief plate on vacuum volume
Port for pumping interfaces
PT
Bellows He-VV vessels
Bellows He vessels
DFHx1-SCLink
Bellows VV vessels
DFHx1-SCLink
Helium vessel
Vacuum vessel
G10 guiding supports
Splices with Peek bi-lateral fixation to pipe
Safety relief device covering DFHx + SCLink helium volumes
Current leads flexible
Current leads flexible
To DFHx2 
Mass flow indiv. controlled
Safety relief devices
+18 kA
-18 kA
+13 kA
-13 kA
He. Vessel instrum.
T-sensors
V-taps
VV instrum.
TS instrum.
Note: thermal shield not shown
≈Ø 1.5m
≈ 2.8 m

## Slide 14: DFHx design proposal
Interlink  to DFHx2
Current
leads
SCLink
DFHx1
Safety relief device
Gaseous He
Insulation vacuum
Fixed point
Flex. Point
Passive TS
HTS
MgB2
NbTi
Warm cable
Splice
PT
PT
PT
Ω
Ω
Integration & interfaces layout
DFH in series between SCLink and current leads
Envelope: ≈Ø1.5m x 4m on rails
Electrical layout
MgB2 – HTS – Current leads
Cryogenic layout
1 common helium volume
Heat extracted through convective heat transfer
Safety relief devices
Leads interface
Instrumentation
Interface
Insulation Vacuum layout
Vacuum barrier at SCLink-DFHx interface
Mechanical layout
Splices fixed to helium vessel
Flexible structures for thermal contractions and installation

## Slide 15: Proposed conceptual installed configuration
Guidelines for the assembly:
  MgB2 cable protected at all times
  MgB2-HTS splices fixed to He vessel
  Orientate angularly the MgB2 leads to the corresponding HTS leads
DSHx
2 x 18 kA
2 x 13 kA
3 x 7 kA
12 x 2 kA
DFHx1
DFHx2
Superfluid @ 1.9K
Liquid He @ 4.5 K
Gaseous He
Heater
Vacuum barrier
HTS
MgB2
NbTi
Warm cable
Splice
DFHx layout for analysis
DFHx 3D pre-design for illustration

## Slide 16: Proposal installation sequence
DFHx1
DFHx2
DFHx1
DFHx2
Protected MgB2 ends
MgB2 cables in flexibles
Cable opening in rigid structure
SCLink end preparation for SM18 test
  He vessels pre-mounted once for all before SM18 test
  Only MGB2 ends (temporary protected are visible)
  Only final welds around splices will be further performed
SM18 test installation (DFH proto)
  90% of He vessels are done
  Insertion DFHx1 VV
  Insertion of Interlink
  Insertion of DFHx2
  Opening of flexibles + angular orientation
  Splicing + Current leads
Transport configuration
  Procedure backward
  2 x 1m rigid section
SCLink installation (same as SM18)

## Slide 17: Key influencing parameters
The pre-opening of the MgB2 cables directly influences:
  The rigid boxes 10m distant to be installed in the turret for transport
  The SCLink vacuum jacket interface flange diameter
  The openings in the vacuum vessels
     increase radial distance to splices  length of DFH due to bending radius of MgB2
  The interlink vacuum jacket ID (could use it for waving only inner pipe)
Today orders of magnitudes:
  DFHx length ≈ 4m (bending radius 1.5m)
  DFHx Vacuum vessels OD ≈ up to 1.5m
  Interlink OD ≈ 400mm
DSHx
2 x 18 kA
2 x 13 kA
3 x 7 kA
12 x 2 kA
DFHx1
DFHx2
Superfluid @ 1.9K
Liquid He @ 4.5 K
Gaseous He
Heater
Vacuum barrier
HTS
MgB2
NbTi
Warm cable
Splice
DFHx layout for analysis
DFHx 3D pre-design for illustration
Ø
Ø
10 m
Ø
Ø

## Slide 18: Needs to cool/maintain a 18kA-splice temperature within spec.
3kA splices
Flowing areas
Preliminary early design MgB2-HTS
Chart: Splice temperature for various gaseous temperatures and splice resistances
| 0.25 | 0.5 | 1 | 2.5 | 5 | 7.5 | 10
The=10K, R=10nO | 10.9231 | 10.5294 | 10.3051 | 10.1463 | 10.0841 | 10.0607 | 10.0482
The=10K, R=25nO | 12.3077 | 11.3235 | 10.7627 | 10.3659 | 10.2103 | 10.1519 | 10.1205
The=10K, R=50nO | 14.6154 | 12.6471 | 11.5254 | 10.7317 | 10.4206 | 10.3037 | 10.2411
The=10K, R=100nO | 19.2308 | 15.2941 | 13.0508 | 11.4634 | 10.8411 | 10.6074 | 10.4821
The=15K, R=10nO | 15.8896 | 15.5094 | 15.2935 | 15.141 | 15.081 | 15.0585 | 15.0466
The=15K, R=25nO | 17.2241 | 16.2736 | 15.7337 | 15.3525 | 15.2024 | 15.1463 | 15.1164
The=15K, R=50nO | 19.4481 | 17.5472 | 16.4674 | 15.705 | 15.4048 | 15.2925 | 15.2328
The=15K, R=100nO | 23.8962 | 20.0943 | 17.9348 | 16.4099 | 15.8096 | 15.585 | 15.4655
The=20K, R=10nO | 20.864 | 20.4954 | 20.2857 | 20.1371 | 20.0787 | 20.0569 | 20.0454
The=20K, R=25nO | 22.16 | 21.2385 | 20.7143 | 20.3426 | 20.1968 | 20.1423 | 20.1134
The=20K, R=50nO | 24.32 | 22.4771 | 21.4286 | 20.6853 | 20.3936 | 20.2845 | 20.2269
The=20K, R=100nO | 28.64 | 24.9541 | 22.8571 | 21.3706 | 20.7872 | 20.569 | 20.4538
Current leads requirement range
LHC 13kA current leads mass flow
for:
R18kA=17nΩ (R3Ka=100nΩ)
TGHE=20K
SPLICE PROPERTIES | Unit | Value
Splice length | [mm] | 220
Flowing area Equivalent diameter | [-] [mm] | 6 x ½ DN10 + central DN10 DN20
Deq | [mm] | 20
Heat transfer area | [mm2] | 27600
Dissipated power Current 3kA Resistance | [W] [kA] [nΩ] | From 0 to 5 W 6 X 3 From 10 to 100
Exercise with (very) preliminary design of 18kA splice
Various configurations:
  3 gas temperatures: 10, 15 & 20 K
  4 splice resistances :
    R3kA=10, 25, 50 & 100 nΩ
    Corresponds to
    R18kA=1.5, 4.2, 8.3, 16.7 nΩ
  Constants : I=18 kA, P=1.1 bara
Observations:
  The helium gas temperature has limited influence on the ∆T between gas and splice surface
   TGHE has direct influence on Tsplice
  For low , high TGHE and very high R18kA , the splice temperature remains below 25K.
   The splice will very most likely never need higher mass flow than current leads
  = the current lead mass flow is limited to CL needs
  (for HTS flexible < 15m)
Note: Tbottom CL increases by 0.5 K @ 0.5g/s mass flow per meter of HTS flexible length
Ex: Lflexible HTS= 5 m,
 Tbottom CL =Tc+3 K
Pc, Tc

## Slide 19: Hydraulic studies for parallel flow options
Exercise with DFHx1 and 18kA splice preliminary design: 4 x 18kA splice + 1 path for DFHx2 leads
Observations:
  Most of the flow goes to the biggest Deq circuit
      ≈20% to the 4 splices (5% each) , ≈80% to central outer circuits
   Install upstream orifices for similar parallel mass flows (common practice)
      Order of magnitude : Ø10 mm  Integration of upstream orifices unreliable around MgB2 cables (various Ø, Kapton, solder geometry)
What if:
   A limited diffirence between parallel circuits implies high mass flows unbalance (higher R, Kapton, solder)
      One splice sub-hole is blocked  Atr reduced by 15%  Q reduced by 15%: Non critical
      One splice is warmer  ∆P increase  local mass flow decreases further
      One splice needs twice more heat extraction  total mass flow +150%
      Support and flowing areas obstructions not perfect  mis balance between hydraulic parallel circuits
Chart: Repartition of mass flows in DFHx1 depending on total mass flow
| 2.0539650594377608 | 7.6162870619649912 | 11.30020811554928 | 14.233715249025927 | 16.766214372162622 | 19.036981455267 | 21.118837779240021 | 23.055687508648528 | 24.876484024958 | 26.601544965462605 | 28.245795282119534 | 29.82059082095677 | 31.334816201353071 | 32.795582080814327 | 34.208687471918267 | 35.578937346544478 | 36.910367413928306 | 38.206407283711407 | 39.470001517950649 | 40.703701165257691 | 41.90973414209526
Mass flow per 18kA splice | 0.12223 | 0.44368 | 0.65405 | 0.82074 | 0.96418 | 1.0925 | 1.2099 | 1.319 | 1.4214 | 1.5183 | 1.6105 | 1.6988 | 1.7836 | 1.8654 | 1.9444 | 2.021 | 2.0953 | 2.1677 | 2.2382 | 2.307 | 2.3742
Mass flow per DN40 | 0.78253 | 2.9208 | 4.342 | 5.4754 | 6.4547 | 7.3335 | 8.1396 | 8.8899 | 9.5955 | 10.2643 | 10.9019 | 11.5127 | 12.1002 | 12.6671 | 13.2156 | 13.7475 | 14.2645 | 14.7679 | 15.2587 | 15.7379 | 16.2065
central flowing area :
DN40 38% of total flow
18kA flowing area :
DN20 5% total flow
Ext flowing area :
DN40, 38% of total flow
To CL
To CL
To DFHx2
To CL
To CL
0.5 g/s around one splice  total 7 g/s
1.0 g/s around one splice  total 17 g/s

## Slide 20
How to match angularly MgB2 and HTS cables ?
Starting data :
Bending radius : 1000 mm
Interlink diameter : 250 mm
MgB2 opening in surface
Rotation in helium tank
(MgB2 cables)
+500 mm length or +200 mm diameter for
Helium tank
DFH
MgB2 cables (+500 mm length in any case)
Need to close Helium tank in UR
In DFHx1, manipulation problem for other cables (depend of layout)
Only very local guide for cables
How to be sure to not rotate the cable in the link ?
MgB2 manipulation in situ
Complicated manipulation due to bad access
Rotation with internal flexibles (MgB2 cables)
+1000 mm length for
DFH
MgB2 cables
Instrumentation and safety flexible will be also rotated
Cables are protected during rotation
Rotation with external flexibles (HTS cables)
+ 4000 mm length for
HTS cables
No impact on DFH enclosure
Need to have a rotatable output flange
Cables are protected during rotation
Possible impact on integration
Illustration – rotation 0°
Illustration – rotation 180°
Illustration – rotation 180°
Illustration – rotation 0°
Illustration – rotation 180°

## Slide 21
Main points to be confirmed to develop final design