## Slide 1: Budget, Resources & Planning
Gerard Tranquille

## Slide 2: Budget
2.427 MCHF was allocated to this project in 2015.
Some money has already been spent, mainly on preparing the test stand (bld 236).
Job opened with EN/MME to initiate integration studies. Will continue for the collector……..
Spending profile in APT |  |  |  |  | 
≤2018 | 2019 | 2020 | 2021 | 2022 | 
118 kCHF | 50 kCHF | 400 kCHF | 1200 kCHF | 659 kCHF | actual
130 kCHF | 100 kCHF | 500 kCHF | 1200 kCHF | 497 kCHF | updated

## Slide 3
Total budget : 2.427 MCHF |  | 
Design, drawings | 250 kCHF | >4500 hours
Magnetic system | 1000 kCHF | Incl. spare coils
Raw materials & production | 750 kCHF | Vacuum chambers, BPM…..
Vacuum | 50 kCHF | NEG (coating,strips), acceptance tests
HT platform | 100 kCHF | 
Cabling | 50 kCHF | 
Misc. | 227 kCHF | 

## Slide 4: Resources
We would like to build the new cooler in the same way that the ELENA electron cooler was made:
  Magnetic system -> industry
  Gun, collector, vacuum elements… -> in-house
BI-EA has >35 years experience in designing, building, commissioning and operating electron coolers.
  One electro-mechanical technician
  One electronics technical engineer
  Two applied physicists
  …………
Requested from other sections/groups:
BE/BI/BP: BPM
EN/MME: Design, production drawings
TE/VSC: Specification of vacuum system, NEG coating, acceptance testing
TE/MSC: Specification of magnetic system, magnetic measurements

## Slide 5: Tentative Planning
2019: Design of new collector. Produce drawings. Start production (main workshop availability?). GT,JC,EN-MME
Specification of the magnetic system. Produce tender documents. Market survey (?). GT,LJ,TE-MSC,CERN-FI
Finish integration study (incl. magnets reshuffle). Ecool & AD teams,EN-MME
Finalise gun study and design. AP,AR,GT,EN-MME
2020: Call for tender for the magnetic system. FC(?)
Production of the new collector (ready for autumn). Main workshop
Produce drawings for the electron gun. Start production (?). EN-MME
Design of the vacuum system. Drawings ready for end of year. Ecool team,EN-MME,TE-VSC
Test new collector on ecool test stand. Ecool team
2021: Install new collector on AD. Exchange electron gun. Ready for start-up. Ecool team,TE-VSC
Magnets production. Follow-up with TE-MSC
Production of the vacuum system. Chamber coating. Acceptance tests. TE-VSC
2022: Continue production and acceptance tests/measurements of magnets and vacuum system. TE-MSC & VSC
Mounting in bld 236 (ecool test stand)
2023: First tests of the new cooler.

## Slide 6: Installation & commissioning
The new AD electron cooler could be ready for installation during the 2023/2024 shutdown.
Depends on how much can be done in preceding shutdowns (21/22, 22/23):
  Install HT platform & cable pulling
  Reshuffle ring magnets
If not we will have to wait until LS3 for the complete installation of the cooler and the modifications to the AD ring.
Commissioning:
  run the new cooler with the present AD cycle i.e. cooling @ 300 MeV/c and 100 Me/c
  during dedicated MD time insert the 500 MeV/c plateau and perform the cooler commissioning