## Slide 1: RWTCS and bldg 573 C. Colloca
RWTCS Steering Commitee

## Slide 2
BLDG. 573 Layout

## Slide 3
BLDG. 573 Cost

## Slide 4: Work progress vs. expenditures
RWTCS Steering Commitee

## Slide 5
WORK PACKAGES | WORK PACKAGE OWNER | WORK PACKAGE TEAM
Civil engineering & building work | C. Colloca SMB/SE | L. Maricalva, R. Ortega, Draughtsmen SMB/SE
Electricity | J. Gomez SMB/SE | F. Vincent SMB/SE
HVAC | G. Rouge SMB/SE | L. Fertin SMB/SE
Cranes & handling/lifting equipment | ? EN/HE | Y. Seraphin EN/HE
IT networks | L. Borakiewicz IT/CS | 
Access control | R. Nunes BE/ICS | N. Rama BE/ICS
Fire detection | D. Raffourt BE/ICS | P. Thome BE/ICS
INFRASTRUCTURE WORK

## Slide 6: - Retention basin waterproofing ISR2 entrance - Rails repairs & replacement ISR2 - TT1 Shaft (empting) + last floor slab sealing - IT network - Fire wall ISR2-ISR3 - Fire detection installation ISR2 - HVAC installation ISR2 and ISR1 (CMS side) - Phase 1 of civil eng. foundation for HVAC surface (sector ISR1-2) - fast opening doors installation - new meeting room bldg. 184
FINISHED WORK (OCT 18 – MAR 19)
ISR2 sector…finished!

## Slide 7
Bldg. 574: - separation wall & door
floor resin
class C cell
electrical installation
envelope repairs
95% HVAC installation (filter missing)
table for cupboard
racks
FINISHED WORK (OCT 18 – MAR 19)

## Slide 8
Bldg. 573: - old SAS demolition
all technical installation dismantling
floor decontamination & repairs
concrete retention basin
shock protection metallic system
painting
FINISHED WORK (OCT 18 – MAR 19)

## Slide 9: RWTCS: - DO for motorized fire door IRS2/ISR3 - fire manual doors ISR2 - green space cleaning for HVAC surface BLDG 573 (1 month) : - retention basin for evaporators - resins - electrical installation - HVAC installation - doors (new and replacements) - roof replacement - waterproofing barrier - fire detection
On going/starting WORK

## Slide 10: RWTCS: - phase 2-5 civil eng. for foundation HVAC surface (ISR3-ISR7) - DO preparation for 10 bldgs for HVAC surface - estimate for DI, IT & elec for HVAC surface BLDG 573: - fire protection wall evaporators BLDG 225: - input from BE/ICS for predesign of sprinkler system
On going/starting STUDIES

## Slide 11
BUDGET - SPENDING PROFILE
HVAC
2019 : 1200 kCHF
2020: 500 kCHF
Possible reports to 2020 (160 kCHF)
- Masonry & fire walls parallel galeries
- Sealing work (walls)
- 4 ducts dismantling in ISR4
- Ventilation unit dismantling ISR2 (entrance)
New estimate for surface work for HVAC (685kCHF)
PHASE 1 : 70 kCHF + 40 kCHF
PHASE 2 : 135 kCHF + 40 kCHF
PHASE 3: 135 kCHF + 40 kCHF
PHASE 4 : 70 kCHF + 40 kCHF
PHASE 5 : 75 kCHF + 40 kCHF

## Slide 12
SPENDING PROFILE
EXPENDITURES (FOR TUNNEL WORK ONLY – NO SECURITY) | 2019 | 2020 | 2021 | 2022 | 2023
GLOBAL BUDGET* (kCHF) | 2’400 | 1’070 | 390 | 340 | 45
TOTAL | 4’245 |  |  |  | 
*Without ‘Access control’, ‘Human resources’
Includes:
New estimate for dry risers (incl. civil eng. 2020)
New estimate fire door ISR2 + motorised fire door ISR2/ISR3
Fast opening doors (2019)
New estimate of civil eng. Works and services (DI+elec.+ IT) for HVAC
Planning v 64

## Slide 13
TO BE FIXED
Reports to 2020
Surface work for HVAC -> IT ?
PHASE 2, PHASE 3, PHASE 4, PHASE 5 = 415 kCHF
Roof (‘toles’) replacement bldg. 573 = 20 kCHF
Fire wall between ISR1 and ISR2 -> needed ?
Fire door ISR2 (+pedestrian fire door IS2/ISR3) = 62 kCHF
Contribution/collaboration with HSE-OHS : - anticipation / suggestions (active presence) of HSE CO - re-set (or respect) SLA - clarify MSI (yes or no, and where)

## Slide 14
SPENDING PROFILE
EXPENDITURES (FOR TUNNEL WORK ONLY – NO SECURITY) | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
GLOBAL BUDGET* (kCHF) | 890 | 2’750 | 500 | 260 | 300 | 45
TOTAL | 4’745 |  |  |  |  | 
*Without ‘Access control’, ‘Human resources’
Includes:
New estimate for dry raisers
Finalization of civil eng. works for HVAC
Floor reparation included (out of the waterproofing)
Planning v 62