## Slide 1: Session 3 – Commissioning: Outcome and next steps
A. Huschauer, V. Kain
Special LIU Executive Committee Meeting, 5 March 2019

## Slide 2
IST, HW commissioning and cold check out
  Elaborate detailed planning of the different activities by December 2019
    Detailed resource-loaded planning with identification of cross-machine interdependencies
    Clear identification/definition of ISTs and their interdependencies/links with HWC and prerequisites
    Resources: preparation (including software) and execution of hardware commissioning
  Activities in the Switchyard (multiple openings/closures)
    Elaborate a final schedule by August 2019
    Last LIU-CCC meeting dedicated to discussing this point
    Follow-up at the end of March once feedback from all groups has been received
    Final planning depends on delivery of POPS capacitors (to be discussed at the Finance Committee in June)
  Improved check-list tool
    next version required by August 2019

## Slide 3
Christmas shutdown 2020
  Identify critical items and elaborate strategy to ensure rapid start-up in January 2021
    First proposal by December 2019
    Will need continuous attention during beam commissioning end of 2020
Beam commissioning
  Elaborate the injector schedule 2020/2021 by December 2019
    Based on the already well advanced schedules presented at the workshop
    Including start-up dates for all FT physics facilities
  Detailed resource-loaded planning to follow early 2020
    In collaboration with the equipment groups:
      Define necessity for expert shifts and/or piquet services
      Identify cross-machine interdependencies
Integration of LIU systems
  Next round of system integration discussion and feedback to working groups
    Sufficient discussion with equipment groups everywhere?
  To be worked out and put in place until August 2019

## Slide 4
Improved operational efficiency
  Towards a beam rather than machine centric operation of the complex
  Develop proposal for performance tracking and online analysis across the injector complex: December of 2019
    Close collaboration between BE/CO, BE/OP, BE/ABP, TE/ABT,… required
    Considering beams for the LHC and the FT facilities
    Definition of observables to be tracked / tools to be used / framework to be applied
  Injector Settings Management WG
    tighter follow-up of activities and re-discussion of reporting
  Sequence and cycle management to be followed-up with BE/CO as of early 2020
  Software and tools development
    Identify appropriate approach depending on problem at hand (multi-parameter optimisation tools, automated procedures, machine learning algorithms, …)
    Establish a team of experts – August 2019

## Slide 5
Prioritization of RF work load: topic for discussion
  Review prioritization of longitudinal painting
    To be discussed at the level of the LIU Executive Committee?
Decide on involving EN/ACE for hardware commissioning planning
  Also use their tools?

## Slide 6: Summary table
Activity | Deadline | Remarks
Switchyard activity planning | August 2019 | Next discussion scheduled for end March 2019
Improved check-list tool | August 2019 | 
Requirements for integration of LIU systems | August 2019 | Potentially dedicated meetings with groups
Team of experts for software and tools development | August 2019 | 
Detailed IST, HWC, cold check out planning | December 2019 | 
Performance tracking | December 2019 | Proposal
Elaborate 2020/2021 injector schedule | December 2019 | 
Christmas shutdown planning | December 2019 | Proposal
Detailed beam commissioning planning | early 2020 | 
Follow-up of timing system renovation | early 2020 |