## Slide 1: Upgrade ex-LEP Refrigerator for HL-LHC @ P4 F723/TE/HL-LHC WP-12_HSE Project HSE Activities
E. Monneret / TE-CRG-ME
CERN HL-LHC 5th March 2019 EDMS #XXXXX

## Slide 2: CONTENT
Overview
Scope of Work
Schedule and Main Milestones
H.S.E. activities

## Slide 3: Upgrade Overview
LHC
Overview
HL-LHC project require additional overall cryogenic capacity
LHC Point 4 (P4) feature is an additional heat load coming from existing superconducting RF cavities
HL-LHC Baseline & Studies
2015 – HL-LHC Baseline
  A new refrigerator for a budget of ~11MCHF
2016 – Alternative study 1
  An upgrade of the LHC refrigerator and the distribution for a budget of ~9MCHF
2017 – Alternative study 2
An upgrade of the ex-LEP refrigerator without modification of the distribution
The sector 3-4 fed by the ex-LEP refrigerator becomes the weakest point of LHC for the production of cryogenic refrigeration power
2018 – Contract with Linde KT for the Upgrade – +2kW@4.5K (+14% capacity) @ Budget ~3.8MCHF

## Slide 4: Upgrade Requirements
How to provide +2kW@4.5K for LHCA @P4
  No modification of the compressor station QSCA
  No modification of the CB’s heat exchangers
  No modification of the cryodistribution
  Replacement of 7 turbines (new Linde model – TED)
  Modification of 1 existing turbine
When it is required
  Capacity for LS3 but to smooth CRG workload and minimize risk to be done during LS2

## Slide 5: Upgrade Scope
Principle of the capacity upgrade: to replace 8 turbines by new type (more efficient)
This requires exchange of turbine housings & instrumentation
Upper CB: 4 TU’s
Lower CB: 4 TU’s
Surface
Shaft
Cavern
Cut view of existing cold box
New turbine housings and instrumentation
Spares and repairs: to ensure availability as all helium refrigerators
Linde Kryotechnik, original designer and supplier in 90’s.
Upgrade late in 90’s (WCS)
CB’s upgrade in 2005.

## Slide 6: Team Organization

## Slide 7: Schedule - Milestones
Project Phases
  Design Q1/Q2 2019
  Manufacturing Q2/Q3 2019
  Installation Q4 2019
  Commissioning Q2 2020
Next Milestones
  Preliminary Design Review (PDR) & turbines MRR – mid March 2019
  CB’s Helium leak test & Internal inspection @CERN LHC-P4 – early April 2019

## Slide 8: HSE (Safety) Activities
Pressure Equipment
  Mechanical design
    New Equipment: According to PED and relatives standards integrated in original (~25 years old) equipment
    Contractor (LKT) will design, manufacture and test the new equipment in accordance to regulation
    Contractor will not be responsible for the global equipment (after integration in existing CBs)
    Directive and Norm: PED and ISO/EN norms (piping, vessels,…)
  CERN will have to make the overall validation
    What is required during design / Manufacturing-Installation / Test / Operation / Maintenance / Decommissioning ?
  Pressure test (1,25 vs 1,43) ?

## Slide 9: HSE (Safety) Activities
Ex. Upper Cold Box
  Change all turbines
  Modification of piping to re-use a valve (5HV219) – Add a “close” volume (use existing SV)

## Slide 10: HSE (Safety) Activities
Other activities
  Electrical design (in charge of CERN if any)
  Instrumentation (LKT only provide instrument)
  Control & Interlocks (implemented by CERN)

## Slide 11: HSE (Health) Activities
Job identified as of today
  Welding, gridding
  Working in confine space
  Working with Pressure gas (N2, Ar, He)
  Working with MLI (Multi layer insulation)
  Transport of Load (~200kg) / opening of cold box (~1 ton flange)
Specific procedure and adequate personal protection will be used + CERN required training

## Slide 12: HSE (Health) Activities
Confined space activities – Upper cold box
H. Recommendation?
Ø600 Manhole
Full CB diameter flange
But limiting opening (~10cm)
~Ø200 Flange on opposite side (Vacuum pump port)

## Slide 13: HSE (Health) Activities
Confined space activities – Lower cold box
H. Recommendation?
Ø2000 Flange to be dismounted
~Ø2000 Flange to be dismounted

## Slide 14: HSE (Environmental) Activities
Dismounting activities – Recycling
  CERN Tech Spec. Req.: “List of dismounting equipment with the recycling option”, e.g:
    Stainless steel piping, cables, instruments
    Pressure vessels (HX turbines)
  Do we need to trace the material?
Limited pollution (?) / No oil, no adsorbant, etc.
Radiation (?) – in the cavern

## Slide 15: Summary
An introduction to the Upgrade project of the refrigerator at LHC-P4
Pressure equipment design and test
Health actions for workers

## Slide 16: Thanks for you attention Let’s start the project