## Slide 1: International Review on the High-Order (HO) Correctors and the D2 Orbit Corrector dipoles for the HL-LHC: Review Committee Report
Review Committee Members Bernhard Auchmann (PSI/CERN), Stefania Farinon (INFN), Helene Felice (CEA), Davide Tommasini (CERN), and Akira Yamamoto (KEK-CERN, Chair)
Link Person: Ezio Todesco (CERN)
Dates: 18 - 19 December, 2018

## Slide 2: Introduction
HL-LHC is in the final stage of design and prototyping: all technologies for the hardware upgrade must be fully proven by the beginning of 2019. This review covers the High Order (HO) Corrector Magnets assembled with the inner triplet system and the D2 Orbit Corrector Magnets assembled with the D2 magnets. These correctors using NbTi superconductor feature respectively a Super-Ferric (SF) design and a Canted Cosine-Theta (CCT) design.
Both types of corrector magnets are in the stage of full-size prototype testing and preparing for series productions. The HO correctors have been designed and prototyped by INFN-LASA (Milan), which is also responsible for the series-production in cooperation with industry. The D2 corrector has been designed and prototyped by CERN, and further prototype work and series-production are to be taken on by IHEP (Beijing) in cooperation with IMP and WST in China, based on the technology transfer coordinated between CERN and IHEP.

## Slide 3: High-Order (HO) Correctors

## Slide 4: D2 Correctors with CCT design

## Slide 5: Charges for the Review Committee
The review committee is invited to assess the points in the scope and in particular, the design, the results of the prototyping phase and the procurement plan, including interface aspects for the system integration.
A detailed analysis of the time plan for the series construction and for the resources is beyond the scope of the review; however, comments on the credibility of the present plan, also with respect to the foreseen available resources, are welcome.
The project is a joint venture between CERN and INFN (for the HO Correctors) and CERN and IHEP-CN for the CCT. The committee is invited to comment on the sharing of the responsibility and on the collaboration interfaces.
Following the close-out by the review chair, the committee is required to compile a short report with findings, comments and recommendations within one month. The report will be delivered to the HL-LHC Project Leader, which will circulate also to the collaborating Institutes and CERN management.

## Slide 6: Charges for the Committee, summarized
assess the design, the results of the prototyping phase, and the procurement plan,
comment on the credibility of the present (time) plan, and
comment on the sharing of the responsibility and on the collaboration interfaces.

## Slide 7: Review Agenda
Time | Subject | Presented by
18 Dec. |  | 
8:8:30 | Closed session | Committee et al.
9:00 | Scope and structure of the review | Lucio Rossi
9:15 | D2 corrector requirements | Ezio Todesco
9:35 | MCBRD (CCT) Assembly and Cold Test | Glyn Kirby et al.
10:10 | Group picture and Coffee break | 
10:30 | Integration in the cold mass | Arnaud Pascal Foussat
10:50 | Short model performance and prototype/series plan in China | Qingjin Xu et al.
11:35 | Documentation and QC/QA | Andrea Musso
11:55 | Closed session | Committee et al.
12:20 | Lunch | 
 | High Order Correctors requirements | Ezio Todesco
13:20 | Magnet design and prototypes performance | Marco Stefera
13:40 | Integration in the cold mass | Herve Prin
14:10 | Plans for the series | Massimo Leone Sorbi
14:35 | Document and QA/QC | Andrea Musso
15:00 | Coffee break | 
15:20 | Closed discussions on: Special focus on: Training of MCBRD prototype Special focus on: Quench protection of the MCBRD | Committee et al Franco Julio Mangiarotti Matthias Mentink
19 Dec. |  | 
9:30 | Closed session Special focus on: Magnetic modelling of MCBRD | Committee et al. Jeroen Van Nugteren
D2 corrector
HO corrector

## Slide 8: Executive Summary -- General
An International Review on the HL-LHC interaction region corrector magnets was held at CERN on 18 - 19 Dec. 2018, with two major topics: High-Order (HO) Correctors, and D2 Orbit Corrector dipoles. The Committee has received eleven reports in open sessions and three specific reports in closed sessions.
The Committee congratulates the team for the significant progress in the corrector magnet model/prototype works in cooperation with INFN-LASA for the HO correctors and with IHEP/IMP/WST for the D2 correctors.
The Committee wishes to thank the HL-LHC WP3 team for their considerable effort to prepare for the review and for fruitful discussions.

## Slide 9: Executive Summary: Findings and Comments (1/2)
The HO corrector concept with the super-ferric magnet technology has been well demonstrated during the model/prototype work. A remaining concern is the series production schedule, which should be re-optimized to minimize the delay. Although INFN is responsible for following up the production, CERN should provide robust oversight.
The D2 corrector concept with the CCT magnet technology has been clearly demonstrated during the model/prototype work. Three technical issues are, however, remaining to be settled to:
  Minimize/control training quenches,
  Optimize the quench protection scheme with the full-scale magnet, and
  Improve/justify the field quality, in particular, for b3.

## Slide 10: Executive Summary: Findings and Comments (2/2)
A 3rd D2 corrector full-scale prototype coil to be built at CERN is required to demonstrate the mitigation of the above issues. It is encouraged to improve instrumentation, in particular, for more precise understanding of the training quench origins.
  The results of the 3rd D2 prototype at CERN will provide a solid basis for the technology transfer to IHEP, and it needs to be completed in timely manner.
The committee notes that a rapid and significant R&D effort for the D2 corrector has already been accomplished in collaboration of IHEP-IMP-WST in China, in parallel to the formal collaboration agreement established.

## Slide 11: Recommendations
For HO-Correctors:
Improve the series production plan to meet the requirement from the general HL-LHC construction schedule in close communication between CERN and INFN-LASA.
For D2-Correctors:
Understand and mitigate the CCT magnet training-quenches currently starting at a much lower level along the load-line and behaving very differently in the two prototype apertures of the full-scale prototypes. It is advised to inspect the cross section cut out from the prototype coils, after confirming the training quench memory stabilized after the thermal cycle.
Demonstrate the base-line performance with the 3rd prototype coil to establish the solutions for the three remaining issues.
  Note that, due to scheduling reasons, a correction of the b3 is only advised, if necessary, according to beam-dynamics studies.
Provide a design report for the D2 corrector with the CCT technology, to enable efficient technology transfer from CERN to IHEP in cooperation with IMP and WST, responsible for the prototype demonstration and the series production

## Slide 12: Responses to further details
See the full review report submitted in end Jan., 2019
Some hot issues are focused in next pages.

## Slide 13: A post-review report: Training test result of the HO Skew Quadrupole Corrector Prototype
The skew quadrupole corrector (last prototype of high order correctors) was tested in LASA. The magnet has a long training reaching nominal after 14 quenches (see plot).
Unfortunately, during the 15th quench, an electrical problem occurred, and now the system presents a few ohm resistance.
The system shall be opened in order to investigate in the magnet and in the test station the cause of the problem.
We will inform you about the outcome of the analysis as soon as possible.
-- Reported by E. Todesco, on 22 Feb.
Note: Further investigation and effort for the mitigation required for realizing the magnet production.
Courtesy: E. Todesco

## Slide 14: A post-review report: Comments on the CCT magnet training quench memory after a thermal-cycling
Observation:
Very good training-quench memory of the CCT magnet observed after a full thermal cycling,
Note:
Physical observation encouraged to check the epoxy-resin bonding at the CCT groove after the thermal cycling
The best approach/justification to be established for the 3rd prototype and the production magnets.
Courtesy: E. Todesco

## Slide 15: Many thanks for everyone involved !!