## Slide 1: Schedule and Coordination of the technical stop
January 12th 2010
K. Foraz

## Slide 2: Aim of this technical stop
Repairs the nQPS connectors
Perform all activities needed for 6kA
Commission machine for 6kA

## Slide 3: Baseline schedule

## Slide 4: Organization
From electrical lock out ph1 to unlock out
User
MEF
HCC
1. Request
2. Check
3. Check
& Implement
Edit ADI’s
4. Inform
& coordinate

## Slide 5: MEF-LPC Website

## Slide 6: List of activities
Is presented at each meeting
nQPS Connectors, incl. work preparation, repairs, quality, ELQA
Non conformities solving
  Electrical activities – Non conformities solving
      Still TBC Cable change in PM45
  Collimation: TDI – waiting from test results
  Cooling and Ventilation
  Kickers: AGK , IPOC hardware, OASIS, LVDT, PFN…
  BLM & BPM repairs
  Power converters
  Cryogenics: DFB’s filters, NC on CV891, valves, tunnel instr., cold compressors….
  ODH (minors:panels…)

## Slide 7: List of activities
Maintenance & Inspection
  Lift maintenances
  Cooling and Ventilation
  Power converters
  ODH
  Access system
Others
  Safety signalization for the cryo valves
  TZ76 dampers
  Radmon collimation
  TIM tests
  TOTEM – request a 3rd week
  Survey Low-Beta
  Commissioning of the tomograph
  Protection of 600A current leads

## Slide 8: nQPS status
  Tableau JCG

## Slide 9: Other activities progress
Electrical activities – Non conformities solving On schedule
Lift maintenances done
Safety signalization for the cryo valves finished tomorrow
TZ76 dampers will be finished this week
Collimation Pt 3 & pt7 in progress
    Tests have been done on TDI, waiting for action/no action
TIM tests in progress
Ventilation: control &/ repairs in progress
TOTEM in progress (requesting a 3rd week)
Survey Low-Beta in progress (60%)
Kickers activities in progress
BLM consolidation in progress
TE-EPC intervention in progress
Cryogenic consolidation in progress (65% done)
Commissioning of the tomograph this week
Protection of 600A current leads done
ODH
Access system maintenance in progress
All activities on schedule
No show stopper

## Slide 10: Updated schedule

## Slide 11: Patrols (forecast @ Jan. 12)
Jan. 12th : Arc 81
Jan. 13een: Arc 12
Jan. 15een: Arc 23
Jan. 19een: Arc 34 + Point 1 + Point 2
Jan. 20th: Arc 45
Jan. 22nd: Arc 56 + Point 3 + Point 4 + Point 5
Jan. 26th: Arc 67
Jan. 27th: Arc 78 + Point 8
Jan. 28th: Point 6
Feb. 1st: Point 7