## Slide 1: Status of QPS – January 2010
R. Denz TE-MPE-CP

## Slide 2: Status of QPS – general issues
Besides nQPS commissioning all QPS and EE systems have to be prepared for the 2010 LHC run
  Most of the work expected to be transparent to planning
  Involves basically the QPS core team
  Very few hardware interventions (exchange of broken items)
  Protection system firmware upgrades (requires as well LHC access)
    nQPS, 600 A, IPD,IPQ & IT
  QPS-IST for LHC main circuits
  QPS supervision upgrade (EN-ICE and BE-CO)

## Slide 3: Status of QPS – supervision
RBAC enabled in strict mode for QPS and EE systems since last week
  Successfully tested for QPS supervision and QPS specialist tools (JAVA and LV based)
    Some specialist tools still to be updated
  Access much more restricted than in 2010
  Access to specialist tools only if really needed and after proper training
Macros and new tools
  Macros for closing switches, resetting 600 A systems and calibration of nQPS currently under test in close collaboration with EN-ICE
  New tools facilitating specialists tasks under development
    E.g. DQQDS diagnostic tool etc.

## Slide 4: Status of QPS – piquet service
QPS piquet service in preparation
  QPS piquet team incorporating QPS experts and additional support from other MPE sections (in total about 8 people)
    Membership still to be defined and approved
  Piquet task list:
    Exchange of damaged QPS and EE hardware
    Restart of QPS and EE systems
    Link to expert in case of more serious problems
      Note: very limited number of experts on best effort basis
      Number of experts can hopefully be increased during 2010
    ...
  Piquet infrastructure as well to be prepared
    Phone number, cars, bicycles, tools ...
  Piquet service supposed to be operational mid of February for beam commissioning and LHC operation (mandatory!)

## Slide 5: Status of QPS – documentation, spares and reference systems
Documentation
  QPS documentation including nQPS for users, operators and experts to be prepared and updated
    Existing documentation partly obsolete
    nQPS documentation including test procedures not yet complete
  Write-ups for standard procedures (e.g. exchange of a quench heater power supply)
  Special documentation and presentations for training
Spares
  Critical situation end of 2009 for a number of items
  Repair and test currently ongoing and advancing well
  Refill of LHC stock (basically quench heater power supplies)
Reference systems for test, debugging and further development
  Existing systems to be upgraded to all QPS/EE system types installed in LHC

## Slide 6: Status of QPS – main circuits
Apart from nQPS commissioning
  All quench heater power supplies and energy extraction systems currently being switched off, but all protection systems running
  Interlock tests to be repeated prior to quench heater charging and nQPS commissioning
  Operation in 2009 fully satisfying
    Practically all observed problems related to quench heater power supplies
      Actual failure rate very low but 6200 units in LHC!
  Operational procedures to be revised (potential loophole!)
    The double fully redundant UPS powering scheme in place since 2009 requires for safe operation 2 out of 2 quad and 3 out of 4 dipole quench heater power supplies being available
    In any other cases and ICircuit > 2 kA the concerned circuit must be ramped down and the faulty power supply be exchanged

## Slide 7: Status of QPS – IPQ, IPD and IT
IPQ’s, IPD and inner triplets
  All quench heater power supplies currently switched off. Systems will be restarted according to HC requirements
  Firmware upgrade for prevention of repeated heater firing to be completed (affects only field-bus controller not detectors)
  Very stable operation in 2009
    No changes of hardware or detector firmware required
  nQPS (= dedicated splice measurement system) for these circuits not before end 2010
    Upgrades only for diagnostic purposes; circuits are fully protected by the present system

## Slide 8: Status of QPS – 600 A
600 A circuits
  Most of problems observed during 2009 run related to a hand full of controllers / circuits
    Hardware failures (very few)
    Communication problems and problems with power cycles
    Trips during pre-cycle and operation
  Analysis is ongoing
    In some cases help by MP3 may be needed
    Firmware updates
    Field-bus controllers, inductance tables (in a few cases only)
    Change of thresholds only where absolutely needed
  Some hardware to be repaired exchanged
PGC tests mandatory for final validation
  Upgrades may be required afterwards