## Slide 1: MQXF Quench Heaters plans and decision tree
Paolo Ferracin, Giorgio Ambrosio, Susana Izquierdo Bermudez
on behalf of the MQXF collaboration
9th HL-LHC Collaboration Meeting
14-16 October 2019
Fermilab, Batavia, USA

## Slide 2: Outline
Planned activities in the coming months
Decision tree

## Slide 3: Planned activities
Some key dates
  11/19
    instrumentation pre-impregnation of MQXFBP2 coil 110
      first coil of second MQXFB prototype
  03/20
    instrumentation pre-impregnation of MQXFA08 coil
      first coil of 3rd series cold mass MQXFA
  06/20
    instrumentation pre-impregnation of MQXFB01 coil 115
      first coil of first MQXFB series magnet (or first “spare”)

## Slide 4: Planned activities
Two options are being investigated with practice and real coils
  “Swap” and external QH
Practice coils
  CERN
    MQXFB 204: External QH  impregnated by end of 10/19
    MQXFB 003: External QH  impregnated by mid of 11/19
    MQXFB 205: swap  impregnated by end of 11/19
  AUP
    Short coil practice coil S4: swap  impregnated mid 08/19
  Coils MQXFB 204 and MQXFB 003 will be used to define the procedure for external quench heaters and tested in dummy assemblies in the MQXFB structure
  Coils MQXFB 205 and AUP S4 will be used to define the procedure for the swap and evaluate results

## Slide 5: Planned activities
Two options are being investigated with practice and real coils
  “Swap” and external QH
“Real coils”
  AUP short coil S10 with swap  to be tested by the end 01/20 in a mirror
  CERN short coil 113 and 114 with external QH
    Winding to start in 11/19 after cabling/insulation
    To be tested in MQXFS7 with two “old” coils by 06/20

## Slide 6: Outline
Planned activities in the coming months
Decision tree

## Slide 7: Decision “tree”
If
  Successful test of MQXFS4 (09-11/2019)
    Several thermal cycles, with all standard electrical tests passed and with intermediate HV test (80-120 K, He gas, 850 V, 1 bar) passed
  Successful test of MQXFA03 (10-11/2019)
    One thermal cycles with all standard electrical tests passed and with intermediate HV test (80-120 K, He gas, 850 V, 1 bar) passed
  …and giving the results of MQXFS1 and MQXFS3
  Experimental observation and computational analysis which explains the failure scenario and the degradation of the insulation
Then
  MQXFBP2 coils fabricated starting on 11/2019 with the swap
The proposal accounts for the change in electrical requirements
  Intermediate electrical test after powering test
    850 V, 100 K, 1 bar, He gas

## Slide 8: Decision “tree”
In the meantime, before 3rd series AUP coil (03/20) or before the 1st series CERN coils (06/20)
  MQXFB mech. Assembly with 1-2 coils with external QH by 01/20
  AUP short coil S10: swap  to be tested in 01/20 in a mirror
  One 11T short model with external QH  to be tested in 01/20
  MQXFA04 with impregnated QH  to be tested by 04/20
  Two 11T series magnets with external QH  to be tested by 04/20
  MQXFS7 with 2 coils with external QH  to be tested in 06/20
These results will be used to re-assess QH performance and finalize plan for 3rd series cold-mass AUP coil and 1st series CERN coils

## Slide 9: Decision “tree”
Else (so if not successful with S4 and A03…)
  Two options can be considered for MQXFBP2 coils fabricated starting on 11/2019
    If experimental observation and computational analysis are convincing that the increase of insulation thickness with the swap significantly improves the insulation
      With Swap
    Otherwise
      With external QH

## Slide 10: Decision “tree”
In the meantime, before 3rd series AUP coil (03/20) or before the 1st series CERN coils (06/20)
  MQXFB mech. Assembly with 1-2 coils with external QH by 01/20
  AUP short coil S10: swap  to be tested in 01/20 in a mirror
  One 11T short model with external QH  to be tested in 01/20
  MQXFA04 with impregnated QH  to be tested by 04/20
  Two 11T series magnets with external QH  to be tested by 04/20
  MQXFS7 with 2 coils with external QH  to be tested in 06/20
These results will be used to re-assess QH performance and finalize plan for 3rd series cold-mass AUP coil and 1st series CERN coils