## Slide 1: ALICE USA Computing Project Report
R. Jeff Porter
ALICE-USA Computing Resource Review
April 11, 2019

## Slide 2: ALICE-USA Computing Project
Initiated in 2009
  Objective: to meet US/DOE obligations to ALICE for Grid-enabled compute & storage
  Organization to procure resources & operate facilities at 2 DOE labs
  In operation since 2010
DOE project for ALICE-USA
  Project Exec. & Acquisition Plan (PEAP)
    Updated annually & submitted to DOE
    Procurement plans from ALICE targets
    Organization w/ operational milestones
  Quarterly reports to DOE
  Subject to periodic multi-year reviews
Current Effort
  ALICE: J. Porter, Project management, ALICE Computing board, AliEn site services
  ORNL: P. Eby, ORNL::EOS storage, M. Galloway, cluster management
  LBNL: J. White, LBNL_HPCS::EOS storage, K. Fernsler, cluster management
ALICE Grid
~1.2 FTE

## Slide 3: Project History
Original facility: NERSC/PDSF @ LBNL and Livermore Computing @ LLNL
  Proposal approved in Jan 2010, in operation by July
  External review in the following year, 2011
Project change in 2014
  LLNL withdraws from ALICE-USA
  Replace LLNL/LC with ORNL/CADES
  New proposal to DOE, review in June 2014
  ORNL T2 fully operational July 2015
  LLNL shut down October 2015
Project change again in 2017-2019
  NERSC to decommission PDSF
    Suggest PDSF groups can instead use its High Performance Computing (HPC) systems
  Our approach is to leverage new LBNL/IT cluster (LBNL/HPCS), with modest use of NERSC HPC
Project expects new multi-year proposal and external review in the next ~year
LLNL
ORNL
LBNL/HPCS
concurrent jobs: 2010-2018
20% annual growth
LBNL/PDSF

## Slide 4: Resource Requirements & Procurement Planning
ALICE Computing Requirements
vetted by the WLCG
ALICE-USA Resource Deployment Plan 
In annual PEAP update
% ALICE-USA participation
DOE requests we don’t overprovision

## Slide 5: ALICE Grid Site Topology
VObox site services
CE manages jobs/local queue
CM monitors global queue
MonaLisa
site monitor
EOS/XRootD
Grid-enabled Storage
Central Services
@ CERN
Global Task queue
File Catalog
Job Catalog
local
squids
CVMFS Stratum 1
Software Repo
Other ALICE
Grid sites
software deployment via cvmfs
cvmfs
OSG CE
LAN
WAN
Compute
cluster

## Slide 6: Site Operations
Sites must meet some basic requirements
  VOBox for AliEn services with selected external ports opened
  Grid-enabled disk-based storage, XRootD or EOS – (preferably EOS)
  Compute cluster supports:
    serial jobs, with 2-3GB mem + 10GB scratch disk per job
    outgoing network connections
    Software delivery via CVMFS
Sites do not have a clear view of what is run on their systems.
  This makes identifying site-level problems very difficult
  ALICE-USA used to provide some effort (B. Nilsen) to help connect cluster performance to ALICE jobs.
The project holds bi-annual meetings with CERN Offline team
  Consult on configurations
  Evaluate our site operations and performance

## Slide 7: US Site configurations
LLNL/LC: 2010-2015
  Stand-alone ALICE cluster within institutional computing facility
  1 continuous facility manager
  Batch: PBS/Torque + OSG gateway
  Gb Ethernet
  CVMFS via NFS gateway
  VObox on physical node
  In-house Linux OS
  XRootD, PB scale, hardware raid system
NERSC/PDSF: 2010-2019
  Shared facility at NERSC for HEP/NP exp.
  4 different facility managers over lifetime
  Batch: SGE, SLURM both + OSG gateway
  Mix 10 Gbit Ethernet & 40Gb InfiniBand
  CHOS virtualization
  VOBox on physical node, then in VM
  XRootD & EOS, PB scale hardware raid
ORNL/CADES: 2014-present
  Stand-alone ALICE cluster within institutional computing facility
  Two continuous facility support staff
  Batch: PBS/Torque, no OSG
  10Gbit Ethernet, 40Gb uplink
  Connected to LHCOne virtual network
  VObox in VM
  EOS, PB+ scale:
    Initially software raid (ZFS)
    Migrate to single disk FS
LBNL/HPCS: 2018-present
  Shared cluster within Institutional computing facility
  Two continuous facility support staff
  Batch: SLURM, no OSG
  Mix 10Gbit Ethernet & 40Gb InfiniBand
  VObox in VM
  EOS, PB+ scale, single disk FS

## Slide 8
ALICE RW test failures begin after 1.5 PB system at 95% capacity
  CPU efficiency drop noticed
  Report to ALICE & search for cause/remedy
Found block size mismatched wrt workload
  test draining data & reconfigure
  Drains stall due to high system load
Meet w/ EOS, ORNL, LBNL, vender engineers
  Confirmed block size mismatch
  Developed new reconfigure strategy
Reconfigure entire SE
  Take ~20% of system offline at a time
  Slow & w/ low cpu eff while in progress
  Lose a filesystem  overall cpu eff degradation
2nd reconfiguration
  Remove large raid file systems
  Slow & w/ low cpu eff while in progress
ORNL CPU Efficiency degradation from
ORNL::EOS configuration/performance
a.
b.
c.
d.
e.
2016
2017
2018
eff = 85%
eff = 70%
eff = 60%
eff =25%
Similar ALICE T2 = 80%
3 year CPU efficiency: Apr 2016– Mar 2019
ORNL
2019
eff = 50%

## Slide 9: ORNL CPU Efficiency degradation summary
ORNL was an early EOS adopter by request of ALICE Offline
  No EOS best practices existed: file-system size, concurrency/TB, OS or filesystem tuning
  Nor reproducible test suites or expectations beyond some global features, e.g. GB/s
Problem found to be from two issues related to the ORNL::EOS storage:
  Default block size used did not match well to ALICE access patterns
  Unresponsive 30-60TB ZFS raid file systems @ near capacity (with even native-EOS draining)
Fix was slow:
  Copy all resident data to new, restructured disks at ORNL
  Resource remained in production  copies were slow
  Many steps required by-hand manipulations on live system  error prone
  Multiple passes: to optimize block size & to move to non-raid single disk file systems
Lessons … ?
  See sub-bullets of top one here !! Can we fix this? -- particularly going into Run 3

## Slide 10: 2018 Project Operations

## Slide 11: 2018 PEAP Plan – Hardware
Resource | 2017 Installed | FY2018 plan | FY2018 (actual)
LBNL HW |  |  | 
HPCS CPU +/- kHS06 |  | 0.0 | +3.5
CPU NERSC HPC |  | 1.5+ | 0.0
CPU installed | 14.0 | 14.0 | 17.5
HPCS Disk +/- |  | 0.44 | 1.2
Disk installed | 1.06 | 1.6 | 2.25
ORNL HW |  |  | 
CPU +/- kHS06 |  | +10.0 | +6.0
CPU installed | 18 | 28.0 | 24.0
Disk +/- (PB) |  | 0.0 | 0.0
Disk installed | 2.25 | 2.25 | 2.25
+1M MPP hrs ~ 0.9 kHS06
2018 Allocation = 5M MPP hrs
2018 Plan Relative to Obligations:
  CPU : 43.5 kHS06 = 100%
  Disk : 3.85 PB = 99%
2018 Actual Relative to Obligations:
  CPU : 41.5 kHS06 = 95%
  Disk : 4.5 PB = 116%
Notes of interest
  Assumed added CADES nodes which came in Jan
  No real NERSC HPC contrib.
  Disk capacity at ORNL was used to reconfigure disks

## Slide 12
ORNL
PDSF
HPCS
~ave #-jobs 2018 target
ave #-jobs
2019
target
PDSF ramp down
HPCS ramp up
ORNL batch issues
significant periods with~70% slot occupancy
PDSF config problem
Stabilize ORNL batch system
Extra nodes from CADES
2018 Job Occupancy
ORNL
New nodes in Sept & Jan
Batch issues lowered rates
LBL PDSF
Early config problem lowered rates
Node removal began in Dec
Final shutdown on Apr 1st 2019
LBL HPCS
New nodes: Nov, Feb, Mar
Will take PDSF nodes in Apr/May
depends on
node-type mix

## Slide 13
CPU Efficiency
ORNL
  Periods of low eff. correlate with restructuring SE
LBNL
  Eff. is similar to other T2s.
HPCS
  Early results track LBNL
  Extreme low efficiency since summer correlated to very high rate of analysis jobs
Similar ALICE T2 = 77%
PDSF = 75%
ORNL = 70%
HPCS = 55%
HPCS trend line?

## Slide 14: 2018 CPU Delivery Relative to Obligations
USA T2 Site | Per/core CPU (HS06/slot) | Wall-time delivered (MHS06-hrs) | ALICE-USA obligation* (MHS06-hrs) | % obligation delivered
LBNL:PDSF+HPCS | 18.8+16.9 | 148.2+35.2=183.4 | 178.9 | 102%
ORNL | 12.0 | 177.0 | 183.0 | 97%
Total |  | 360.4 | 361.9 | 99.6%
Walltime delivered RRB-2018
CPU Obligations | kHS06
ALICE-USA | 43.5
LBNL T2 | 21.5
ORNL T2 | 22.0*
*ORNL cannot pledge w/o MoU
Issue: CPU deployment & utilization was not as planned, thus we underperformed early and overperformed late
Relative to 2018 Project Plan
* includes 95% uptime

## Slide 15
2019 Project Planning

## Slide 16: Resource Requirements & Procurement Planning
ALICE Computing Requirements
vetted by the WLCG
ALICE-USA Resource Deployment Plan 
In annual PEAP update
% ALICE-USA participation
DOE requests we don’t overprovision
Note:
Does not include obligations for US/NSF funded Scientists ~10%

## Slide 17: Site Change at LBNL
NERSC makes decision to decommission PDSF
  Future power & space needs, Operating costs
  NERSC desire to support workflows on HPC
Decommissioning schedule:
  Operate existing hardware to April 2019
  Allow grace period as needed until Aug 2019
Project plan:
  Replacement storage at HPCS
  Copy data from LBL::EOS to LBL_HPCS::EOS
  New CPU only on HPCS
  Move ~30 nodes from PDSF to HPCS
PDSF was shutdown April 1st 2019
And here we are
PDSF Decommissioning Schedule
✓
✓
✓
 we need to schedule!

## Slide 18: Overview of 2019 PEAP Update
Maintain facility at ORNL/CADES
  CPU slots & 2.x PB Storage
  Extra CPU gives us great safety margin!!
Expand new LBNL/HPCS Facility
  300 CPU slots  1000 CPU slots
  1000 CPU slots from PDSF
  1.2PB  2.5 PB storage
Modest use of NERSC HPC
  ~150 CPU slots
  Ready for next system: 2020
Submitted to DOE, Nov 9
  Reviewed at quarterly DOE call
Expect Multi-year Project Review in late 2019 or summer 2020
  Will cover the early Run 3 resource needs & operations
2019 PEAP Update

## Slide 19: 2019 Project Tasks
✓ - ORNL still cannot pledge
✓
✓
✓
✓
✓
✓
✓
✓
✓
✓
✓
✓
We have quotes -->
Do we need to document? -->
We couldn’t this year -->
We couldn’t this year -->
Students this summer -->
New program manager -->
Oct-Dec 2018
Jan-Mar 2019

## Slide 20: 2019 Project Tasks continues
Proposal not funded!!
June-Sept 2019
Apr-June 2019

## Slide 21: Project Effort - Issues & Opportunities
PDSF support staff are no longer part of the project
  In truth, this has been so since Iwona & Lisa left in 2015
ALICE-USA used to provide ~1/3rd FTE as community service
  Last effort ended in 2013
LDRD funds still remain, but no one to take up the tasks
  Funds go away Sept 30, 2019
I have funds to support:
  2 Romanian Student for summer 2019
  1/2 Post-Doc for 2 years, can be paired up with NP/OSG funds for CS-type PD or project scientist/engineer. Note, tasks are more engineering than PD research
Current support items:
  Michael is on retirement slope
  Jeff may be on retirement slope in the next year+

## Slide 22
2014 Proposal Review:
ALICE USA T2 Sites