## Slide 1: ECR: Positioning of the Quench Heaters on the 11T magnet
D. Schoerling
TCC 2nd of May 2019

## Slide 2: Comments
The technical aspects have been discussed in detail in the 67th TCC (14th February 2019). In this meeting the outcome of the dedicated technical meeting chaired by Felix Rodriguez Mateos has also been presented.
It is planned to produce two coils (12 and 13) still with quench heaters impregnated to be able to equip magnet 2 with collared coils of the same kind as magnet 1 (QH impregnated)
The production with external quench heaters has been impregnated (coil 10); the next coil with external QH will be impregnated on May 5th (coil 11). Following all coils (except 12 and 13) will be produced with external QH.
Comments:
Benoit: At WP11 PSM of 07/02/19, it was explained that this change might induce 5 coils and 4 collared coils more. Why does this ECR refer to 8 coils and 4 collared coils? This has an impact on the cost of this ECR. The plan presented in PSM was estimated to cost 580kCHF for components and about 1420kCHf for the S197 manpower, i.e. a total of 2000kCHF. This ECR amounts to about 2700kCHF. I guess this change shall be clarified at TCC. The impact on the manpower needed for cabling activities should also be assessed (additional unit length of cable to be produced).
Answer: Please refer to the table on the next slide for clarification on the number of coils, CC and magnets to be produced. This table will be included in the ECR for clarification. In a success oriented planning, we have to do 5 additional coils and 3 additional collared coils, with a cost of:
Components | 500 kCHF
GE contractual price | 1300 kCHF
TOTAL | 1800 kCHF

## Slide 3
 | Conforming magnets | Conforming CC | Coil production
Baseline, QH | 4+2 M + 6 coils | 12 CC + 6 coils | 24+6 coils
To fullfill the recommendation R2 & R18 at the present state of production: | 2 M (QH), 4 M (external QH) + 4 CC (external QH) | 16 CC (conforming) | 32 coils; + 4 coils (lost)
Recommendation, aligned to strand availability | 2 M (QH), 4 M (external QH) + 3 CC (external QH) + 1 coil | 15 CC (conforming) + 1 coil (spare) | 31 coils; + 4 coils (lost)
QH, impregnated | 2 M | 4 CC | 8 coils
QH, external | 4 M + 3 CC + 1 coil | 11 CC + 1 coil | 23 coils

## Slide 4: Comments
Laurent: Following the test results in September 2019, the Master Schedule of the WP11 will be updated for the next C&S review scheduled in November 2019.
Answer: In September the go/no-go decision will be taken based on an internal review after testing one 11 T dipole magnet
Daniel W: The recent use of the uQDS prototype for the protection of the 11T hybrid magnet in SM18 has been very successful and gives us the confidence that the specified interlock limits and reaction times can be fulfilled.
It should, nevertheless, clearly be stated that the threshold and evaluation time needs to be significantly increased for currents below 6 kA to avoid trips by flux jumps
Answer: Thank you for this confirmation. It will be clarified that the threshold and evaluation time needs to be significantly increased for currents below 6 kA to avoid trips by flux jumps. The values used in SM18 were 200mV threshold and 40 ms evaluation time for < 6 kA, the same values are planned to be used in the LHC. Analytical estimates of the MITTs, based on measurements on the short models in SM18, show that also with these settings the MIITs are largest at nominal current; therefore, the largest hot-spot is expected to arise in case of quench at nominal current (values as presented in the QH ECR). The analytical estimates will be discussed in MCF.

## Slide 5: Comments
Lucio: I am very concerned to introduce such modification during final production. I think that the risk vs. advantage are a little underestimate, but I do not oppose since it is a technical item that must be decided by the technical group.
Answer: Thank you for this comment. Production and operation risks were evaluated by the technical meeting on quench heaters, discussed in detail in the 67th TCC, we decided to follow R14: ‘R14- The Panel strongly recommends positioning the QH outside of the impregnated coil’.
Arnaud: Seen.
Answer: Thank you.
Gianluigi: Do not see implications for beam dynamics. I assume that the is no impact on coil aperture and field quality.
Answer: We confirm that there is no impact on beam dynamics.
Michele: It does not seem to have any impact on "warm powering"
Answer: We confirm that there is no impact on "warm powering".