## Slide 1: Transport and installation of DFX in the LHC underground areas
R.Betemps, EN-MME
Y.Leclercq, V.Parma, TE-MSC
With input from SOTON (Y.Yang, W.Bailey) and WP15 (M.Amparo, P.Fessia)
Detailed Design Review of the DFX, CERN 20 June 2019

## Slide 2: Preamble
The following slides show the main steps of the assembly of the DFX according to the design by SOTON, but projected into the tunnel environment according to the study by the integration team under WP15. It does not include tools for transport, handling, positioning, nor the special tools for welding, leak detection and other QC means. This work will be done by CERN in the next future and the first assembly need will be for installation in SM18 (for the system test and for the String) which will provide an opportunity for validating procedures, tools and QC.
The intention of these slides is to illustrate the environment and space limitations in the LHC tunnel in IR5L.

## Slide 3: Tunnel configuration at DFX installation
DCM
QXL
D1
SC link for DFM/D2
(space occupation, size is smaller)

## Slide 4: DFX machine assembly
Plug install with LTS
Assembly of IFS assy. to DCM
DCM
SC link
(space occupation)
IFS assy.
Plug now part of DCM, with LTS bus bars

## Slide 5: DFX machine assembly
1. Top Flange and DFX tank in prepared position
2. Link Down +100 mm with LTS
3. Weld of the flange, weld inspections and leak checks

## Slide 6: DFX machine assembly
Move the He tank and link 100 mm up
Equipment of the top flange
LTS extension shaped for threading of horizontal segments
(Burst disk mounted
only after Pt)

## Slide 7: DFX machine assembly
Threading of helium & vacuum chamber in place (will be helped with a side bend of the LTS cable)
Welding, weld inspections and leak checks

## Slide 8: DFX machine assembly
Vacuum chamber move to allow the weld with the horizontal section

## Slide 9: DFX machine assembly
Helium & vacuum vessel segments
Welding, weld inspections and leak checks

## Slide 10: DFX machine assembly
Splices, instrumentation wires connections, electrical checks
Final welding helium chamber (+checks)
Close the vacuum chamber
Connection of cryogenic lines flexible to QXL (not shown)
Cryogenic line flexible)

## Slide 11: DFX machine assembly
Add the DFX longitudinal force frame
Ins. vacuum pumping and global leak check possible
…

## Slide 12: Summary
From this preliminary study we learn about the space limitations for the DFX assembly in the tunnel providing the play ground for developing handling, positioning and assembly tooling
Once the 3D models are finalized, a structured assembly study work should be carried out to define assembly procedures, and QC checks
This study is planned to be closely followed in WP15

## Slide 13: Thank you for your attention Q&A?