## Slide 1: Status of the PSB IST
LIU Commissioning Coordination Committee
31st May 2019
Work done by A. Akroh, F. Chapuis
Presented by G.P. Di Giovanni

## Slide 2
PSB IST
  Goal: Collect information for scheduling, including safety aspects.
    Type of test, sequence, duration, prerequisites, risk and compensatory measurements.
    Deadline: end June 2019.
  The PSB HW commissioning coordinators worked to gather the necessary information and presented the current list at the LIU-PSB TCM, https://indico.cern.ch/event/813464/
    Validated the list of tests and made sure that no test was overlooked.
5 weeks: from Monday 09/03/2020 to Friday 09/04/2020

## Slide 3
PSB IST
IST Inventory |  | 
Equipment Group | Systems | Comment
BE-BI | All | Waiting feedback
BE-CO | FEC - Middleware | Local OASIS cable connection
 | External Conditions | Local test
 | SIS | No IST. Done in HW Comn.
BE-ICS | Booster Safety Chain | Software test
BE-RF | Finemet | Fence the tested area
 | Transverse FeedBack | Local test. No access tunnel.
EN-STI | Beam Stoppers | New Beam Stoppers
TE-ABT | Kickers / Septa / Bumpers / Distrib. /Strip. Foil | Earlier start for SF and BT.SMV
TE-EPC | Auxiliairy Pow. Conv. | Detailed planning. Anticipate tests as much as possible
 | POPS-B - BR.MPS | No IST. Tests in B245 with dummy load from B237
TE-MPE | BIC | Loca test
 | WIC | Tests will follow EPC schedule
TE-MSC | Magnet | Follow EPC schedule or HW commissioning
 | B-Train | Local test. No coativity
TE-VSC | Vacuum | No IST

## Slide 4
PSB IST
BE-BI will provide the necessary information to
assemble the list of IST and HW tests beg. June
IST Inventory |  | 
Equipment Group | Systems | Comment
BE-BI | All | Waiting feedback
BE-CO | FEC - Middleware | Local OASIS cable connection
 | External Conditions | Local test
 | SIS | No IST. Done in HW Comn.
BE-ICS | Booster Safety Chain | Software test
BE-RF | Finemet | Fence the tested area
 | Transverse FeedBack | Local test. No access tunnel.
EN-STI | Beam Stoppers | New Beam Stoppers
TE-ABT | Kickers / Septa / Bumpers / Distrib. /Strip. Foil | Earlier start for SF and BT.SMV
TE-EPC | Auxiliairy Pow. Conv. | Detailed planning. Anticipate tests as much as possible
 | POPS-B - BR.MPS | No IST. Tests in B245 with dummy load from B237
TE-MPE | BIC | Local test
 | WIC | Tests will follow EPC schedule
TE-MSC | Magnet | Follow EPC schedule or HW commissioning
 | B-Train | Local test. No coativity
TE-VSC | Vacuum | No IST

## Slide 5
PSB IST
Prerequisite for tests is that the Rack Power Supply (CANALIS) must be powered.
[Expected 13/01/2020]
BE-ICS: Connection of new EIS.f to PSB Safety Chain and
PASS program update
3 days without Access in the machine
(from 24/02/2020 to 20/03/2020)
IST Inventory |  | 
Equipment Group | Systems | Comment
BE-BI | All | Waiting feedback
BE-CO | FEC - Middleware | Local OASIS cable connection
 | External Conditions | Local test
 | SIS | No IST. Done in HW Comn.
BE-ICS | Booster Safety Chain | Software test
BE-RF | Finemet | Fence the tested area
 | Transverse FeedBack | Local test. No access tunnel.
EN-STI | Beam Stoppers | New Beam Stoppers
TE-ABT | Kickers / Septa / Bumpers / Distrib. /Strip. Foil | Earlier start for SF and BT.SMV
TE-EPC | Auxiliairy Pow. Conv. | Detailed planning. Anticipate tests as much as possible
 | POPS-B - BR.MPS | No IST. Tests in B245 with dummy load from B237
TE-MPE | BIC | Local test
 | WIC | Tests will follow EPC schedule
TE-MSC | Magnet | Follow EPC schedule or HW commissioning
 | B-Train | Local test. No coativity
TE-VSC | Vacuum | No IST

## Slide 6
PSB IST
High-Level Finemet tests start during LS2 (mid November 2019)
  Demi water and electrical network required.
  Access should be possible.
  Fence the tested area.
Low-Level RF experts tests will follow the testing done for the HLRF.
TFB:
  Check-up cables connection and length with a network analyser.
  Amplifier commissioning in local.
IST Inventory |  | 
Equipment Group | Systems | Comment
BE-BI | All | Waiting feedback
BE-CO | FEC - Middleware | Local OASIS cable connection
 | External Conditions | Local test
 | SIS | No IST. Done in HW Comn.
BE-ICS | Booster Safety Chain | Software test
BE-RF | Finemet | Fence the tested area
 | Transverse FeedBack | Local test. No access tunnel.
EN-STI | Beam Stoppers | New Beam Stoppers
TE-ABT | Kickers / Septa / Bumpers / Distrib. /Strip. Foil | Earlier start for SF and BT.SMV
TE-EPC | Auxiliairy Pow. Conv. | Detailed planning. Anticipate tests as much as possible
 | POPS-B - BR.MPS | No IST. Tests in B245 with dummy load from B237
TE-MPE | BIC | Local test
 | WIC | Tests will follow EPC schedule
TE-MSC | Magnet | Follow EPC schedule or HW commissioning
 | B-Train | Local test. No coativity
TE-VSC | Vacuum | No IST

## Slide 7
PSB IST
TE-ABT detailed commissioning organised in 4 Phases.
IST needed for Phase 2 and possibly Phase 1 (tbc).
Starts earlier for some equipment such as Stripping Foil,
BT.SMV (04/03/2020)
Pulse the system in local mode at Low Voltage.
IST Inventory |  | 
Equipment Group | Systems | Comment
BE-BI | All | Waiting feedback
BE-CO | FEC - Middleware | Local OASIS cable connection
 | External Conditions | Local test
 | SIS | No IST. Done in HW Comn.
BE-ICS | Booster Safety Chain | Software test
BE-RF | Finemet | Fence the tested area
 | Transverse FeedBack | Local test. No access tunnel.
EN-STI | Beam Stoppers | New Beam Stoppers
TE-ABT | Kickers / Septa / Bumpers / Distrib. /Strip. Foil | Earlier start for SF and BT.SMV
TE-EPC | Auxiliairy Pow. Conv. | Detailed planning. Anticipate tests as much as possible
 | POPS-B - BR.MPS | No IST. Tests in B245 with dummy load from B237
TE-MPE | BIC | Local test
 | WIC | Tests will follow EPC schedule
TE-MSC | Magnet | Follow EPC schedule or HW commissioning
 | B-Train | Local test. No coativity
TE-VSC | Vacuum | No IST

## Slide 8
PSB IST
TE-EPC commissioning follows a check-list of 14 steps!
Two batches of tests:
  Step 1 to 8: not connected to magnet → IST
  Step 9 to 14: connected to magnet → HW Commissioning
LT / LTB commissioning scheduled in 2019 during LBE Run.
BI/BR/BE/BT/BTM/BTP and BTY.BVT101 commissioning during the IST period.
  Electrical Hazard. May require closed access.
IST Inventory |  | 
Equipment Group | Systems | Comment
BE-BI | All | Waiting feedback
BE-CO | FEC - Middleware | Local OASIS cable connection
 | External Conditions | Local test
 | SIS | No IST. Done in HW Comn.
BE-ICS | Booster Safety Chain | Software test
BE-RF | Finemet | Fence the tested area
 | Transverse FeedBack | Local test. No access tunnel.
EN-STI | Beam Stoppers | New Beam Stoppers
TE-ABT | Kickers / Septa / Bumpers / Distrib. /Strip. Foil | Earlier start for SF and BT.SMV
TE-EPC | Auxiliairy Pow. Conv. | Detailed planning. Anticipate tests as much as possible
 | POPS-B - BR.MPS | No IST. Tests in B245 with dummy load from B237
TE-MPE | BIC | Local test
 | WIC | Tests will follow EPC schedule
TE-MSC | Magnet | Follow EPC schedule or HW commissioning
 | B-Train | Local test. No coativity
TE-VSC | Vacuum | No IST

## Slide 9
PSB IST
IST Inventory |  | 
Equipment Group | Systems | Comment
BE-BI | All | Waiting feedback
BE-CO | FEC - Middleware | Local OASIS cable connection
 | External Conditions | Local test
 | SIS | No IST. Done in HW Comn.
BE-ICS | Booster Safety Chain | Software test
BE-RF | Finemet | Fence the tested area
 | Transverse FeedBack | Local test. No access tunnel.
EN-STI | Beam Stoppers | New Beam Stoppers
TE-ABT | Kickers / Septa / Bumpers / Distrib. /Strip. Foil | Earlier start for SF and BT.SMV
TE-EPC | Auxiliairy Pow. Conv. | Detailed planning. Anticipate tests as much as possible
 | POPS-B - BR.MPS | No IST. Tests in B245 with dummy load from B237
TE-MPE | BIC | Local test
 | WIC | Tests will follow EPC schedule
TE-MSC | Magnet | Follow EPC schedule or HW commissioning
 | B-Train | Local test. No coativity
TE-VSC | Vacuum | No IST
For information: POPS-B and BR.MPS are scheduled during the HW commissioning from 02/06/2020 to 10/07/2020.
BIC modification to be tested beginning 2020: Local test
with no interference to shutdown activities; missing
input will be tested during HW commissioning. Still plan
to integrate in the planning.
TE-VSC specialist commissioning scheduled during
Jan. 2020 and depending on equipment availability.

## Slide 10
Summary
  List of ISTs prepared and discussed with equipment experts.
  Three systems flagged to require safety regulation:
    Finemet cavities (BE-RF).
    Beam transfer equipment (TE-ABT).
    Auxiliary power converters (TE-EPC).
  The PSB HW commissioning coordinators have prepared a similar template used for the Linac4 LBE run.
    Still outstanding is the list for BE-BI. To be finalized beginning June.