## Slide 1: Procedures (fabrication and inspection)
Michinaka Sugano
KEK
Production Readiness Review for D1 Yoked Magnet, CERN & KEK, October 3, 2019

## Slide 2: Organization: KEK, CERN, Hitachi
Project Manager
T. Nakamoto
Head of Cryogenics Science Center
T. Ogitsu
Design Team
M. Sugano
Quality Control Team
T. Nakamoto
Test Team
K. Suzuki
Contract Section
Manufacturer (Hitachi)
A. Horikoshi (PM)
T. Chiba (GL)
Outside supplier
Technical supervision
WP3
WPL: E. Todesco (CERN)
WPE: A. Musso (CERN)
Technical
transfer

## Slide 3: Contents
Fabrication processes in 2 m-long model magnets
Preparation for constructing 7 m-long yoked magnet
Technical transfer from KEK to Hitachi
EIQA withstand voltage test

## Slide 4
Fabrication processes in 2 m-long
model magnets

## Slide 5: Flow of fabrication processes to yoked magnet
Coil winding
Curing
Coil size measurement
Instrumentation (Only for model magnets)
Preparation before QPH wrapping
QPH, Ground insulation wrapping
Brass shoe assembly
Collaring
Yoking
Electrical test
Electrical test
Electrical test
Electrical test
Electrical test
Shell
Collar
Nb-Ti/Cu coil
GFRP
wedge
Yoke
QPH
Insulation
Brass shoe

## Slide 6: Coil winding ~ Curing
Tensioner
Feeder
Turn table
Winding mandrel
Coil winding
Curing
Cu/Nb-Ti cable
GFRP wedges
Wet-winding applied to coil end
Pushing a coil into curing mold
Pressing and heating for coil forming
All the model magnets (MBXFS1–3)
were fabricated and tested at KEK.

## Slide 7: Coil size measurement ~ QPH, insulation wrapping
Coil size measurement
QPH, ground insulation wrapping
Coil is compressed to a certain size to evaluate azimuthal coil size
QPH composed of SUS strips sandwiched by polyimide insulations
Four layers of ground insulations
Brass shoe assembly

## Slide 8: Collaring ~ Yoking
Collaring
Yoking
SUS collar assembly by pressing
Yoke assembly and key insertion
Coil pre-stress is mainly applied in yoking process
Removing collapsible collaring mandrel

## Slide 9: Feedback from model magnet development to prototype construction
Detachment
No detachment
Shorter duration
time
Different loading cycle
Some issues have been solved through model magnet development.
The modified processes will be applied to prototype construction.
Modified process
ex. Consideration of curing condition in the second model magnet

## Slide 10: Electrical test
 | Coil resistance | Coil inductance | QPH resistance | Energy deposition test of QPH | Surge test | Hi-pot* test
After Coil winding |  |  |  |  |  | 
After curing |  |  |  |  |  | 
After instrumentation |  |  |  |  |  | 
Before QPH, GI wrapping |  |  |  |  |  | 
Before collaring |  |  |  |  |  | 
After collaring |  |  |  |  |  | 
After yoking w/o collaring mandrel |  |  |  |  |  | 
The condition of Hi-pot test was in compliant with EDMS2187266.

## Slide 11: Measurements and inspections other than electrical test
Coil winding
  Visual inspection of cable surface, longitudinal cable position and cable angle, longitudinal position of end spacers
Curing
  Curing press: Vertical gap between pressing jigs, ground fault check by a multimeter, coil resistance, displacement by longitudinal loading, azimuthal coil pressure at MP by Fuji-paper test
  Curing: Temperature monitor
  Cured coil: Longitudinal position of end spacers, coil length
Collaring
  Thickness of collar substacks
  Collaring press: Coil resistance, ground fault check by a multimeter, azimuthal coil stress by strain gauges
  Meas. after collaring: Outer diameter and length of collared coil, relative position of coil end w.r.t collar
Yoking
  Thickness of yoke substacks
  Yoking press: Vertica gap between pressing jigs, ground fault check by a multimeter, coil resistance, azimuthal coil stress by strain gauges
  Meas. after yoking: Outer diameter and length of yoked magnet, relative position of coil and collar w.r.t yoke
The same measurements and inspections will be
performed in fabrication of a prototype

## Slide 12
Preparation for constructing
7 m-long yoked magnet

## Slide 13: Manufacturing site
Distance between KEK and Hitachi, Ltd. is about 80 km
Total transportation distance until final delivery to KEK is
about 240 km (3 times for 1 magnet).

## Slide 14: Layout of manufacturing site for a prototype
Vinyl house, dust rejection & air conditioner
Preparation table of Yoking
Curing & Yoking press
Welding area
Winding
Preparation of Curing/
Insulation
Coil assembly and collaring
Unit: mm

## Slide 15: Layout of manufacturing site for series production
Working area for yoking and welding will be moved to another building to keep cleanness necessary for coil winding.
Unit: mm
Working area 1: 20m×13m
Working area 2: 24m×9m
> Parts storage
> Welding
> Yoking
> Pressurization test
> Winding
> Curing
> Insulation
> Collaring
Vinyl house, dust rejection
& air conditioner

## Slide 16: Preparation for toolings
Toolings provided from KEK to Hitachi
  Winding machine
  Curing press
  Coil size measurement apparatus
  Collaring press
  Yoking press (same as curing press)
Toolings prepared by Hitachi
  Forming blocks
  Yoking jigs
  Collaring mandrel

## Slide 17: Technical updates from model magnets to a prototype
Coil winding
  The winding machine for a 7 m-long coil has been installed and basic operation test was completed by KEK.
  Resin sheet for wet-winding  under development by Hitachi
Curing
  Gap filling with radiation resistant resin
   R&D of new resin is ongoing by a company in collaboration with KEK.
QPH, insulations
  Cutting 7 m-long QPH and ground insulations
   Cutting by an automatic cutting machine was proposed by KEK to Hitachi
7 m-long winding machine
R&D of resin
QPH cutting

## Slide 18: Procedure manuals
Date
Worker
Check when this work
has been done
Caution for safety
Caution to avoid
non-conformity
issue
ex. Procedure manual and check list for curing
Procedure manual and check list were prepared by KEK for fabrication of model magnets.
Similar documents will be prepared by Hitachi for manufacturing a prototype.
These documents will be written in Japanese and stored as applicable documents referred in MIP. As for the inspection reports, English language version shall prevail.

## Slide 19: MTF
In model magnet fabrication, KEK uploaded material data sheets, inspection report and measurement results to MTF.
MTF for a prototype is now being prepared by CERN based on BOM.
The documents will be uploaded to MTF by KEK.
MTF for MBXFS3 (3rd model magnet)
BOM for a prototype

## Slide 20
Technical transfer
from KEK to Hitachi

## Slide 21: Hitachi’s experience in mode magnet fabrication
Hitachi started the cooperative research with KEK from Oct. 2016.
Through this research, Hitachi acquired detailed knowledge about model magnets including manufacturing.
Because Hitachi didn’t take part in the actual manufacturing of model magnets, technical transfer from KEK is necessary.

## Slide 22: Drawings
All the drawings prepared for 2-m long model magnets have been provided from KEK to Hitachi. Design of collar and yoke will not be changed from the third model magnet, MBXFS3.
Coil cross-section will be changed from MBXFS3 to a prototype to improve field quality. The final drawings for coil wedges and end spacers is under preparation by KEK and provided to Hitachi soon.
The drawings of forming blocks and collaring mandrel were prepared by KEK and provided to Hitachi to save time.
Reference assembly drawings and drawings of toolings for a prototype have been also provided from KEK to Hitachi. Hitachi will make all the drawings for ordering.
After KEK’s approval of the drawings from Hitachi, parts and toolings will be placed an order. The final drawings will be uploaded to CDD.

## Slide 23: Examples of drawings prepared by KEK
Most of the parts used in model magnets can be applied to a prototype.
Assembly drawings of a prototype as a reference were also provided from KEK so that Hitachi can make necessary modifications easily.
Coil
Ground insulations
Collared coil
Yoked magnet

## Slide 24: Dry run of coil winding
A dry run of coil winding will be performed at KEK at the end of October before the winding machine is transported to Hitachi.
Purposes: Validation of winding machine in terms of workability and safety
Technical transfer to Hitachi’s worker
Items to be checked:
  Winding machine: Rotating speed, braking distance, safety
  Toolings: Workability to remove and attach the support jigs, cable support in the straight section

## Slide 25: Fabrication of a 7 m-long test coil
A 7-m long test coil with the same cross-section as a prototype will be wound and cured at Hitachi with KEK.
Purposes:
  Technical transfer from KEK to Hitachi
  Validation of winding tools, wet-wining with resin sheets
  Validation of curing
  Practice for quality assurance: Electrical test, measurement during winding
  Test of curing cycle: Temperature profile and homogeneity, pressure
  Validation of coil handling tools: jigs for coil rotation and hanging
  Coil size measurement
  The cutouts from the straight section will be used for mechanical short model assembly

## Slide 26: Mechanical short model assembly
Purposes:
Validation of wedge design to be applied to
a prototype by evaluating azimuthal coil
pre-stress
Technical transfer of magnet assembly
7 m-long
test coil winding
Curing
Coil cut
QPH, insulation
wrapping,
Brass shoe
assembly
Collaring
Yoking
Shell welding
Cooling-down
to 77 K
Instrumented collar

## Slide 27
EIQA withstand voltage test

## Slide 28: EDMS document for EIQA
ElQA test conditions are defined in EDMS2187266.
The test for the third model magnet (MBXFS3) already followed this criteria.

## Slide 29: Maximum voltage condition for Hi-pot test
Maximum voltage condition of Hi-pot test up to yoked magnet in compliant with EDMS2187266.
Hi-pot test was performed at the same condition in MBXFS3.
 | Coil | QPH | Inspector
Before QPH cutting | – | 4.6 kV | KEK
After yoking w/o collaring mandrel | 2.6 kV* | 4.6 kV | Hitachi
* Voltage is applied between one of the coils and the ground.
Another coil is grounded.

## Slide 30: Conclusion
7 m-long yoked magnet for a prototype of MBXF will be constructed in the processes similar to the model magnets.
Technical transfer from KEK to Hitachi is crucial in terms of quality and schedule.
Manufacturing procedures will be prepared by Hitachi based on those for model magnets and test coil fabrication.
EIQA test will be performed according to the conditions defined in EDMS document.