## Slide 1
Planning tools for recommissioning
J. Ridewood on behalf of BE/OP recommissioning coordinators
for LIU Hardware commissioning meeting

## Slide 2
Recap
A request from Montreux LIU review for recommissioning coordinators to use planning tools that allow EN-ACE to perform resource allocation across machines and across periods
Despite a demand from CERN as a whole to reduce dependence upon MS products, MS project remains the de-facto standard
Currently available alternatives do not have the required functionality
  JIRA gantt is the closest viable alternative... but resources can be assigned only to a single JIRA user….therefore not compatible for resource allocation

## Slide 3
What do we need to use MS project?
A license (≈350CHF per person per year) is required for all those wishing to see or work on MS project files https://cern.service-now.com/service-portal/article.do?n=KB0005844
  IT have agreed to cover license costs for those requiring access until end LS2
  Many recommissioning coordinators may already have a license to view shutdown planning
  However work is underway to made read only access easier/cheaper
EN-ACE (Julie) agreed to put the planning files in place for us on their server
Editing from a web browser is possible…but less convenient
  Therefore a windows PC (or virtual machine) is desirable

## Slide 4
Benefits? Inconveniences?
Will allow some EN-ACE analyses of resource allocation and perhaps highlight potential clashes across the complex
Will allow a more dynamic means of planning restarts
  If one task is late then the consequences on planning can be evaluated
A new tool with an uncertain future to learn
  And a windows machine (real or virtual) is required
Still no direct link between checklists and planning
  It remains a manual task to make the two work together

## Slide 5
What needs to be planned?
It is not necessary (or practical) that each test, each item of equipment or each checklist node is included explicitly in the planning
  However it may be useful to link to nodes in the details
  Recommissioning coordinators will schedule checklist tasks and monitor progress … as before
We envisage a similar level of detail as used previously
  Blocks of tests, equipment availability, milestones, key stages, restrictions, tests with specific prerequisites etc.
EN-ACE will be owners of IST planning (With OP collaboration)
  EN-ACE will also plan for certain ISTs which extend into HWC period
OP will plan HWC period
Both plannings for IST and HWC should be superimposable (part of a master planning)

## Slide 6
Status
Julie has created individual planning files for both IST and HWC for each machine https://cern.sharepoint.com/sites/Projects-Accelerator-Complex-Schedules/Projects.aspx
Julie has given an introductory session to explain the basics
  Primarily checking out and in of planning files to avoid file conflicts
Recommissioning coordinators are now starting to fill HWC planning and assist with IST planning