## Slide 1: Infrastructure Modification Compatibility for 11T
M. Gonzalez de la Aleja, P. Fessia
13/08/2019

## Slide 2
Outline
Description of necessary modifications for the installation of the 11T assembly (11T dipoles+TCLD) are described in:
  WP11: 11T Dipole Full Assembly Integration Study  EDMS 1904620
  WP5: TCLD Integration Study  EDMS 1903950
The aim is to go through the list of activities foreseen, analise compatibility of services and components for both configurations:
  11T full assembly
  Standard LHC dipole
Summarize the info in 2 tables and 2 images (LHC dipole vs 11T config.) + spare slides

## Slide 3
11T expected activities - Compatibility
R7
LHC C9R7
HL-LHC C9R7
1
9
9
9
7
10
12
14
16
11
DYPB
6
6
2
3
4
5
In the RR77
8
13
15
17
In the TZ76
17
17
MB.A9R7 (LBARA.9R7)

## Slide 4
11T expected activities – Infrastructure modif. compatibility
n | Activities | Loc | Fully Compatible | Non Compatible | Comp. with Modification | Comments
1 | DYPB.9R7 removal Currently installed under MB.A9L7, protecting the mentioned dipole. MB.A9L7 dipole to be removed. | 9R7 | X |  |  | It can be stored and put it back. Possibility to leave cabling in place
2 | RYSA01 removal Rack installed at RR77. It will be replaced by the new RYABA01 (11T PC) | RR77 | X |  |  | RYSA01 is a rack where EPC has disconnected modules that serve as spares for the racks in that area; if there is a problem in a connected spare, they take out the module and replace by one that is in the RYSA rack.
3 | RYABA01 (11T PC) installation Plus the current leads cabling | RR77 | X |  |  | Activity to be performed at the RR, Independent from tunnel activities
4 | Water connection for 11T PC | RR77 | X |  |  | Activity to be performed at the RR, Independent from tunnel activities
5 | 2 crates for QDS and TRIM Units can be integrated between DYPG01 and DYPIB01 racks | RR77 | X |  |  | Activity to be performed at the RR, Independent from tunnel activities
6 | 2 DYPB racks for 11T installation - Under MB.A8R7 - Under MB.A10R7 | 8R7, 10R7 | X |  |  | Activity to be performed away from 11T cryostat. Cabling connected to the IFS and to the racks in the RRs can be installed anyway.
7 | 3BLMs for 11T magnets + 1BLM for TCLD | 9R7 |  | X |  | BLM to be considered as part of the 11T assembly. Present BLM to be uncabled at the last moment
8 | Paint Limited Stay Areas on the floor (at the level of the non spring loaded valve in MB.B8R7) | 8R7 | X |  |  | 
9 | F3/F4 Electrical Boxes displacement Installed on cable trays in front of the MB.A9L7 (LBBRB.9L7) dipole. To be displaced by 11m towards the arc. | 9R7 | X |  |  | Check the cabling length of components with connections to those boxes (EN-EL)
10 | Reduce size of L18A EC (control cable ladder) To avoid intefrerence with palfinger during TCLD installation | 9R7 | X |  |  | 
11 | Displace the cable tray support to the left of its actual position, and if needed, install another one to the right. | 9R7 | X |  |  | 
12 | Re-route nQPS and BLM cables currently installed in a TELEX along the magnets (using L18A EC and L12A EC, respectiv.) | 9R7 |  |  | ? | Presently approved configuration is not compatible between 11T and stardand dipole. To check if it can be modified to make it compatible with both configurations
13 | 3 Coffrets Prise installation 4x10A monophase, 16A triphase, 32A triphase | 9R7 |  |  | X | At the foresee location, they might interfere if we later re-install the old dipole with the current racks. In any case, they should be installed after the 11T dipoles are in place.
14 | Passerelle over the QRL installation | 9R7 | X |  |  | It can be installed and left in place
15 | LHC Bridge installation | 9R7 | X |  |  | It will be removed if 11T if the 11T is not installed
16 | Water connections to the EDA/EDR pipes Installation of flexible pipes to the TCLD | 9R7 | X |  |  | It can be done and ready for use. It doesnt matter if in the end they are not used
17 | Installation of new racks for TCLD in the LHC galleries | TZ76 | X |  |  | Independent from tunnel activities. Cabling to be connected to the TCLD can be pulled from the racks and installed along the tunnel till the area
18 | 11T+TCLD jacks installation | 9R7 |  | X |  | Standard dipole jacks and new 11T+TCLD jacks are not compatible
13
TCLD
TCLD
TCLD
TCLD
TCLD
TCLD
TCLD
TCLD
TCLD
TCLD

## Slide 5
11T expected activities - Compatibility
DRAFT
L7
LHC C9L7
HL-LHC C9L7
1
10
MB.A9L7 (LBBRB.9L7)
DYPB
15
2
DYPQ
9
3
4
5
6
In the RR73
14
In the TZ76
10
8
11
12
15
13
7

## Slide 6
n | Activities | Loc | Fully Compatible | Non Compatible | Comp. with Modification | Comments
1 | DYPB.9L7 removal Currently installed under MB.A9L7. To be removed | 9L7 | X |  |  | It can be stored and put it back. Possibility to leave cabling in place
2 | DYPQ.9L7 displacement Currently installed under MB.A9L7. To be displaced under MB.B8L7 | 9L7, 8L7 | X |  |  | It can be displaced and leave it installed there
3 | RYSA01 removal Rack installed at RR73. It will be replaced by the new RYABA01 (11T PC) | RR73 | X |  |  | RYSA01 is a rack where EPC has disconnected modules that serve as spares for the racks in that area; if there is a problem in a connected spare, they take out the module and replace by one that is in the RYSA rack.
4 | RYABA01 (11T PC) installation Plus the current leads cabling | RR73 | X |  |  | Activity to be performed at the RR, Independent from tunnel activities
5 | Water connection for 11T PC | RR73 | X |  |  | Activity to be performed at the RR, Independent from tunnel activities
6 | 2 crates for QDS and TRIM Units can be integrated between DYPG01 and DYPIB01 racks | RR73 | X |  |  | Activity to be performed at the RR, Independent from tunnel activities
7 | 2 DYPB racks for 11T installation - Under MB.B9L7 - Under MB.B10L7 Plus cabling going from the racks to the magnets and to the RR. | 9L7, 10L7 | X |  |  | Activity to be performed away from 11T cryostat. Cabling connected to the IFS can be installed till the 11T area
8 | 3BLMs for 11T magnets + 1BLM for TCLD | 9L7 |  | X |  | 
9 | Paint Limited Stay Areas on the floor (at the level of the non spring loaded valve in MB.A8L7) | 8L7 | X |  |  | 
10 | F3/F4 Electrical Boxes displacement Installed on cable trays in front of the MB.A9L7 (LBBRB.9L7) dipole. To be displaced by 3.5m towards the arc. | 9L7 | X |  |  | Check the cabling length of components with connections to those boxes (EN-EL)
11 | Re-route nQPS and BLM cables currently installed in a TELEX along the magnets (using L18A EC and L12A EC, respectiv.) | 9L7 |  |  | ? | Presently approved configuration is not compatible between 11T and stardand dipole. To check if it can be modified to make it compatible with both configurations
12 | 3 Coffrets Prise installation 4x10A monophase, 16A triphase, 32A triphase | 9L7 |  |  | X | At the foresee location, they might interfere if we later re-install the old dipole with the current racks. In any case, they should be installed after the 11T dipoles are in place.
13 | Water connections to the EDA/EDR pipes Installation of flexible pipes to the TCLD | 9L7 | X |  |  | It can be done and ready for use. It doesnt matter if in the end they are not used
14 | New racks for TCLD in the LHC galleries | TZ76 | X |  |  | Independent from tunnel activities. Cabling to be connected to the TCLD can be pulled from the racks and installed along the tunnel till the area
15 | 11T+TCLD jacks installation | 9L7 |  | X |  | Standard dipole jacks and new 11T+TCLD jacks are not compatible
11T expected activities – Infrastructure modif. compatibility
TCLD
TCLD
TCLD
TCLD
TCLD
TCLD

## Slide 7
Current dipole (LBBRB.9L7) vs Full 11T configuration
Jacks no compatible
1200
500
500
700
500
1000
Overlapping the 2 images
1200
700
500
1000
500
500

## Slide 8
Current dipole (LBARA.9R7) vs Full 11T configuration
Jacks no compatible
1200
500
500
1200
500
1000
1200
500
500
1200
500
1000
Overlapping the 2 images

## Slide 9
SPARE SLIDES

## Slide 10
Displacement of F3 and F4 Electrical Boxes

## Slide 11
Installation of new coffets prise

## Slide 12
Re-routing of current cables: nQPS and BLM cables in the telex placed along the magnets.
To check if the routing could be modified, to make it compatible with both 11T or dipole configurations

## Slide 13
Location of new 11T DYPB racks underneath the magnets

## Slide 14
Current MB.A9L7 (LBBRB.9L7) vs Full 11T configuration
Position of jacks and racks presently installed

## Slide 15
Current MB.A9R7 (LBARA.9R7) vs Full 11T configuration
Position of jacks and racks presently installed

## Slide 16
BLM layout

## Slide 17
Standard LHC dipole vs 11T assembly configuration
R7
L7
LHC C9R7
HL-LHC C9R7
LHC C9L7
HL-LHC C9L7
MB.A9R7 (LBARA.9R7)
MB.A9L7 (LBBRB.9L7)