## Slide 1: HL LHC Inner Triplet STRING Complement with functional , safety and risk analysis
M. Bajko
HL-LHC IT STRING Coordinator
International Review of HL-LHC Inner Triplet Circuits, 9-10th of September 2019

## Slide 2: HWC of the LHC
Verification of the Protection Interlocks
Configuration of the Power Converter
Verification of the Energy Extraction System at different current levels
Extract from a presentation of R. Saban on HWC of LHC

## Slide 3: Impact of the HL-LHC IT STRING on HWC of HL-LHC and availability of the machnine

## Slide 4: Delays for Start of Operation
Possibly absorbed by HWC (assuming HWC duration of 4-5 months):
  Setting up for controls aspects of IT circuit powering  ~1 month
  Setting up and optimization of protection controls e.g. QPS thresholds)  ~1 month
  Setting up of cryogenics controls and parameters  ~1 week
Extending beyond hardware commissioning:
  Solving problems related to new magnet protection strategy and related impact on other systems (e.g. cold and warm powering)  several months
  Solving problems with vacuum / beam instrumentation assembly  several months
  Solving problems with warm/cold powering system (SC link, DFH, DFX, energy recuperation, crowbars,…)  several months
  HL target: 250 fb-1 in 160 days of operation (~1.6 fb-1 / day), potential performance loss in the order of 100-150 fb-1 for any of the items above

## Slide 5: Potential Downtime for HL-LHC
Manual re-alignment (if remote alignment not working)  ~1 month (order of 50 fb-1)
Cross-talk between circuits:
  Possibly frequent trips of corrector/triplet circuits
  Limitations in the use of orbit feedback
  Possible limitations for ramp rates
  Induced downtime impossible to quantify, but could be a major limitation for operation
Quenches in SC links inducing magnet quenches, several h for recovery for each occurrence

## Slide 6
Potential Performance Limitations (Input WP2)
If remote alignment from Q1 to Q3 NOT working:
Correction bump limited to 1.2 mm instead of 2 mm (requested from experiments) due to limited strength in the correctors  reduction of aperture margins, impact on β* reach (only for flat optics)
Or manual re-alignment required, worst case 4-5 weeks (order of 50 fb-1)
  Frequency of re-alignment so far in LHC: 1/year, i.e. every YETS or LS
BPM stability, requirements from WP2: 10 µm from fill to fill, 30 µm over a run
If not achievable and machine stability worse than LHC  solution to be found  potentially impact on time to set-up collisions in every fill (to be assessed)
Triplet powering precision:
If regulation is significantly worse than specifications (e.g. due to flux jumps), new developments could be required to allow machine operability
STRING test would help WP6b to further verify the new class 0 precision on the IT main circuit
Handling of flux jumps is under investigation at the moment with individual powering tests, but additional understanding should be gained on the reaction of the nested circuit control to such events
Cold mass vibrations:
If 1-100 Hz ground motion and HL-LHC triplet transfer function not worse than LHC  no problem
Otherwise need for fast orbit feedback system to cope with vibrations (not in baseline, requiring special hardware)
Beam screen vibrations:
No problems expected (issues only if beam screen vibrates at tune frequency, 3 kHz and harmonics)
Eigen frequencies of beam screen (13 Hz for Q1-type, 20 Hz for Q2-type), no impact on field stability

## Slide 7: Conclusions on impact of IT STRING on Machine HWC and operation
Highest priority items based on potential impact on performance/availability are:
  Magnet protection: fundamental to test protection strategy in realistic operating conditions, including impact on all involved systems
  Cross-talk between circuits: assess impact ad potential limitations for operation
  SC links: performance in the presence of inductive load
  Powering: control strategy in realistic environment (e.g. handling of flux jumps)
  Fully remote alignment: performance could be critical for HL
One of the added values of the STRING is to address also ‘unknown unknowns’ (low probability, potentially high impact)

## Slide 8: Functional and safety analysis of the HL-LHC IT STRING

## Slide 9: Functional anlysis HL-LHC IT STRING
Projet HL LHC IT STRING
Level A0:
HL-LHC IT STRING test bench including all infrastrictures of SM18
Level A4: the HL-LHC test dench
Project HL-LHC IT STRING
HL-LHC IT STRING Including infrastructure of Sm18
HL-LHC IT STRING
Our study is on that level
Work in progress

## Slide 10: Niveau A4
Draft
Level A42:
Warm powering system

## Slide 11: Composition of the box of activity SADT (Structured Analysis and DesignTechnique)
A-0 | Projet HL LHC IT STRING |  |  |  | 
 | A0 | Valider le fonctionnement et les performances des composants du banc d’essai HL LHC IT STRING pour satisfaire les exigences du CERN |  |  | 
 |  | A1 | Délivrer un courant électrique |  | 
 |  | A2 | Distribuer de l’hélium liquide |  | 
 |  | A3 | Distribuer de l'eau déminéralisée |  | 
 |  | A4 | Tester les composants du banc d’essai HL LHC IT STRING |  | 
 |  |  | A41 | Faire dissiper l’énergie stockée dans la chaine d’aimant. | 
 |  |  | A42 | Alimenter en énergie électrique la chaine d'aimant RQX (Q1, Q2a, Q2b, Q3) Ajuster le courant électrique (Q1 & Q3) Injecter un courant sinusoïdal (Q1a) Alimenter en énergie électrique D1 Alimenter en énergie électrique SF (SuperFerric) HO Alimenter en énergie électrique les correcteurs 2kA Mesurer le courant de fuite à la terre et arrêter l’alimentation s’il dépasse un seuil | 
 |  |  | A43 | Protéger les aimants supraconducteurs et les équipements lors d’un Quench | 
 |  |  |  | A431 | Surveiller le circuit « boucle FPA » Initier l’ouverture des commutateurs d'extraction
 |  |  |  | A432 | Détecter un Quench
 |  |  |  | A433 | Chauffer les aimants avec des chaufferettes internes pour que sa résistance se propage rapidement et que l’énergie soit dissipée dans le plus grand volume possible.
 |  |  |  | A434 | Décharger du courant dans les bobines pour dissiper l’énergie
 |  |  | A44 | Acheminer l'énergie électrique des «Power Convecters» vers les aimants | 
 |  |  |  | A441 | Acheminer l'énergie électrique des PC vers les amenées de courant. Evacuer les calories des câbles pour maintenir les conditions de fonctionnement.
 |  |  |  | A442 | Acheminer l'énergie électrique des « Power Converters » vers DFH Faire la liaison électrique entre le câble supraconducteur HTS et le câble cuivre
 |  |  |  | A443 | Acheminer l'énergie électrique des câbles DSH (Sc Link) vers les câbles des amenées de courant. Assurer la T° des câbles (HTS et MgB2) et des amenées de courant.
 |  |  |  | A444 | Acheminer l'énergie électrique des câbles DFH vers les câbles DFX Assurer la T° des câbles MgB2
 |  |  |  | A445 | Acheminer l'énergie électrique des câbles DSH (Sc Link) vers les aimants. Produire un débit massique d'hélium gazeux pour refroidir et maintenir toute la chaine à T° cryogénique.
 |  |  | A45 | Permettre de distribuer Hélium | 
 |  |  | A46 | Etre alimenté en énergie dans les mêmes conditions que le tunnel du LHC | 
 |  | A5 | Superviser et gérer le banc de test IT STRING |  | 

## Slide 12
Données d’entrée
Données de sortie
Mécanismes du support de l’activité
Données de contrôle

## Slide 13: The Safety context for HL-LHC A new approach: The System Safety Assessment
The PSO office proposed to HSE:
Conventional safety requirements
UNIQUE document to reference the (conventional) rules
Editor: HSE
Hazard register
150+ hazards/dangerous situations
Matching with the Rules
Including Radioprotection
Editor: PSO
Adapted from T. Otto’s work for FCC
SSA
SSA
SSA
n System Safety Assessment forms
Editor: Workpackage engineer, w/PSO support
w/ customised hazard list
Courtesy: C.Gaignant

## Slide 14: Equipment safety for WP16
  SM18 String test : activity with major Safety implications
    Many components that are part of the WP16 SM18 string test are classified as equipment with “major Safety implications” by the CERN-HSE unit.
  This triggers a series of actions on the Project Safety Office side:
    Magnets, Cold powering, Warm powering, Cryogenics, Machine Protection:
      Each equipment is being assessed individually through the production of a System Safety Assessment (HL-LHC Baseline safety documentation) where a hazard register is established between a Project Office Safety Officer (N.Grada) and the WPE in charge (ex: R2E-HL-LHC-600A-10V)
    A specific risk assessment to study the collective behavior of the components, in the SM18 facility, is being written to complete the study (EDMS 2134341).
      This document will address HSE requirements to get the safety clearance for the String test
      The risk control measures defined will be SM18 specific.