## Slide 1: WP2: Planning for the CDR
4 December 2019 Neil Thompson, STFC

## Slide 2: Contents
Purpose and scope of the CDR
Contents
Production method
Schedule
Examples of other CDRs

## Slide 3: What is the purpose of a Conceptual Design Report?
To state the project goals
To justify and present a self-consistent description of the design choices made for each component of the facility
To make a convincing case that
  the facility design will meet the required output specification
  the feasibility and risk of the design choices is well understood
  remaining technical challenges are identified with a clear R&D path to overcoming them
To provide a cost estimate
What a Conceptual Design Report is not:
A detailed technical description of each system and subsystem.

## Slide 4
SECTION | SUB-SECTION | WPs | PREVIOUS RELEVANT REPORTS | REPORTS DUE AT SAME TIME AS CDR
1. Executive summary |  | 1,2 |  | D1.2 Production of a short monograph summarizing the Conceptual Design Report.
2. Introduction |  | 1,2 | All | 
3. Science Goals and Photon Output Requirements | 1. Summary of Science Case | 2 | D2.1 Report providing users requirements and FEL performance specification (M12) | 
 | 2. Photon Output Requirements | 2 | D2.1 Report providing users requirements and FEL performance specification (M12) | 
4. Systems design and Performance | 1. Facility Layout | 2,6 | D2.2 Report summarizing the FEL design with accelerator and undulator requirements (M24) | 
 | 2. Injector | 3 | D3.1 Evaluation report of the optimum e-gun and injector solution for the CompactLight CDR. (M18) D3.2 A review report on the bunch compression techniques and phase space linearization (M18) | D3.3 Design report of the injector diagnostics/beam manipulations based on Xband cavities D3.4 E-gun and injector Design Report with diagnostics and phase space linearizer
 | 3. RF Systems | 4 | D4.1 Computer code report for RF power unit design and cost optimization. (M18) | D4.2 Design report of the optimized RF unit D4.3 Report on RF unit design and fabrication
 | 4. Undulators | 5 | D5.1 A review report comparing the different technologies for the CompactLight undulator. (M18) | D5.2 Conceptual Design Report of the undulator
 | 5. Accelerator Lattice Design and FEL Performance | 6 | D6.1 Review report on the most advanced computer codes for the facility design (M18) | D6.2 Final report with start to end facility simulations
 | 6. Photon Beamlines and User Facilities | 2 |  | 
 | 7. Building and Site Considerations | 2 |  | 
5. Strategic Issues | 1. Global Integration | 7 | D7.1 Mid-term report with CompactLight global integration and cost analysis (M24) | 
 | 2. Cost Estimates | 7 | D7.1 Mid-term report with CompactLight global integration and cost analysis (M24) | 
 | 3. Technology Transfer | 7 |  | 
6. Appendices | 1. Institutes | 1 |  | 
 | 2. Publications | 1 |  | 

## Slide 5: CDR Production
  Each WP leader to be responsible for providing relevant material, as described in table on previous slide.
  As far as possible, material from any WP reports already produced as deliverables can be reused in the CDR.
  N.B. Those WP reports that are due at the same time as the CDR must be fully consistent with content provided for CDR.
We propose to compile the report in Latex, using Overleaf which has worked well so far for WP reports
  multiple collaborators can work on document simultaneously
  document history, Dropbox and GitHub sync
  no local Latex installation required

## Slide 6: CDR Production – Points to note
  Vector-based graphics files are strongly preferred to bitmap formats as they reproduce at full resolution irrespective of scaling.
To help obtain a uniform style, we propose the following guidelines
  We write about the CompactLight finished design in the present tense and in the third person. For example,
    we do say “the undulators for the hard X-ray beamline are superconducting helical devices with a 2mm aperture and a 4mm period”
    we don’t say “we decide that the undulators will be....”
  However, in discussing the process that led to the final design, we use the past tense and the third person. For example,
    we do say “a number of different technology options were evaluated”
    we don’t say “we consider a number of technology options”
  The idea is that this helps distinguish between the process of designing CompactLight and the final result and by presenting the finished design in the present tense it makes it seem ‘more real’
Process = past tense
Result = present tense
Always third person

## Slide 7: 2020 CDR Proposed Schedule
Date | Task/Milestone | Responsibility of..
January 16 | Complete document structure/subfiles/directories set up in Overleaf | WP2
September 30 | 1st complete draft which includes all material submitted by WP leaders | All
During October | Cross checking for consistency, errors and omissions | All
 | Layout editing, style editing, editing for consistency | WP2
October 31 | 1st complete edited draft. | WP2
During November | Corrections | WP2 + All
November 30 | 2nd complete edited draft | WP2
December 18 | Submission to EU (pre-Christmas) | WP1
January 2021 | Online publication (and printed copy?) once approved by EU. | WP1/2

## Slide 8: Examples of other FEL Facility CDRs
STFC CDRs
  4GLS
  NLS
  CLARA (compiled in Latex)
Other CDRs
  LCLS
  Fermi@Elettra
  SwissFEL
pdfs of all the above available on the WP2 Collaborative Workspace: https://espace.cern.ch/compactlight/WP2/