## Slide 1: SPS BPM system renovation
Status review
September 2019

## Slide 2: Outline
Status and planning in January Vs. today
Reviewed planning till the end of LS2
  Installation
  Development of the interlock system
  Dry runs
System performances as from the production batch

## Slide 3: Status and planning in January

## Slide 4: Status of the production today

## Slide 5: Status of the production today

## Slide 6: Status: Hairpin filters
350 at CERN: 100 paired and 50 pizza boxes assembled
100 to come by the end of September
150 expected in November
No impact of the 1st sextant installation
End of installation postponed to September from June

## Slide 7: Status: Hairpin filters
350 at CERN: 100 paired and 50 pizza boxes assembled
100 to come by the end of September
150 expected in November
No impact on the 1st sextant installation
End of installation postponed to September 2020 (was June)

## Slide 8: Status: Pizza Boxes
All the boxes produced and equipped with PS
50 fully assembled
Remaining ones waiting for hairpin filters….

## Slide 9: Status: Automated test bench
Hardware set up finalized but with some delays
Delay due to review of calibration procedures/fitting algorithms that have been just recently approved

## Slide 10: Status: Automated test bench
Hardware set up finalized but with some delays
Delay due to review of calibration procedures/fitting algorithms that have been just recently approved
No impact on production: 1st 50 can be manually tested

## Slide 11: From now to LS2 end: installation and dry runs

## Slide 12: Planning till the end of LS2
1st sextant installation by the end of 2019 (unchanged)
Dry runs can start Early 2020 (unchanged)
End of production delayed by 3 months (no impact on general planning)
  End of installation potentially moved to end of September 2020
  Full accelerator dry runs possible from October 2020
Interlock functionality implemented in the FPGA/FESA early 2020
  Test starting in spring 2020

## Slide 13: Planning till the end of LS2: dry runs
Sextant dry run : Jan-March 2020
  Validation of FESA JASP integration
  Validation of logging
  Validation of the various acquisition modes
    FIFO
    Injection trajectory
    Orbit
    Trajectory
Interlock tests: May-June 2020
  Validation of the BIS connections
Full SPS dry run : October-December 2020
  Points synchronization
  Full data logging

## Slide 14: What we can emulate in dry runs

## Slide 15: Performances as from the production batch

## Slide 16: Calibration procedure and limits

## Slide 17: Calibration procedure and limits
Single bunch
5ns train
ADC counts

## Slide 18: Multi bunch: results (5ns)
1e9
1e10
1e11
1e9
1e10
1e11
10mm displacement
2mm displacement

## Slide 19: Multi bunch: results (25ns)
1e9
1e10
1e11
1e9
1e10
1e11

## Slide 20: Multi bunch: results (50ns)
1e9
1e10
1e11
1e10
1e11
1e9

## Slide 21: Multi bunch: results (75ns)
1e9
1e10
1e11
1e10
1e11
1e9

## Slide 22: Single bunch: results
1e9
1e10
1e11
1e9
1e10
1e11

## Slide 23: Performances summary
1e10
1e10

## Slide 24: Performances summary
Intensity dependent systematics
  <250um for small displacements (less than 5mm)
  <1mm for big displacements (10mm plus)
Expected Resolution:
  Single bunch
    turn by turn: 500-700um
    Orbit @1ms : ~100um
  Trains (72 bunches @25ns):
    turn by turn: 50-80um
    Orbit @1ms : ~15um