## Slide 1: GE2/1 chambers: design, prototypes, production readiness and production schedule
LUIGI BENUSSI
GEM WORKSHOP
September 24, 2019

## Slide 2: Overview
GE2/1 Project Status
  Updates since EDR
  Integration tests with prototypes
    Mechanical tests
    Electronics Integration
  Production overview
    Production Readiness and Planning
    Risk Management
  Summary

## Slide 3: GE2/1 Project Overview
GE2/1 station consists of 36 20o chambers
Same technical solution as for GE1/1
Two independent GE2/1 chambers will form on the YE1/1 disk a Super Chamber

## Slide 4: GE2/1 Chambers Layout
With a single layer, the average acceptance × efficiency would be reduced to 92% due to gaps.
To achieve maximum coverage, modules in front and back chambers will be staggered.
As a consequence, eight different types of modules will be
designed and produced.
Front Chamber Hit Efficiency
Back Chamber Hit Efficiency
Super Chamber Hit Efficiency (OR)
M1
M2
M3
M4
Back Chamber
M5
M6
M7
M8
Front Chamber
I.P.
GE2/1 Superchamber
35.5 mm
35.5 mm
35.5 mm
longer
shorter
M8/M4
M7/M3
M6/M2
M5/M1
Front Chamber
Back Chamber
8 GE2/1 Triple-GEM Modules

## Slide 5: GE2/1 Mechanical test
Two GE2/1 chambers forming a Super Chamber fully assembled, tested and mechanically integrated
Mechanics for chamber installation validated in situ

## Slide 6: GE2/1 Electronics Integration
GE2/1 M1-M4 prototype modules with all mezzanine components are produced and integrated
Ultimate grounding scheme identified with the noise level under 0.6fC

## Slide 7: GE2/1 R&D Steps to Completion
Complete GEB boards M6-M8
  Timeline: by the end of 2019
Minor adjustments and optimization of OptoHybrid and select GEB boards to correct small mechanical issues
Validate packaged VFAT3 chips
Optimize VFAT3 chip protection and manufacture PlugIn Cards
  PlugIn Cards design is almost ready, await for pinout confirmation from manufacturer
Integrate and test, including proof of principle with ATCA backend
  ATCA backend ordered, estimated delivery: Nov. 2019

## Slide 8: GE2/1 Production Readiness
Central Site at CERN
Vendors
Production Sites

## Slide 9: GE2/1 Production Readiness
Components used in GE2/1 are almost identical to GE1/1
  Vendors are already identified
Small mechanics and electrical components are produced by international companies (e.g. Bossard)
  Minimal risk of failure or production delay
Drift and Readout boards: Micropack
  Experience from GE1/1 Production: ~100% yield, in time delivery
Frames: Eltos
  Experience from GE1/1 Production: >93% yield, in time delivery
Central Site at CERN
Vendors
Production Sites

## Slide 10: GE2/1 Production Readiness
Central Site at CERN
Vendors
Production Sites
Pre-production activities (central site at CERN)
  Reception or materials
  Initial inspection and acceptance test (approval/rejection of materials)
    Optical inspections
    Groove measurement on external frames
    PCB bending measurements
    RO board connectivity test
  GEM QC2 fast and long tests at CERN
Material preparation
  Coating of the internal/external frames (+ spacers)
  Sorting of the O-rings
  GEM foil packing
  GE2/1 kit preparation
List of tasks is well defined
Manpower requirements and responsibilities are clear
Work plan is established with the production community

## Slide 11: GE2/1 Production Readiness
Central Site at CERN
Vendors
Production Sites
List of items is well defined
Design is 80% completed
Work plan is established with the production community
Specific Tooling for GE2/1 Module Assembly
(adaptors and tools to make GE1/1 production sites compatible with the GE2/1 design)
  Assembly Jig with Alignment Pins
  Protective Plate
  Grounding Plate
  Fixation Bars
  HV Clips for QC2
  Adaptor PCB for QC4/QC5
Material Transport
  Shipment Boxes
GE2/1 Assembly Jig
GE2/1 Shipment box

## Slide 12: GE2/1 Production Readiness
Site | Nb of Production lines | Certified for GEM Production | Infrastructure ready and tested | Team | Comments
Belgium | 1 | YES | YES | 2 Physicists 3 Technicians | Produced 30 GE1/1 detectors
Germany | 1* | YES | YES | 4 Physicists | *QC only (no clean room) Tested 21 GE1/1 det.
Italy | 2 | YES | YES | 8 Physicists 8 Technicians +Students | Produced 26 GE1/1 detectors
India | 2 (+2 under approval) | YES (+2 on-going) | YES (+2 on-going) | 8 Physicists 5 Engineers/Tech + Students | Produced 17 GE1/1 detectors
Pakistan | 1 | YES | YES | 4 Physicists 8 Engineers/Tech | Produced 13 GE1/1 detectors
Sri-Lanka | 1 | YES | YES | 4 Physicists 1 Engineer + Students | Using CERN infrastructure and tooling
China | 1 | On-going | On-going | 3 Physicists 2 Engineer + Students | New site, QC Jamboree in progress
New sites
Central Site at CERN
Vendors
Production Sites

## Slide 13: GE2/1 Production Readiness
Central Site at CERN
Vendors
Production Sites
Sri-Lanka (UOC and UOR)
  Strong team already involved in the GE1/1 production (test, operation and analysis)
  Will use the CERN infrastructure to assemble and test GE2/1 modules
  Participated in 6 training sessions
  Approved for GE2/1 mass-production
China (PKU)
  Strong group already experienced with gaseous detectors and small GEM chambers
  Infrastructure 90% ready
  1st stage of the QC Jamboree about to be completed (out of three stages)
  Participated in CERN training
  Full Approval is expected during Fall 2019
Two New Production Sites for GE2/1
Sri-Lanka team at CERN
China PKU

## Slide 14: GE2/1 Production Planning
GE2/1 Module Production (TDR dates)
  Baseline schedule with 4 production sites, each one assembling two types of modules
  Production organized in batches of 6 modules every 10 weeks (including 1 week for shipping)
  Start of the production in October 2019, end in April 2022 (662 working days)

## Slide 15: GE2/1 Production Schedules
Small Mechanics and Electrical Components

## Slide 16: GE2/1 Production Schedules
PCBs: 304 Readout and Drift Boards

## Slide 17: GE2/1 Production Schedules
Frames: 304 External/ 304 internal kits

## Slide 18: Risk Management
Case I: unavailability of detector components
Late delivery of components
  Risk: medium
High rejection rate – components outside specifications
    Risk: medium (GEM foils – new vendor)

## Slide 19: Risk Management
Case II: failure at production sites
Assembly/test rate slower than expected
  Risk: low (based on GE1/1 experience)
One or several sites not ready for mass-production
  Risk: low (already 7 sites approved out of 4 needed)
Main risks are related to detector components but the GE1/1 experience gives good confidence and knowledge to anticipate possible delays

## Slide 20: Risk Management
Country | Nb of Prod. lines | Module types | Nb of Modules | Comments
Italy | 2 | M6 + M8 | 38 (M6) + 38 (M8) | 
Belgium | 1 | M3 +M1 | 38 (M3) + 19 (M1) | 
Germany | 1* | M1 | - | *QC only
India | 2 | M2 | 38 (M2) | 
China | 1 | M5 | 38 | To be approved
Sri-Lanka | 1 | M4 + M1 | 38 (M4) +19 (M1) | 
Pakistan | 1 | M7 | 38 | 
M1
M2
M3
M4
M5
M6
M7
M8
Layer 1
Layer 2
Similar to GE1/1 size
Sharing of the module production over 8 production sites
Each production line is assigned one type of GE2/1 modules
38 modules/line
Belgium and Sri-Lanka will produce extra 19 modules, each to be tested in Germany
Demonstrated capability to produce large size GE1/1 at high rate (~3 days per module)
Proximity of CERN experts and large infrastructure capacity

## Slide 21: Summary
GE2/1 and RnD and prototyping progressing very fast
Change control performed for GE2/1 optical transceivers
  We are back on track with schedule with a minimal delay
  Given a new need-by date we have solid floating time
GE2/1 prototype is fully integrated and efficiency studies are ongoing
Production schedule is well established and production process is under control

## Slide 22: Backup

## Slide 23: GE2/1 Production Schedules
Central Site at CERN
Vendors
Production Sites
Small Mechanics and Electrical Components

## Slide 24: GE2/1 Production Schedules
Central Site at CERN
Vendors
Production Sites
PCBs: 304 Readout and Drift Boards

## Slide 25: GE2/1 Production Schedules
Central Site at CERN
Vendors
Production Sites
Frames: 304 External/ 304 internal kits

## Slide 26: ME0 Design
Mechanical Design
  HGCAL Envelope has been frozen
    Space for ME0 stack insertion confirmed
  HGCAL fixation points to HE back flange not yet finalized
    May require special design of two stacks per Endcap at 3 and 9 o’clock
    Discussion and studies on-going

## Slide 27: ME0 Design
Electronics Design
  FPGA-less on-chamber electronics design is ready
    Prototypes produced
      ASIAGO (ME0 OptoHybrid board)
      PIZZA (Special board to place ASIAGO over GE2/1 GEB)
      Adapter for FireFly transceivers until Vlplus aren’t available
    Integration started using GE2/1 detector
    Communication between LpGBT and VFAT chips is established!

## Slide 28: ME0 Detector Prototypes
Reduced space under the chamber cover
Foils with double face segmentation layout choosen
9 prototype modules production launched at CERN

## Slide 29: ME0 Aging Studies at GIF++
Total integrated Charge at GIF++ up to 22nd March: ~ 218 mC/cm2
Chamber CERN GEM Foils
Total integrated Charge at GIF++ up to 22nd March: ~ 82 mC/cm2
137Cs Source
Chamber Korean GEM Foils

## Slide 30: ME0 Milestones from TDR
Up to the start of the construction project
Achieved
Achieved
Achieved
Achieved
Delayed till 14.01.2020
Expect on-time
Expect on-time
Expect on-time
Expect on-time
Expect on-time
Projected on-time | 
Projected on-time | 
Projected on-time | 

## Slide 31: Electronics R&D Schedule
The “waterfall” plot for the updated R&D schedule
Ready for ESR (LpGBT): Aug. 21 2020
Ready for ESR (GBTX): Apr. 3 2020