## Milestones
Version 3.0 | 2019-09-09 |  | EDMS: 2112813
Machine | Due date | Topic | Responsible | Technical Coordination | Beam Commissioning WG | Beam Dynamics WG | Comm. Coordination | Beam Dyn. Coordination | Status | Details
Beam Dynamics Coordination | 2020-12-01 | Document the options and left-overs from post LS2 to prepare for future deployment including the check-points and timelines | LIU Beam Dyn. Coordinator |  |  |  |  | X
Commissioning Coordination | 2019-03-29 | Switchyard opening/closure: Identify best option with all experts involved | LIU Comm. Coordinator |  |  |  | X |  | Done | Planning defined in the CCC: access to switchyard before and after LN4 LBE run, https://indico.cern.ch/event/803331/
Commissioning Coordination | 2019-03-31 | IST Definition | LIU Comm. Coordinator |  |  |  | X |  | Done
Commissioning Coordination | 2019-04-30 | Planning tool: Discuss ASM vs. EN/ACE tool | LIU Comm. Coordinator |  |  |  | X |  | Done | EN-ACE tool will not be used for commissioning scheduling - other solutions to be found
Commissioning Coordination | 2020-03-01 | Check lists: Upgraded version | LIU Comm. Coordinator |  |  |  | X
Commissioning Coordination | 2019-06-01 | HWC and dry runs planning: LBE line LINAC4; with check lists | LIU Comm. Coordinator |  |  |  | X |  | Done
Commissioning Coordination | 2019-07-01 | Reference measurements: Final feedback. First version of viewer What is the future of it? | LIU Comm. Coordinator |  |  |  | X |  | Done | https://indico.cern.ch/event/824431/
Commissioning Coordination | 2019-07-01 | Injector schedule: First version | LIU Comm. Coordinator |  |  |  | X |  | In progress | Rende is putting together the information provided by CCC
Commissioning Coordination | 2019-08-01 | Switch yard opening/closure: Final iteration pending decision on POPS capacitors | LIU Comm. Coordinator |  |  |  | X |  | Done
Commissioning Coordination | 2019-09-01 | Planning by EN-ACE + OP: final IST lists and conditions (shifts/no shifts, access system SPS, CV availability, …) | LIU Comm. Coordinator |  |  |  | X |  | In progress
Commissioning Coordination | 2019-10-01 | Feedback from LBE run HWC: lessons learned and consequences for 2020 start-up (planning, updates on check-lists, sufficient preparation for beam commissioning?) | LIU Comm. Coordinator |  |  |  | X
Commissioning Coordination | 2019-11-01 | Beam commissioning details: Experts shifts and piquets start dates | LIU Comm. Coordinator |  |  |  | X
Commissioning Coordination | 2019-12-01 | Performance tracking: Requirements and possible implementation | LIU Comm. Coordinator |  |  |  | X |  | In progress
Commissioning Coordination | 2019-12-01 | HWC for the rest of the complex | LIU Comm. Coordinator |  |  |  | X
Commissioning Coordination | 2019-12-01 | Injector schedule: Refined version | LIU Comm. Coordinator |  |  |  | X
Commissioning Coordination | 2019-12-01 | Christmas shutdown 2020 plan: Critical items; strategy for rapid start-up in January 2021 | LIU Comm. Coordinator |  |  |  | X
Commissioning Coordination | 2019-12-01 | Functional specification of the post-LS2 power converters interlocks | LIU Comm. Coordinator |  |  |  | X
Commissioning Coordination | 2020-02-01 | Beam commissioning details: Resource-loaded planning | LIU Comm. Coordinator |  |  |  | X
Commissioning Coordination | 2020-03-01 | Beam commissioning details: Cross-machine interdependencies | LIU Comm. Coordinator |  |  |  | X
LIU-IONS PS injectors | 2019-03-31 | Linac3 LLRF specification - under L3 RF CONS | LIU Machine Tech. Coordinator | X |  |  |  |  | Done | The LLRF document approval (Functional Specification and Engineering Design Report https://edms.cern.ch/ui/#!master/navigator/document?D:100328658:100328658:subDocs, https://edms.cern.ch/ui/#!master/navigator/document?D:100329287:100329287:subDocs) was reviewed at an RF meeting last week. It is agreed with modifications, which are being implemented.
LIU-IONS PS injectors | 2019-04-01 | Integration of LIU systems: prepare lists of new systems to be integrated Definition of integration meetings with equipment groups if required | LIU Machine Comm. WG Leader |  | X |  |  |  | Done | Presented at the CCC: https://indico.cern.ch/event/817498/contributions/3412990/attachments/1837942/3012420/Linac3_LEIR_status_NB_RS_RA.pdf
LIU-IONS PS injectors | 2019-06-01 | Identification of software needs | LIU Machine Comm. WG Leader |  | X |  |  |  | Done | https://indico.cern.ch/event/825719/
LIU-IONS PS injectors | 2019-06-01 | Performance tracking: Definition of observables to be tracked | LIU Machine Comm. WG Leader |  | X |  |  |  | Done | Presented at https://indico.cern.ch/event/833199/ and https://indico.cern.ch/event/841490/
LIU-IONS PS injectors | 2019-06-01 | Status of source solenoids verification from MSC and plans for spares | Frederic Wenander (Detlef Kuchler) |  |  | X |  |  | Done | MSC decided to use present solenoid type to build a spare possibly with improvements
LIU-IONS PS injectors | 2019-06-01 | Analyse used foils status | Edgar Mahner |  |  | X |  |  | In progress | Visit to GSI foreseen for September
LIU-IONS PS injectors | 2019-06-01 | Effect of energy ramping on inj. Efficiency | Richard Scrivens |  |  | X |  |  | In progress | update presented at: https://indico.cern.ch/event/832065/
LIU-IONS PS injectors | 2019-06-01 | Machine models availability: impedance, aperture - optics (MADX) | Angela Saa Hernandez, Nicolò Biancacci |  |  | X |  |  | Done | presented at: https://indico.cern.ch/event/816834/
LIU-IONS PS injectors | 2019-06-01 | Summary of understanding of IBS, SC effects and impedance in LEIR | Nicolò Biancacci, Angela Saa Hernandez |  |  | X |  |  | Done | https://indico.cern.ch/event/816834/
LIU-IONS PS injectors | 2019-06-01 | Stray fields compensation, define process. | Nicolò Biancacci |  |  | X |  |  | Done | presented at: https://indico.cern.ch/event/816834/
LIU-IONS PS injectors | 2019-06-30 | Injection BPMs (design, boards, FESA) | Michele Bozzolan | X |  |  |  |  | Done | presented at: https://indico.cern.ch/event/838898/
LIU-IONS PS injectors | 2019-07-01 | Establish lists of ISTs in collaboration with equipment groups | LIU Machine Comm. WG Leader |  | X |  |  |  | In progress | presented at: https://indico.cern.ch/event/824431/
LIU-IONS PS injectors | 2019-07-01 | Injector schedule: list of beam readiness and FT facility start-up dates: first iteration | LIU Machine Comm. WG Leader |  | X |  |  |  | Done | presented at: https://indico.cern.ch/event/839130/
LIU-IONS PS injectors | 2019-11-28 | Linac3 Ventilation | Richard Scrivens, Roberto Bozzi | X
LIU-IONS PS injectors | 2019-08-01 | FESA class readiness dates | LIU Machine Comm. WG Leader |  | X |  |  |  | Done | presented at https://indico.cern.ch/event/844660/
LIU-IONS PS injectors | 2019-11-01 | EN-ACE + OP: final IST lists and conditions | LIU Machine Comm. WG Leader |  | X
LIU-IONS PS injectors | 2019-12-01 | Injector schedule: list of beam readiness and FT facility start-up dates: refined version | LIU Machine Comm. WG Leader |  | X
LIU-IONS PS injectors | 2019-12-01 | HWC planning for the rest of the complex(apart LBE) | LIU Machine Comm. WG Leader |  | X
LIU-IONS PS injectors | 2019-12-01 | Christmas shutdown 2020/21: critical items, piquet requirements, equipment state... | LIU Machine Comm. WG Leader |  | X
LIU-IONS PS injectors | 2019-12-31 | Modelling of effect of foil degradation (mean energy error) | Richard Scrivens |  |  | X
LIU-IONS PS injectors | 2019-12-31 | Ecooler - Effect of current intensity (sim vs meas.) | Andrea Latina |  |  | X
LIU-IONS PS injectors | 2020-02-01 | Detailed beam commissioning planning with resources | LIU Machine Comm. WG Leader |  | X
LIU-IONS PS injectors | 2020-06-30 | Linac3 LLRF Ready - under L3 RF CONS | Daniel Valuch | X
LIU-IONS PS injectors | 2020-12-01 | Document the stock of spares available after LS2 | LIU Machine Tech. Coordinator | X
LIU-IONS PS injectors | 2020-12-31 | Test thicker foils | Giulia Bellodi (Richard Scrivens, Edgar Mahner) |  |  | X
LIU-IONS PS injectors | 3 months before HWC start | HWC check lists | LIU Machine Comm. WG Leader |  | X
LIU-PS | 2019-04-01 | Integration of LIU systems: prepare lists of new systems to be integrated Definition of integration meetings with equipment groups if required | LIU Machine Comm. WG Leader |  | X |  |  |  | In progress | To be presented at the CCC: https://indico.cern.ch/event/819356/
LIU-PS | 2019-06-01 | Performance predictions for LS2 RF upgrades | BE-RF |  |  | X |  |  | Done | https://indico.cern.ch/event/833548/
LIU-PS | 2019-06-01 | Identification of software needs | LIU Machine Comm. WG Leader |  | X |  |  |  | Done | presented at https://indico.cern.ch/event/821925/
LIU-PS | 2019-06-01 | Performance tracking: Definition of observables to be tracked | LIU Machine Comm. WG Leader |  | X |  |  |  | Done | Presented at https://indico.cern.ch/event/830277/ and https://indico.cern.ch/event/841490/
LIU-PS | 2019-07-01 | Establish lists of ISTs in collaboration with equipment groups | LIU Machine Comm. WG Leader |  | X |  |  |  | In progress
LIU-PS | 2019-07-01 | Injector schedule: list of beam readiness and FT facility start-up dates: first iteration | LIU Machine Comm. WG Leader |  | X |  |  |  | Done | presented at https://indico.cern.ch/event/839130/
LIU-PS | 2019-08-01 | FESA class readiness dates | LIU Machine Comm. WG Leader |  | X |  |  |  | In progress | to be presented in the CCC meeting on 20 September
LIU-PS | 2019-09-01 | Longitudinal impedance source identification | BE-RF |  |  | X
LIU-PS | 2019-09-01 | Define energy at intermediate plateau for LHC beams | BE-RF |  |  | X |  | X
LIU-PS | 2019-11-01 | EN-ACE + OP: final IST lists and conditions | LIU Machine Comm. WG Leader |  | X
LIU-PS | 2019-12-01 | 2 GeV injection Space charge simulations to validate tune spread scaling | BE-ABP, TE-ABT |  |  | X
LIU-PS | 2019-12-01 | PS microwave instability (ions) | BE-RF, BE-ABP |  |  | X
LIU-PS | 2019-12-01 | Longitudinal instability simulations / benchmarking | BE-RF |  |  | X
LIU-PS | 2019-12-01 | Investigate horizontal blow-up with large longitudinal emittance | BE-ABP, TE-ABT |  |  | X
LIU-PS | 2019-12-01 | Flat top horizontal instabilities (e-cloud) | BE-ABP, BE-RF |  |  | X
LIU-PS | 2019-12-01 | Injector schedule: list of beam readiness and FT facility start-up dates: refined version | LIU Machine Comm. WG Leader |  | X
LIU-PS | 2019-12-01 | HWC planning for the rest of the complex(apart LBE) | LIU Machine Comm. WG Leader |  | X
LIU-PS | 2019-12-01 | Christmas shutdown 2020/21: critical items, piquet requirements, equipment state... | LIU Machine Comm. WG Leader |  | X
LIU-PS | 2020-02-01 | Detailed beam commissioning planning with resources | LIU Machine Comm. WG Leader |  | X
LIU-PS | 2020-06-01 | Review longitudinal parameters at PS-SPS transfer | BE-RF |  |  |  |  | X
LIU-PS | 2020-06-01 | Longitudinal instabilities with small longitudinal emittance (PS-SPS transfer) | BE-RF |  |  | X |  | X
LIU-PS | 2020-12-01 | Document the stock of spares available after LS2 | LIU Machine Tech. Coordinator | X
LIU-PS | 3 months before HWC start | HWC check lists | LIU Machine Comm. WG Leader |  | X
LIU-PSB | 2019-03-01 | Prepare tool to optimize alignment of all rings after LS2 | BE-ABP |  |  | X |  |  | Done | Presented at the Liu-PSB-BD: https://indico.cern.ch/event/819016/
LIU-PSB | 2019-04-01 | Integration of LIU systems: prepare lists of new systems to be integrated Definition of integration meetings with equipment groups if required | LIU Machine Comm. WG Leader |  | X |  |  |  | Done | Presented at the CCC: https://indico.cern.ch/event/819356/
LIU-PSB | 2019-06-01 | Need for longitudinal painting for MTE/ISOLDE | BE-ABP, TE-ABT, BE-RF |  |  | X |  | X | Done | No need for longitudinal painting to reach pre-LS2 performance of ISOLDE beams. Presented at https://indico.cern.ch/event/835600/
LIU-PSB | 2019-06-01 | Identification of software needs | LIU Machine Comm. WG Leader |  | X |  |  |  | Done | Presented at https://indico.cern.ch/event/839130/
LIU-PSB | 2019-06-01 | Performance tracking: Definition of observables to be tracked | LIU Machine Comm. WG Leader |  | X |  |  |  | Done | Presented at https://indico.cern.ch/event/830277/ and https://indico.cern.ch/event/841490/
LIU-PSB | 2019-07-01 | Establish lists of ISTs in collaboration with equipment groups | LIU Machine Comm. WG Leader |  | X |  |  |  | Done | The IST were presented at the LIU-PSB TCM, https://indico.cern.ch/event/813464/
LIU-PSB | 2019-07-01 | Injector schedule: list of beam readiness and FT facility start-up dates: first iteration | LIU Machine Comm. WG Leader |  | X |  |  |  | Done | Presented at https://indico.cern.ch/event/819356/
LIU-PSB | 2019-08-01 | FESA class readiness dates | LIU Machine Comm. WG Leader |  | X |  |  |  | Done | The presentation is at https://indico.cern.ch/event/844660/
LIU-PSB | 2019-08-01 | Detailed planning SWY co-activities | BE-OP | X |  |  | X |  | In progress
LIU-PSB | 2019-09-01 | Production scheme low intensity beams | BE-RF, BE-OP |  | X | X |  | X | In progress
LIU-PSB | 2019-11-01 | EN-ACE + OP: final IST lists and conditions | LIU Machine Comm. WG Leader |  | X |  |  |  | In progress
LIU-PSB | 2019-12-01 | Longitudinal stability with Finemet | BE-RF |  |  | X
LIU-PSB | 2019-12-01 | Confirm that transverse damper cures instability from kicker impedance | BE-ABP, BE-RF |  |  | X
LIU-PSB | 2019-12-01 | Preparation of list of spares | BE-OP | X |  |  |  |  | In progress | The current list of spares is available https://edms.cern.ch/document/2086996/0.1
LIU-PSB | 2019-12-01 | Detailed planning for IST, HW commissioning | BE-OP, EN-ACE | X |  |  | X |  | In progress
LIU-PSB | 2019-12-01 | Propose strategy for winter break 2020/2021 | BE-OP | X |  |  | X
LIU-PSB | 2019-12-01 | Injector schedule: list of beam readiness and FT facility start-up dates: refined version | LIU Machine Comm. WG Leader |  | X
LIU-PSB | 2019-12-01 | HWC planning for the rest of the complex(apart LBE) | LIU Machine Comm. WG Leader |  | X
LIU-PSB | 2019-12-01 | Christmas shutdown 2020/21: critical items, piquet requirements, equipment state... | LIU Machine Comm. WG Leader |  | X
LIU-PSB | 2019-12-01 | Production scheme LHC | BE-RF, BE-OP |  | X | X |  | X | In progress
LIU-PSB | 2020-02-01 | Detailed beam commissioning planning with resources | LIU Machine Comm. WG Leader |  | X
LIU-PSB | 2020-03-01 | Brightness curve for LHC beams | BE-ABP |  |  | X |  | X
LIU-PSB | 2020-04-01 | WP optimization | BE-ABP |  | X | X
LIU-PSB | 2020-04-01 | Production scheme all beams | BE-RF, BE-OP |  | X | X |  | X
LIU-PSB | 2020-08-01 | Validate KFA14 kicker impedance reduction measures | BE-ABP |  |  | X
LIU-PSB | 2020-12-01 | Document the stock of spares available after LS2 | LIU Machine Tech. Coordinator | X
LIU-PSB | 3 months before HWC start | HWC check lists | LIU Machine Comm. WG Leader |  | X
LIU-SPS | 2019-03-13 | Decision on QD/MBB aperture improvement | LIU SPS JTL | X |  |  |  |  | Done | The improved flanges will be installed and quality control is needed to ensure correct installation, strategy under definition
LIU-SPS | 2019-03-13 | Final TI2 BLM shielding from new TCDIL locations | LIU SPS JTL | X |  |  |  |  | Done | Presented at the LIU-SPS-TCM: https://indico.cern.ch/event/808336/, New shielding designed, ordered and integration complete
LIU-SPS | 2019-03-27 | Collimation system wrap-up, including analysis of TIDP robustness | LIU SPS JTL | X |  |  |  |  | Done | Presented at the LIU-SPS-TCM: https://indico.cern.ch/event/813430/; functional specification of primary scraper to be provided by OP for precise cost estimate from EN-STI
LIU-SPS | 2019-03-27 | Follow up of missing LS2 documentation (ECRs, safety documents) | LIU SPS JTL | X |  |  |  |  | In progress | https://indico.cern.ch/event/808336/
LIU-SPS | 2019-03-27 | Proposed plans for including electrical circuits in Layout DB | LIU SPS JTL | X |  |  |  |  | In progress | Waiting decision from management
LIU-SPS | 2019-04-01 | Finish off injection interlocking and interface to powering systems | LIU SPS JTL | X | X |  |  |  | Done | Presented at the LIU-SPS-TCM: https://indico.cern.ch/event/809651/, MKP discharge time only open point
LIU-SPS | 2019-04-01 | Integration of LIU systems: prepare lists of new systems to be integrated Definition of integration meetings with equipment groups if required | LIU SPS JTL |  | X |  |  |  | Done | Presented at the CCC: https://indico.cern.ch/event/817498/contributions/3412993/attachments/1837949/3012014/05_integration.pptx
LIU-SPS | 2019-04-10 | Review of risk analysis for installation with technical input from groups | LIU SPS JTL | X |  |  |  |  | In progress | Templates ready, working on BI as test case. Presented at LIU Executive Committee meeting: https://indico.cern.ch/event/811955/
LIU-SPS | 2019-04-10 | Review 200 MHz SSPA production follow up | BE-RF | X |  |  |  |  | Done | Presented at the LIU-SPS-TCM: https://indico.cern.ch/event/813430/ On Track
LIU-SPS | 2019-10-01 | Review margins in shutdown planning from CE (or EN/ACE in SDC?) | LIU SPS JTL | X | [5 empty] | Possible when phase I of CE finished (tunnel breakout)
LIU-SPS | 2019-04-24 | Proposed strategy for quadrupole jacks | LIU SPS JTL | X |  |  |  |  | Done | Decided (all jacks to be replaced and local radial smoothing), presented at LIU-SPS-TCM https://indico.cern.ch/event/809651/
LIU-SPS | 2019-07-01 | Review performance MKDV switch | LIU SPS JTL | X | X
LIU-SPS | 2019-05-01 | RF parameter tree for voltage program with new voltage partitioning connected to RF mock interface | LIU SPS JTL |  | X |  |  |  | In progress
LIU-SPS | 2019-05-22 | BD input for decision on installation of 630 MHz HOM damper | BE-RF | X |  | X |  |  | Done | Baseline decided in LIU-SPS TC 28/8/19, https://indico.cern.ch/event/843573/
LIU-SPS | 2019-06-01 | LLRF application refactoring – decision Java vs. Python | LIU SPS JTL |  | X |  |  |  | In progress
LIU-SPS | 2019-06-01 | Identification of software needs | LIU SPS JTL |  | X |  |  |  | Done | presented at https://indico.cern.ch/event/817498/
LIU-SPS | 2019-06-01 | Performance tracking: Definition of observables to be tracked | LIU SPS JTL |  | X |  |  |  | Done | Presented at https://indico.cern.ch/event/833199/ and https://indico.cern.ch/event/841490/
LIU-SPS | 2019-06-19 | Review 200 MHz overall progress, including 200 MHz HOM decision | LIU SPS JTL | X |  | X |  |  | Done
LIU-SPS | 2019-09-20 | Review ALPS electronics production follow-up | LIU SPS JTL | X
LIU-SPS | 2019-07-01 | FEI implementation – test bed LINAC4 | LIU SPS JTL | X | X |  |  |  | In progress | Tests started
LIU-SPS | 2019-07-01 | Establish lists of ISTs in collaboration with equipment groups | LIU SPS JTL |  | X |  |  |  | In progress
LIU-SPS | 2019-07-01 | Injector schedule: list of beam readiness and FT facility start-up dates: first iteration | LIU SPS JTL |  | X |  |  |  | Done
LIU-SPS | 2019-08-01 | FESA class readiness dates | LIU SPS JTL |  | X |  |  |  | In progress | Still waiting clarification for some groups
LIU-SPS | 2019-09-01 | Update the Functional Specifications for the SPS scrapers with use cases depending on the number of LHC fills per day during the HL-LHC | BE-OP | X |  |  |  |  | Done
LIU-SPS | 2019-11-01 | EN-ACE + OP: final IST lists and conditions | LIU SPS JTL |  | X
LIU-SPS | 2019-12-01 | Beam loss on FB/ start ramp + feasibility of smaller longitudinal emittance | BE-RF | X |  | X |  | X
LIU-SPS | 2019-12-01 | Horizontal instability - first results on source + possible mitigations | BE-ABP |  |  | X
LIU-SPS | 2019-12-01 | Impact of bunch-by-bunch tune shift on tune footprint of bunches | BE-ABP |  |  | X
LIU-SPS | 2019-12-01 | Beam information distribution – come up with a concept and implementation | LIU SPS JTL | X | X
LIU-SPS | 2019-12-01 | LLRF cavity control ready | LIU SPS JTL | X | X
LIU-SPS | 2019-12-01 | Impedance impact of 200 MHz cavities for eSPS on proton beam stability | LIU SPS JTL
LIU-SPS | 2019-12-01 | Injector schedule: list of beam readiness and FT facility start-up dates: refined version | LIU SPS JTL |  | X
LIU-SPS | 2019-12-01 | HWC planning for the rest of the complex(apart LBE) | LIU SPS JTL |  | X
LIU-SPS | 2019-12-01 | Christmas shutdown 2020/21: critical items, piquet requirements, equipment state... | LIU SPS JTL |  | X
LIU-SPS | 2019-12-04 | ALPS electronics test deployment follow-up | LIU SPS JTL | X | X
LIU-SPS | 2020-02-01 | Detailed beam commissioning planning with resources | LIU SPS JTL |  | X
LIU-SPS | 2020-03-01 | Longitudinal instability on the ramp, with smaller longitudinal emittance | BE-RF |  |  | X
LIU-SPS | 2020-04-01 | Review margins in shutdown planning from civil engineering works with EN-EL | Etienne, Jonathan | X
LIU-SPS | 2020-04-01 | Ensure readiness of TIDVG | LIU SPS JTL | X
LIU-SPS | 2020-09-01 | Horizontal instability - conclude on effect and strategy for mitigation | BE-ABP, BE-RF | X |  | X
LIU-SPS | 2020-09-01 | Study and propose mitigation of longitudinal instabilities for ions | BE-RF |  |  | X
LIU-SPS | 2020-12-01 | Definition & performance of slip stacking scenario | BE-RF |  | X | X
LIU-SPS | 2020-12-01 | Emittance preservation for operation with -0.21 space charge tune shift | BE-ABP |  |  | X
LIU-SPS | 2020-12-01 | Transverse instabilities to be expected during slip stacking | BE-ABP, BE-RF |  |  | X
LIU-SPS | 2020-12-01 | Document the stock of spares available after LS2 | Machine Coordinator | X
LIU-SPS | 3 months before HWC start | HWC check lists | LIU SPS JTL |  | X
Shutdown Coordination | 2019-03-01 | Release the final versions of the readiness for installation documents with an approval process | Julie and Machine Coordinators | [5 empty] | Done | All installation readiness documents to be found here: https://edms.cern.ch/project/LIU-000450
Shutdown Coordination | 2019-06-01 | Ensure the quality assurance process to release 3D models, detailed mechanical assembly drawings, differential layout drawings and ECRs | Malika, Wim, Yvon
Shutdown Coordination | 2019-09-01 | Review the risk analysis associating scheduling and technical aspects (Julie and Ray to make a proposal based on BE-BI equipment by May 2019) | Julie

## Progress (hidden)
Done
In progress
Late