## Slide 1: AD-CONS / ELENA Projects
AD- CONS project status

## Slide 2: PS / AD target / AD ring / ELENA ring / TLs coordination
AD ring : new e-cooler collector / vacuum bake-out
ELENA ring: ion source / HV transformer
ELENA transfer lines: Secondary Emission Monitors (SEM)
LS2 works critical path items:
Mid April 2021
Pbars in ELENA
Feb 2021
AD target HW test
July 2020
Start of ELENA
TL’s commissioning
Mid March 2021
PS beam on AD target
Early May 2021
Start of Physics
PS
AD

## Slide 3: LS2 simplified schedule

## Slide 4: LS2 AD-CONS program (1)
1 (2 ?) bending
2 bending
1 bending + 1 quad
1 Beam stopper + 2 slits removal
1 bending + 1 quad + 1 septum
RF C02 cavity swap
1 bending + 4 quads
E-cooler collector swap
3 weeks ahead of schedule
See https://indico.cern.ch/event/867869/
3 quads
1 bending

## Slide 5: LS2 AD-CONS program (2)
AD target: good progress
Details: https://indico.cern.ch/event/867025/
BEAM FROM PS
Courtesy: S. De Man

## Slide 6: LS2 AD-CONS program (3)
Horn testbench
Instrumentation: new BPM + BCCCA consolidation
p Beam

## Slide 7: LS2 AD-CONS program (4)
CV : AD target cooling in 2020. AD hall ventilation upgrade: LS3 ?
Bdg 196

## Slide 8: LS2 AD-CONS program (5)
HLRF CO2 cavity replaced by Finemet, remains to be connected (Vac + cabling: Jan –March 2020)
LLRF Radial loop, Cavity servoloop, gap relay control: syst production, development and lab tests till Oct 2020, then HW commissioning
Power convertors: Upgrade to Megadiscap and Maxidiscap convertors planned for Spring 2020
Vacuum upgrade complete (minor items remaining for LS2: ion pumps, dammaged alu flanges…)
Kickers: repair feedthroughs (done)

## Slide 9: LS2 AD-CONS program (6)
Cryogenic distribution in AD hall:
-Pre-study done in 2018
-Installation planned for 2021
-Financially not approved yet

## Slide 10: LS2 AD-CONS program (7)
AD e-cooler: the decision to build a new e-cooler for 2023 was confirmed 6 Dec 2019.
A new collector is planned to be produced and installed during LS2. Design is in progress, installation is planned for Oct- Dec 2020.
Electron cooler
collector

## Slide 11: Conclusions
AD-CONS program well on its way
AD e-cooler collector on critical path – recovery plan is to keep existing one
Cryo distribution line not funded yet (again…)
A number of re-organizations are getting prepared, in addition to existing baseline, owing to experiment related changes