## Slide 1: First iteration by skype
25 October 2019

## Slide 2: nanoDesign
A semester = 18 weeks, divided in 3 modules of ~6 weeks. 3 hours x 3 days per week
Already run for 3 years, with presentations on quantum physics and its links with nano-technology, but inclusion of CERN and particle physics is new.
~14 students per semester, no prior knowledge on arts and art-science.
Primary goal:
open the minds of the students, who will primarily do design.
train them to learn and express concepts.

## Slide 3: Module timeline
Start with ~2 weeks of research/reading and lectures
4 groups present ideas (maximum 3) to a panel of 4 teachers. One is selected.
At the end of the module ( week 6 ) their piece is presented.
  For the 1st and 2nd modules internally (in University)
  for the 3rd – supposed to be the best – in an art gallery, for 1 day.
Visits to institutes/labs can be organised ( few per year ).

## Slide 4: Action plan
Ongoing semester end on Nov 20
  Theme was standard model. Presentations already given by ATLAS and LHCb physicists
  The 4 students groups have taken 1 LHC experiment each
   Take pictures that can be integrated in a future presentation to ATLAS/LHCb/ORIGIN
Early December 2019:
  Decide on the module which will be dedicated to HEP (1st to leave more time ?), how many scientist talks will be needed… and in which week(s).
Next semester starts in January 2020
  If local scientists cannot make it, Claire to look for Spanish speaking ones who can present remotely. Possibly organise a Virtual Visit.
  Could include a visit to the HEP institutes or any site/lab working with muons, for example.