Agenda (https://indico.cern.ch/event/864067)

1.	Approval of Minutes and Communication

2.	PSB Hardware Commissioning Planning

3.	IST Planning

Present: S. Albright, M. Atanasov, W. Bartmann, A. Beaumont, F. Chapuis, L. De Mallac, J. Devine, G.P. Di Giovanni, A. Findlay, E. Fortescue-Beck, M. Haase, D. Hay, A. Newborough, F. Pedrosa, G. Petrika, S. Pittet, F. Pozzi

# Approval of Minutes and Communication

The minutes of the previous meeting, LIU-PSB TCM #4, on the preparation of the IST have

been approved. The minutes are available here.

# PSB Hardware Commissioning Planning

F. Chapuis presented the current status of the PSB hardware (HW) commissioning planning, see

here.  Below a few keys points to retain. More details available in the presentation.

- The PSB HW commissioning period will last 17 weeks, from 04/04/2020 to 09/08/2020.

- The equipment installation in the tunnel should be completed by end February 2020. Therefore equipment installation is not allowed during the HW commissioning, but any equipment troubleshooting and corrective interventions will be punctually allowed. The time of the intervention should be discussed with the PSB HW commissioning coordinators (A. Akroh/F. Chapuis) as it may depend on several constraints.

- The expected general services availability is

  - Electrical Network: Power ready at 100% for HW commissioning. Full network redundancy available form 30/04/2020.

  - EN-CV Services ready for the start of HW commissioning (before 14/04/2020).

- Control Network and Middleware ready for 01/04/2020. All CCR (Control Change Request) should be released for the 02/03/2020.

- The beam patrol is planned for the 14 April 2020.

- Two DSO tests are required to authorize the Main Power Supplies Tests:

  - DSO Test to qualify: POPSb with BR.BHZ/QFO/QFE → 02/06/2020.

  - DSO Test to qualify: BR.MPS with BR. BR.BHZ/QFO/QFE → 06/07/2020.

- Every time an equipment is successfully tested, it will be left running in order to also probe its reliability over time.

- PSB HW commissioning split in 3 main blocks.

- Currently part 2 is still in discussion with EPC: A bottle neck has been raised by TE-EPC due to limited resources in March-May 2020 to be able to complete the work in the PSB and PS. F. Pedrosa added that this issue is currently treated by the LIU-CCC, as it affects the planning of two machines.

- An important limitation is the Linac4 commissioning to the LBE which will impose the closure of the switchyard since the beginning of June 2020. As said the plan may change. Also the access strategy may be revised allowing all access during dedicated days to concentrate the effort and mitigate the disruption of the beam commissioning.

- A few tests require the synchronization of TE-ABT and TE-EPC. In fact, TE-EPC is responsible for the power supply of septa and bumpers. Dedicated meetings have been organized and a dedicated slot was added in the planning.

- The PSB HW commissioning requested TE-ABT to advance phase 4 as there is a significant lag between the expected completion of the phase 3 activities and the beginning of phase 4. W. Bartmann agreed with the proposal, shifting the full phase 4 block such that BI.DIS starts in the week of 1st June. This leaves 2 weeks margin wrt phase 3 and should finish the dry runs well before 1st August.

- BE-BI provided the list of tests and desired dates. Additional discussions will be needed to iron out the details and agree on the final dates.

- planning is available in MS-Project-OnLine: PSB_LS2_HC

- The work for the future weeks is:

  - Refine the presented schedule and re-adapt in case of major changes, see the ongoing discussion with TE-EPC.

  - Complete the OP check-list

  - The deadline is end March 2020.

Discussion:

- F. Pedrosa said that the dates for the PS Main Units (slide 3) has to be updated with the latest information, i.e. to be completed by the end of week 22, to allow the start of the Linac4 commissioning to the LBE run without interventions in the swytchard.

- A. Findlay commented to also add in slide 11 a time slot for the commissioning of the old analogic system for the Transverse FeedBack (TFB), as it will remain as a back-up system.

- F. Chapuis will add a time slot for the commissioning of the PSB FEI (interlock system), see slide 13.

- F. Pedrosa commented on the complexity of performing both PSB HW commissioning and PS IST at the same time and in common areas. Looking at the current planning of both machines,  a risk assessment for intra-machine works should be done. F. Chapuis agreed with F. Pedrosa’s comment and added that until the planning are frozen (see the ongoing discussion with EPC), it does not make sense to ask experts to prepare a risk assessment document. If the plan changes, the risk will change as well. G.P. Di Giovanni added that both machine responsible should meet, cross-correlate the planning, systematically review the risks with equipment and safety experts.

# IST Planning

D. Hay presented the latest planning for the IST, see here.

G.P. Di Giovanni and E. Fortescue-Beck reported on the list of requirement for the IST collected

so far, see here.

Discussion:

- G. Petrika reported that, because of additional delays with the SMB work, the cooling from B237 will be available in week 11 of 2020 (beginning of March 2020). This is about 2 weeks more than previously announced.

- G. Petrika also added that the recent pressure tests, almost all the joints leaked in the tunnel and surface. The joints will have to be consolidated. A meeting between EN-CV and EN-ACE has been organized to schedule the work.

- TE-EPC will need water in the BHP from the 19th March 2020, so this is compatible with their tests.

- A. Newborough raised the issue with the TE-MSC high voltage tests which are currently planned for the beginning of March 2020:

  - He will meet with EN-CV to see what can be done. TE-MSC would like to have water flow to test the magnets under nominal conditions. A test dry (without water) could also be done in case of delays.

  - G.P. Di Giovanni suggested to see if it makes sense to post-pone the test by couple of weeks.

- M. Haase reported of a few issues with the cooling for the ongoing RF Finemet tests. The water is polluted and this required already a few stops to clean the filters. G. Petrika commented that indeed this is not acceptable and EN-CV is working on fixing the issue. The problem seems to come from the welding of the pipes.

- A. Newborough expressed concerns about the pollution of the water. The water should be clean before connecting the flow to the magnets, as they do not have filters, differently from the RF system.

- The document preparation for the risk assessment is proceeding well. TE-ABT already prepared a few documents which should be soon circulated. G.P. Di Giovanni reminded that, once a document is ready, the person to contact is T. Birtwistle. He will handle to approval process.

- A. Newborough commented that the procedure for the high voltage test on the magnet has been prepared, but currently EN-EL does not approve the load on the magnet. He will meet with EN-EL and work to unblock the issue.

Minutes by G.P. Di Giovanni