ARTIC
Advanced PFA in Pandora (EoI-145)
Gérald Grenier & Vincent Boudry
IP2I, CNRS/UCBL@Lyon LLR, CNRS/IPP@Palaiseau
AIDA++ Software WP preparation
22/11/2019

---
ARBOR like PFA sw
1. ARBOR PFA SW in continuous development:
  1. LLR + IHEP (M. Ruan + H. Videau + VB) → ARBOR in use for CEPC + some ILD Studies
    1. Partial re-writing in AIDA (Bo LI @ LLR + IPNL)
    2. implementation of Lepton ID (LICH)
  APRIL (Algorithm of Particle Reconstruction for the ILC LCWS'2019 ➚ )
  1. IPNL (R. Été + B. Li + GG ) : Complete re-write in Pandora SDK

---
AIDA++ Completion, tentative planning
Long standing work
@ LLR and IPNL, IHEP
1. Deliverable 1: APRIL PFA
  1. M1: usable code: [M12]
  2. D1: optimised for various setup (ILD, CEPC, FCC) ? [M36+]
2. Deliverable 2: PFA performance detailed comparison tools.
  1. M1: Beyond the global performances: comparison of clustering results
     (distance, Rand-index), e.g. wrt to MC truth
  2. D2: provide tool [M18]
  Deliverable 3: 3D+ pattern recognition tools for particle PFA
  1. M1: Pattern recognition for reclustering [M24]
    1. Application of various algo, esp. EM [F. Magniette, 2018]
      1. using CALICE data (shower shapes)
  2. M2: Application to and from PID [M36]
HARPO (B-less TPC), track finding of triplet

---
Ressources
1. Too Scarce (off course)!!!
2. Request:
  ~ 190k€ for 390k€ matching
    (a) = one PhD student for 3 years + 10k€ missions ⬅︎⇦⇦
    (b) =	0.25 FTE salary for 4 years × 3 *(VB, J.C Brient, PD-LLR)
    0.25 FTE, G. Grenier, assistant professor, for 4 years = 90 kEUR
  1. With 6M FTE... no travel (?)
    1. Contract extension of existing PD only...
    2. Delay in production → planning to be reviewed
3. Institutes
  1. Full benef: CNRS + UCBL ? (only IPNL ?)
  2. Collab: IHEP