## Slide 1: Report: 28 Activity: SPS
Chiara Pasquino, Anthony Harrison
Meeting 03/08/2020

## Slide 2: Activities of the past 2 weeks
BA1:
  TT10 passage pumpdown; Postponed by EN-ACE to September.
  Check of the sector valves in 1- : small CA issues, all working now;
BA2:
  ZS reconfiguration – pumpdown and NEG activation; postponed to september, after cabling campaign;
  MSE exchange – bakeout; leak found on a weld, new tank under preparation at surface: waiting for a window within the cabling campaign where the exchange could be done;
  Pumpdown of 212 & 220;
  Radiation damaged cables for penning gauges endorsed by LS2C;
BA3:
  321 reinstallation;
  800MHz cavities installation;
  RF Cavity 1 – under RF conditioning;
BA4:
  QF_43010 jack exchange: unforeseen but completed, 461 leak tight, ion pumps flashing;

## Slide 3: Activities of the past 2 weeks
BA5:
  Material preparation: MDHD modification, BTV acceptance tests, TIDVG5 leak tight, MKDH surface preparation;
  561 pumpdown;
  Marking of the vacuum supports for the new line: few conflicts with existing coffret solved.
BA6:
  QDA_61910 jack exchange: unforseen, activity completed.
TT-60/66 -TI2 – TI8:
  Pumpdown of TI8 line - 1805;
  TI2 Alignement campaign: first vertical measurement of the quadsTT60 – TT66 done, no mechanical disconnection needed;
  TT66 magnet reconnection after jacks replacement;
AWAKE:
  Issue with an interlocking pirani on the plasma cell: to be checked at next access, e-line operation resumed.

## Slide 4: News from LSS3
5 cm!!
First RF conditioning

## Slide 5: News from LSS5
5 cm!!
Equipments and magnet being installed. Few delays expected:
QFA_518 – busbars modifications;
FWS – issue with insulation of the forks cables --> possible delayed installation;
BTV – leak tightness;

## Slide 6: News from LSS5
5 cm!!
TIDVG5 readiness:
Shielding installed;
TIDVG5 vacuum chamber fully assembled and leak tight;
Acceptance test + bake out cycle foreseen beginning of September.

## Slide 7: Pressure map
Vacuum sector

## Slide 8: PLANNING OVERVIEW

## Slide 9: TI2 alignment campaign: approved strategy
Courtesy of J. Coupard
Clash for the access to TI2 from LHC P2 with the ELQA and cool-down of sector 1-2 to be addressed
Clash for the access to TI2 from BA7 with the PPS tests to be addressed
Approved at the LS2C: planning to be updated after the alignment measurements are completed (mid September).

## Slide 10: DASHBOARDS - 2020

## Slide 11: DASHBOARDS - 2020
Steep curve in august – september
Courtesy of
A. Grande Mallavia

## Slide 12: Activities of the next 2 weeks
BA2:
  MSE exchange?
BA4:
  Coldex Y chambers reinstallation;
BA3:
  800MHz cavities & pickup installation;
BA5:
  Material preparation;
  LSS5 VSC support drilling;
  Installation of sector valves and chambers;
TT66:
  Magnets reconnection;

## Slide 13: Resources distribution
LSS5 reinstallation: Tony
LSS3 reinstallation: Jarmo
Arcs pumpdown and leak detection: Jarmo, Anthony, aC Coating & 40/30;
Acceptance test & lab activities: Tony;
Jobs follow-up & ECR update (Design & Production): Chiara & Tony;
Stock check and purchasing: Chiara & Tony.

## Slide 14: Thank you !

## Slide 15: Pumpdowns
Lengthy pumpdowns (ion pump flashing) – arcs/DS are behaving all similarly.

## Slide 16: Pumpdowns
Lengthy pumpdowns in LS1 too, very similar pumpdown considering we are comparing 1 arc with an half arc (double pumping speed).
For info: 510 – LS1 1 year exposure; 411 – LS2 3 months exposure;
Longer exposure --> difficult flashing.

## Slide 17: Pumpdowns – aC coated Vs uncoated sectors (once on ion pumps)

## Slide 18: Pumpdowns - summary
Pumpdown on TMPs is strongly dependent on:
  Exposure time to air:
    Location of the openings, length of the intervention;
    It strongly affects the behaviour of the ion pumps during flashing;  is becoming a limiting factor (all SPS pumping groups are in use at the minute).
    New ion pumps shows a more ‘stable’ behaviour to flashing, but still the process is lenghty in time.
For long exposures (LS1 and LS2), pumpdowns are very similar for coated and uncoated sectors;
Pressure recovery once on ion pumps, is very similar for coated and uncoated sectors, after long exposure.
After LS2 I would test ion pumps performace at different exposures to air/N2/noble gases.