Agenda (https://indico.cern.ch/event/868965/)

1.	Executive Summary

Present:  E. Amarilla, C. Bedel, E. Cano, J. Devine, G.P. Di Giovanni, R. Folch, G. Georgiev, D. Hay, M. Meddahi, F. Pedrosa, S. Pittet, M. Sardano

# Executive Summary

D. Hay and M. Sardano reported on the timeline of the activities and current issues with the BHP:

- In the middle of the year, it was decided to install a galvanized metallic structure to support the racks, because of issues with the presence of lead in the painting and the floor tiles containing traces of asbestos. The metallic structure was not part of the original plan.

- Before starting the EN-CV and EN-EL activities, a VIC was performed end October. As a result, and in order to guarantee the safety of the working personnel, TE-EPC had to fix the racks, hosting the SIRIUS power converters, to the metallic structure.

  - Two clamps (safety redundancy) were installed per rack.

  - Some of them had to be customized to better adapt to the structure.

- During the EN-CV activities this week, EN-CV requested to remove 1 clamp to connect the flexibles to the rack. They left the removed clamp in each rack, waiting for TE-EPC to put it back in position.

- When TE-EPC restarted clamping the racks, they realized that the second clamp which should have guaranteed the safety had disappeared. As a result, they were not able to guarantee the safety in the area and all activities were stopped since 04/12/2019.

- Yesterday afternoon, TE-EPC restarted fixing the racks with the available spares and noticed that part of the disappeared clamps were put back in position. They were placed incorrectly but nevertheless they were returned. The customized clamps are still missing.

- Additionally EN-CV reported that during the pressure tests in BHP they had problems with some flanges that leaked. To sort this out SMB will have to remove the asbestos-containing joints (about 16). A specialized team is needed to take care of their replacement. EN-CV already contacted D. Pazem's team (the one working in the PS asbestos removal), but they will only be available from the beginning of January 2020. F. Pedrosa and D. Hay agreed that it is better to keep the SMB team complete the work in the PS and then move it elsewhere. About 2 days should be allocated for these replacement.

- The hard constraint is to allow EN-EL to pull the DC cables next week without any co-activity.

Following the discussion, the updated planning is:

- TE-EPC will re-fix the racks to the metallic structure. The customized clamps will be fabricated again. The clamping should finish at the end of this week. G. Georgiev mentioned that, if an extra day (say on Monday 9th December) is needed, he could dispatch the team to complete the cabling work in the BCER.

- EN-EL completed their planned activities, but the additional general services should be postponed to sometime next year. D. Hay said that for this work the false floor needs to be in place as stairs and similar tools will be used for the installation. Also in this case, G. Georgiev mentioned that he already discussed with J. Devine and E. Cano and, while the cabling activity completes in different areas, the EN-EL teams could start their work on the additional general services. So instead of planning 1 week straight for the work, EN-EL should intervene punctually. This was accepted as a good solution.

- The remaining EN-CV works include the replacement of the joints with asbestos, the connection of the flexible to the remaining 9 power converters (<1 day would be needed) and the repetition of the pressure tests. It was agreed that to organize a VIC to discuss the timing and the co-activity between cabling and EN-CV. The connection of the remaining power converters can be done as soon as the rack are secured and TE-EPC is available, i.e. already next Monday morning 9th December. Concerning the punctual intervention of replacing the joints with asbestos, G. Georgiev said he will support this co-activity work. The tentative planning is to organize the asbestos removal on Tuesday and Wednesday 14th and 15th January 2020 and repeat the pressure test on Friday evening 17th January.              G. Georgiev prefers that the tests are carried out when there is no personnel pulling cables. This will avoid uncomfortable situation, such as stopping the cabling work in the middle of the day because of leaks, etc, etc.

- Between the completion of the cabling pulling, which should end the 14th February 2020, and the beginning of the IST, 2nd March 2020, there are couple of weeks which should allow TE-EPC to complete minor remaining activities.

- As the plan stands now, it does not jeopardize the IST in the PSB or PS (BTP line).

M. Meddahi thanked all the participants to have worked out together a mitigation, with an honest

and collaborative approach.

Minutes by G.P. Di Giovanni