## Slide 1: PSB Dry Runs
LIU Commissioning Coordination Committee
13th December 2019
A. Akroh, F. Chapuis, J.F. Comblin, G.P. Di Giovanni, B. Mikulec

## Slide 2
PSB Upgrade Snapshot
Instrumentation
  H0/H-
  TbT BPMs
  Diamond and IC BLMs
  Matching Monitors
  Wire scanners
  Tune/Quadrupolar PU
Operation
  Cycle generation and tune control
  Interlock: BIS, External Conditions, SIS
  Synchronisation adjustment of equipment (distribution, injection, extraction, recombination)
  Operational applications
Upgrade
  New injection and extraction energies
  New H- injection schema: Stripping foil, transverse & longitudinal painting, beta-beating correction
  New RF system (Finemet) and LLRF control
  POPS-B control: beta-beating corrections, special trims, etc, etc
  B-Train
  Transverse Feedback
  New Extraction Kicker control

## Slide 3
Overview
In previous years in the PSB we were used to refer to Dry Run as test with experts
The current definition of Dry run is: full (sub-)system functionality tests in operational conditions (from K. Li, SPS Dry Run).
Plan and schedule tests per equipment or system ideally from highest level (application) through LSA/INCA and FESA down to hardware.
The ‘verticality’ is the key aspect of the test.
In these slides we present the identified list of tests.
The integration in the Hardware Commissioning planning will follow.

## Slide 4
Beam Instrumentation
Dry Run | High Level Application | Tested Dependencies | Requirements
Injection/Extraction Trajectory | Injection/Extraction Trajectory application | BPMs reading Logging in DB Timing (change of destination) | MTG BPM calibration signal NXCALS Optical/mechanical/electrical offsets in FESA
Injection/Extraction Trajectory Ring Orbit | YASP Optics uploader | BPMs reading (time integrated for rings) Logging in DB Optics according to destination/beam type Transitional FGC setting Timing (destination) Open Bump (position/angle at injection/extraction) | MTG BPM calibration signal NXCALS MADX Optics FGC for correctors Optical/mechanical/electrical offsets in FESA High Level Parameter Knobs
Multi-turn Ring Orbit | Turn-by-Turn application | BPMs turn-by-turn reading Gain setting Test calibration procedure Logging in DB | MTG BPM calibration signal RF NXCALS Optical/mechanical/electrical offsets in FESA
BCT | Watchdog BCTTRIC | Watchdogs with new medium ring BCT Wetting of BCT gates Calibration signals Logging in DB | BCT calibration signal OASIS NXCALS RF Timing
BTV | BTV application | Screen movement Acquisition for different settings Alarms | Laser

## Slide 5
Beam Instrumentation
Dry Run | High Level Application | Tested Dependencies | Requirements
BLM | BLM Surveillance Ring BLM Viewer | BLM reading Threshold management OASIS signal for diamond BLMs Logging in DB Virtual parameter in knobs Laser | BLM calibration signal OASIS NXCALS Laser
Transverse Profile Measurements | Wirescanner application: “Old” WS LIU WS | Acquisition for different gain and speed Automatic retrieval of the tune-dependent optics parameters Test bunch-by-bunch in LIU WS Logging in DB | FESA class with simulated data NXCALS MADX Optics
Matching Monitor | Matching Monitor application? ABT scripts | Acquisition for different gain In/Out movement Interlock when inserting grids Logging in DB | SEM calibration signal? OASIS, SIS, NXCALS External Condition Tested (slide 11) Detailed procedure for dedicated MD
H0/H- Monitor | H0/H- Monitor application | Acquisition for different gain Logging in DB Alarms | OASIS NXCALS Laser
SEM GRIDs | SEM Grid application | Check different optics settings Wire reading Logging in DB | SEM calibration signal? NXCALS

## Slide 6
New PSB Injection
Dry Run | High Level Application | Tested Dependencies | Requirements
Distributor | Cruise Control | Vary number of turns and verify the distributor response Logging in DB Synchronisation with Chopper | MTG OASIS Knobs (Virtual Devices) NXCALS
Kicker SloW | Cruise Control | Load/read KSW functions Vary number of injected turns and verify the KSW response Logging in DB | OASIS Knobs (Virtual Devices) NXCALS
Bumper Slows | Cruise Control | Vary number of injected turns and control the flat-top length Asynchronous control of the flat-top length (for optics measurements, beam commissioning) Logging in DB | OASIS Knobs/FGC NXCALS
QSTRIP Beta-beating compensation | ABP Scripts | Tune-dependent generation of the beta-beating compensation Load the compensation in HW and test expected response Logging in DB | OASIS Knobs/FGC NXCALS Makerules
Stripping Foil | --- | Foil movement and no foil positioning Snapshot of each foil before beam impact BTV IN/OUT + Interlock | Knobs

## Slide 7
Early Beam Extraction
Dry Run | High Level Application | Tested Dependencies | Requirements
Extraction/Recombination Kickers | --- | Supercycle with only 1 beam type Anticipate extraction time to C275.xxx with xxx < 100 and verify the response of the kicker. Reliability run of extraction kicker at injection: Without beam, triggering on injection timing & acquire KFA14 current waveform on OASIS. Several hours needed to accumulate sufficient statistics. Logging in DB. | MTG OASIS Knobs (Virtual Devices) NXCALS
Early extraction after maximum 100 turns is critical to be able to commission the matching monitor and be able to
study the Linac4 matching at the PSB injection and give the option to anticipate the commissioning of the extraction
line at 160 MeV.

## Slide 8
Other OP Applications
Dry Run | High Level Application | Tested Dependencies | Requirements
Tune Setting | Tune Control Application | Modify tune and verify the trims for main quadrupoles, qstrips Logging in DB | OASIS FGC NXCALS Makerules MADX Optics
Cycle Generation | POPS-B Cycle generation | Generate operational 1.4 GeV and 2.0 GeV, load and play in the supercycle Test MD variations Verify thresholds with FGC Logging in DB | MTG OASIS FGC B-Train
Tune/Chromaticy Measurement | Q-meter | Check that the new hardware is compatible with the old application (the interface should not have been changed) | OASIS Knobs

## Slide 9
RF
Dry Run | High Level Application | Tested Dependencies | Requirements
Tomography | Tomoscope | Check PU signal Check timing/trigger behaviour with 2 connexion on each scope Loading data from previous year to check reconstruction algorithm Logging in DB | MTG BPM calibration signal OASIS (signal, trigger/timing, attenuators) NXCALS
Bunch Shape Monitor | BSM Application | Check application and scope functionalities Logging in DB | MTG OASIS NXCALS
Transverse Feedback (old analog system) | TFB Inspector panel | Check control behaviour with FESA class. | MTG

## Slide 10
Expert Dry Run (I)
Dry Run | High Level Application | Tested Dependencies | Requirements
LLRF (to be repeated for 4 rings) | --- | VME & NIM Power supply checks Check RF synoptic can be used to control LL Working sets and knob checks Timing generation B Train reception by cable and fiber Check of local LL B train simulator, official simulated B Train and measured B Train RF train generation and distribution, FREV, TFB(old and new), Q-Meter, injection synchro, PSB extraction synchro RF Train reception from PS for synchro 10 MHz reception and distribution Frequency program generation Voltage program/frequency generation and distribution to cavity Cavity ready signals check Gap voltage reception check Cavity current reception check Check functions required to program system, voltage, blow-up etc. Visualization of all functions and signals on OASIS and samplers Phase pick-up power check. Synchro signal switching for destination and harmonic number Check of all signals distributed to OASIS, digital and analogue Check Tomoscope app. + programming & operation of HW | CO infrastructure Tomoscope application RF Synoptics OASIS Samplers NXCALS

## Slide 11
Expert Dry Run (II)
Dry Run | High Level Application | Tested Dependencies | Requirements
Transverse Feedback (digital electronics) | --- | Power amplifier performance Verify the cable length/connection Perform pattern injection tests Excitation signal generation Logging in DB | Calibration signal OASIS Knobs NXCALS
B-Train | Inspector Panel | Check electronics (calibration, WhiteRabbit transmission to TE-MSC-MM lab) in simulated mode Check electronics in current regulation mode Check electronics in field regulation mode with cavities Logging to DB | POPS-B (current/field regulation test) RF (field regulation test) NXCALS OASIS
PSB Scraper | --- | Mask positioning Reading of the temperature sensors | Scrapers Control

## Slide 12
EPC
Dry Run | High Level Application | Tested Dependencies | Requirements
BT.BHZ10 switching magnet | --- | Multi-PPM, multi-destination control Verify the interlock response Configure FEI Logging to DB | MTG FGC OASIS Makerule NXCALS
Check of configuration, state, control, acquisition + OASIS for each power converter is a critical part of the HW
Commissioning → validate shape, ripple, synchronization
Several of the dry runs described before already include EPC system in the chain of tests

## Slide 13
Miscellanea
Dry Run | High Level Application | Tested Dependencies | Requirements
Interlock | BIS GUI BIS Monitor SIS FEI PSB WIC EC GUI | Check all instances Check settings and interlock acquisition for power converters Verify that the correct interlock is displayed Test all failure scenario Laser alarms | MTG FGC Knobs OASIS External conditions Laser
Septa | --- | Blade alignment | Knobs
Timing: 24 to 32 users | Sequencer Manager | Check machine behaviour after migration from 24 to 32 timing Check the presence of 8 new timing users Check PLS number of user ZERO=first position map/unmap cyclses. Check wset update with 8 new users. Check PPM behaviour on operational device | MTG
Timing | Sequence Manager | Check destination Check inhibit by destination in CCC Check inhibit sequence change | MTG
Special sequences | Sequencer Manager | Test special sequences for dedicated measurement cycles | MTG