## Slide 1
Task Force for Energy Upgrade of the CERN PS Booster from
presently 1.4 GeV to ~2 GeV
Follow-up of the 2010 LHC performance workshop at Chamonix
http://indico.cern.ch/conferenceOtherViews.py?view=standard&confId=67839
remove bottlenecks in the LHC injector chain
consolidation of the injectors is necessary anyway
KH 04/03/2010

## Slide 2
Mandate
The aim of the study is to evaluate the technical feasibility of an increase in beam
energy of the CERN PS Booster from presently 1.4 GeV to about 2 GeV as proposed
at the Chamonix 2010 workshop.
The study comprises:
Confirm the potential gain in terms of intensity and brilliance for LHC-type beams as
presented at the Chamonix 2010 workshop.
Confirm the technical feasibility. Identify accelerator components and equipment
that need to be upgraded or exchanged. Identify potential showstoppers and point out
solutions. Assign the responsible groups/units. Provide first rough time estimates for the
various interventions needed.
Provide a first estimate of material and personnel resources needed to complete
the upgrade. Draft a project break-down into work packages, in preparation for a project
to be launched by the director of accelerators.
KH 04/03/2010

## Slide 3
Working Group Organisation
CERN Task Force Leader | K. Hanke
Scientific Secretary | T. Hermanns
US LARP Representative | E. Prebys
 | Work-Package | Responsible (confirmed) | Unit
1. | Beam Dynamics | G. Rumolo | BE/ABP
2. | Magnets | D. Tommasini, A. Newborough | TE/MCS
3. | RF System | A. Findlay, M.Paoluzzi | BE/RF
4. | Beam Intercepting Devices | O. Aberle | EN/STI
5. | Power Converters | S. Pittet | TE/EPC
6. | Vacuum Systems | E. Mahner | TE/VSC
7. | Instrumentation |  | 
8. | Commissioning | B. Mikulec | BE/OP
9. | Extraction and Transfer | J. Borburgh | TE/ABT
10. | PS Injection |  | 
11. | Controls | M. Gourber-Pace | BE/CO
12. | Electrical Systems |  | 
13. | Cooling and Ventilation | M. Nonis | EN/CV
14. | RP and Safety | T. Otto | DGS/RP
15. | Transport and Handling | I. Ruehl | EN/HE
16. | Survey |  | 
17. | Linkperson Consolidation | D. Macfarlane | EN/MEF
CERN Task Force Leader | K. Hanke
Scientific Secretary | T. Hermanns
US LARP Representative | E. Prebys
KH 04/03/2010

## Slide 4
Time Lines
Identify showstoppers: rapidly; 1-2 months from now
first approximate cost estimate (still with large error bars):
end April / beginning of May 2010
by then inventory of equipment, ballpark estimate but no design yet
Enter in MTP in May 2010, in time for council meeting
The actual work will be constrained by the shutdowns.
LHC off 2012, possibly short run of the injectors
2013 long LHC run
2014/15 long LHC shutdown (connection of Linac4)
KH 04/03/2010

## Slide 5
Meetings & Homework
In the first phase (to identify showstoppers) suggest weekly meetings (i.e.
come back with a first survey of showstoppers next week)
In a second phase, when we do the “real work”, probably go to bi-weekly meetings
Time slot Thursday 16:00 convenient for FNAL
Other possible time slot Wednesday, same time
KH 04/03/2010

## Slide 6
1. Beam Dynamics:
identify showstoppers & bottlenecks, confirm the gain that
we can expect (primarily for LHC type beams), do we hit other bottlenecks,
look particularly into PS injection
2. Magnets:
what field (energy) can be realistically achieved (assume around 2 GeV but
to be confirmed; can the magnets run like this 7/7 24/24; can the magnets run like this
only for certain users (~1/3 of the beams)?; what are the modifications needed
3. RF:
Biggest uncertainty for me; do we need to re-build an rf system or can we consoli-
date the existing one?; it is on the consolidation list anyway.
4. Beam intercepting devices:
Inventory of all devices; does the dump withstand this?;
the dump is being looked into anyway; spare situation
Homework
KH 04/03/2010

## Slide 7
5. Power converters:
MPS; other power converters, which ones need to be replaced; is
there a fundamental problem with ramping up to 2 GeV within 1.2 s?; keep the 600ms
option for ISOLDE (presumably at 1.4 GeV).
6. Vacuum:
Assume no showstopper but a lot of activity.
7. Instrumentation:
Assume no showstopper, but confirm (e.g. intercepting devices)
8. Commissioning:
Main issue will be tight planning, constrained by the (few) shutdowns
9. Extraction and transfer:
Need to go through all the kickers, septa etc and confirm which ones need to be changed;
include the corresponding power supplies
Homework
KH 04/03/2010

## Slide 8
10. PS injection:
probably part of 9.
11. Controls:
Do not expect showstoppers but confirm.
12. Electrical Systems:
Confirm whether electrical systems are appropriate or need to be upgraded; for this
need power consumption.
13. Cooling & Ventilation:
Confirm whether present cooling (water station etc) is appropriate, or need to be up-
graded; need to estimate power dissipation
RP and Safety:
Identify showstoppers (shielding, existing buildings etc); look in particular at PS injection.
Homework
KH 04/03/2010

## Slide 9
15. Transport and Handling:
Look into existing equipment (cranes etc), confirm whether operational to do major
interventions.
16. Survey:
Expect no showstoppers.
17. Consolidation:
Ensure that consolidation takes into account the energy increase; at a later stage need
to share the tasks (and the budget)
Homework
KH 04/03/2010