## Slide 1: Commissioning Coordination Committee meeting 10/01/2020
Fernando PEDROSA

## Slide 2: DSO tests

## Slide 3: DSO tests

## Slide 4: DSO tests

## Slide 5: DSO tests

## Slide 6: DSO tests

## Slide 7: DSO tests
Based on the information collected on these tables the scenario that would minimize the times that an access zone needs to be stopped for the DSO tests is:
LINAC4 DSO test the 23rd of March or the 24th before the PS SWY DSO tests;
LEIR DSO test the 23rd of March or the 24th before the PS SWY DSO tests;
PS SWY, PSB, PS Ring and TT2 DSO tests performed together the 24th and 25th of March
  This DSO tests should validate all the EIS BEAM and as much as possible the EIS Machine
Having all the EIS BEAM validated would allow to perform the DSO test for the EIS machine validation later if needed (PS -> POPS, PSB-> POPS-B + MPS) faster and without affecting the adjacent areas

## Slide 8: Master Schedule
POPS-B + MPS

## Slide 9: Modifications
Wish expressed from EPC to start the POPS-B tests in April instead of June as foreseen today in the PSB HWC planning and agreed in February 2019
POPS not available before the 6th July 2020 due to the new delivery date at the end of February
New durations (EDMS 2279382)

## Slide 10: Actual PSB Hardware commissioning planning before and during POPS-B + MPS
POPS-B + MPS
All tests requiring access
All tests requiring access
  MSC tests – auxiliary magnet tests + transfer lines (BI, BTP, BTM, …)
  ABT tests phase 3 and phase 4
  …

## Slide 11: Actual PSB Hardware commissioning planning before and during POPS-B + MPS
POPS-B + MPS
All tests requiring access
POPS-B and MPS
  DSO test with POPS-B for the Hardware Permit
  1 week at the beginning for the magnet patrol
  4 weeks of POPS-B tests
  DSO test with the MPS for the Hardware Permit
  1 week for the MPS test
  DSO test for the for the Beam Permit

## Slide 12: PSB Hardware commissioning planning before and during POPS-B + MPS with the new date
POPS-B + MPS + others
Option 1
  The tests that require access are performed together with POPS-B +MPS if compatible, and the POPS-B or MPS tests are stopped to allow access if needed

## Slide 13: PSB Hardware commissioning planning before and during POPS-B + MPS with the new date
POPS-B + MPS
All tests requiring access
Option 2
  The tests that require access are performed after POPS-B +MPS, and the LINAC4 LBE dump tests are stopped to allow access

## Slide 14: PSB Hardware commissioning planning before and during POPS-B + MPS with the new date
Option 3
  POPS-B +MPS tests are kept as much as possible as planned today without affecting the availability of POPS for the 6th of July 2020
POPS-B + MPS
All tests requiring access

## Slide 15: Master Schedule

## Slide 16: New POPS commissioning schedule
15 days of POPS tests with the MUs (LINAC4 tests stopped for access on a 1 day pre-warning notice)
9 days of full access to TE-MSC

## Slide 17: Planning options for the period before PS SWY closure

## Slide 18: Planning options for the period before PS SWY closure

## Slide 19: Planning options for the period before PS SWY closure
The two options give more time for the ISTs that require access and that have to be performed before closing the PS SWY
The 5 days removed in August 2020 to the ISTs period is compensated by the additional access time that is now recovered in May 2020 by removing the POPS tests (RF are the may systems affected and they will start their IST period in Feb 2020 already)
The 5 days removed to the LS2 shutdown period will have to be compensated by a tighter schedule, but we had already a limited number of activities in this period because we were already in the IST period

## Slide 20: New POPS commissioning schedule
15 days of POPS tests with the MUs (LINAC4 tests stopped for access on a 1 day pre-warning notice)
9 days of full access to TE-MSC

## Slide 21: New POPS commissioning schedule – PS HWC
Problem to be addressed

## Slide 22: New POPS commissioning schedule – PS HWC