## Slide 1
Air conditioning restored by 21/02/2020 (temporary solution)
Signal cabling activities
Renovation of electrical power distribution to racks
Installation of optical fibres (on top of racks)
  Fibres between buildings and trenches completed
  Number of patch cables for initial installation to be defined
Ethernet socket installations
10 MHz cavity controller front-ends removed from b. 359 racks
  Reconnection early February
  VME few power supplies to be reinstalled
Racks for Finemet cavity (b. 151), exchanged  needs re-cabling
Status of activities in PS central building

## Slide 2
Controls installations
  Network re-connections to new socket infrastructure completed
  BE-CO  pulse repeaters in CR33/35 done
  CR13 general timing distribution completed
  Migration of timings for 20, 40 and 80 MHz systems
  Modified architecture of timing front-end cfv-353-allbc3
    Adapt for 32 users
Ongoing
  Renovation of pulse repeaters in racks
    Priority with CR24 to CR30 (to restart clock distribution)
  Installation request for VXS crates CR10, 11
  Installation request for virtual devices of DR detection
  Virtualization of functions (e.g. PA.GSV10GLOBAL) and associated restarts
  Many thanks to B. Ninet, E. Said, BE-CO installation team
Controls installations

## Slide 3
VXS modules for PS produced
Spare 1-turn delay feedback boards produced
Update synoptics
Simulated transmission of bending field via WR B-train?
Controls front-ends:
  cfv-353-allbc1/2 on CERN CentOS7
  cfv-353-allbc3/4 on hold for migration of timings to cfv-151-xxx
Configuration of new crate for RF train distribution
  cfv-353-alltd
Layout of front-ends in b. 151 (20/40/80 MHz)
  cfv-151-allbc1, cfv-151-allc20, cfv-151-allc40, cfv-151-allc80-08, cfv-151-allc80-88-89
Beam control: Status and next steps

## Slide 4
VXS modules for PS produced
Spare 1-turn delay feedback boards produced
Update synoptics
Simulated transmission of bending field via WR B-train?
Controls front-ends:
  cfv-353-allbc1/2 on CERN CentOS7 (timings not accessible)
  cfv-353-allbc3/4 on CERN CentOS7, devices accessible
Configuration of new crate for RF train distribution
  cfv-353-alltd
Layout of front-ends in b. 151 (20/40/80 MHz)
  cfv-151-allbc1, cfv-151-allc20, cfv-151-allc40, cfv-151-allc80-08, cfv-151-allc80-88-89
Beam control: Status and next steps

## Slide 5
Status of hardware developments
 | Hardware |  | Comments
Module | Prototype | Series | 
CTU |  |  | Hardware completed
Fractional divider (AWAKE/PS) |  | 02/2020 | Completing prototype validation Series production
AVC surveillance | 02/2020 |  | Design phase
Master DDS FMC | 02/2020 |  | Almost ready for design office
Master clock divider | 03/2020 |  | Development starting?
Clock/sync adaptor | 02/2020 |  | Finalization of design, then review

## Slide 6
Status of firmware/software developments
 | Hardware | Firmware |  | FESA
Module |  | Test | Operational | class
CTU | CTU |  | 12/2019 | 12/2019
Fractional divider (AW./PS) | new | () | 02/2020 | 03/2020
Radial position detection | PS 1-TFB board |  |  | 12/2019
Internal function generator | n.a. |  |  | 12/2019
Synchronous 4-ch. receiver | PSB mother b. | 01/2020 | 03/2020 | 03/2020
Fast data concentrator | PSB mother b. | 02/2020 | 04/2020 | 04/2020
Slow data concentrator and distributor | SVEC | 06/2020 | 07/2020 | 07/2020
Beam loops calculation | PSB mother b. | 05/2020 | 06/2020 | 06/2020

## Slide 7
Status of firmware/software developments
 | Hardware | Firmware |  | FESA
Module |  | Test | Operational | class
Clock/sync adaptor | New | 12/2019 | 02/2020 | 02/2020
Master clock, DDS-FMC | SVEC | 02/2020 | 02/2020 | 03/2020
Master clock divider | New | 03/2020 | 04/2020 | 04/2020
20/40/80 MHz cavity contr. | PS 1-TFB board | 12/2019 | 02/2020 | 03/2020
Coupled-bunch feedback | PS 1-TFB board | 12/2019 | 02/2020 | 02/2020
AVC surveillance | New | 02/2020 | 04/2020 | 04/2020