## Slide 1: MBHA-001 - Update on test results and plan Scenarios for repair / replacement
F. Savary
SM18 – 2020-03-05

## Slide 2: Plan A
Assuming that the leak path between Ap1 and Ap2 is localized
Condemn the concerned V-tap (cut/insulate wire) with special tooling introduced in the end cover through one of the end cover nozzles
To be done after CD1, before CD2. The work shall be done in SM18, with the magnet on the test bench
Once the repair is done, go for CD2 in order to (1) validate the repair work, (2) confirm the performance of the magnet after thermal cycle, and (3) complete the test plan

## Slide 3: Plan B
Assuming that the leak path between Ap1 and Ap2 cannot be localized
Assuming that the leak path between Ap1 and Ap2 passes across the V-tap wires (4 in Ap1 x 3 in Ap2)
We can think of replacing the part of the instrumentation wires that is inside the end cover (up to the splicing, prior to the capillary), for the 7 V-taps concerned
This requires de-cryostating the magnet, cut/remove the end cover, replace the wires (part of …), close the magnet, and re-do cryostating
This could be done after CD1, before CD2
Once the repair is done, go for CD2 in order to (1) validate the repair work, (2) confirm the performance of the magnet after thermal cycle, and (3) complete the test plan

## Slide 4: Plan C
Wait for the next type A magnet … equipped with external QH
S5, which has to be a type A, would be ready for transport in the tunnel in the first half of October, if conforming to expectations
  Cold mass construction will start in the end of March
It is not faster to repair the second type A (S3) that we are now dismounting
  The collared coils will be ready for de-collaring in the end of March
Make a type A with a type B (S4) will not be faster
  We would need first to test S4 in SM18, then to dismount it to the point we can replace the bus bars and end plates … before we can start the re-construction work

## Slide 5: Overview
S3: LMBHA002 2020-02-24
CC06
C10
C14
CC07
C15
C16
S1: LMBHB002 2019-08-22
CC02
C01
C05
CC03
C06
C07
S4: LMBHB003 2020-04-15
CC08
C17
C19
CC09
C20
C21
S5: LMBHB004 2020-07-20
CC10
C22
C23
CC11
C24
C25
S6: LMBHA003 2020-09-28
CC12
C26
C27
CC13
C28
C29
S2: LMBHA001 2019-12-16
CC04
C08
C09
CC05
C12
C13
Magnets equipped with impregnated QH
Magnets equipped with external QH
S6: LMBHA003 2020-09-28
CC14
C31
C32
CC15
C33
C34
S6: LMBHA003 2020-09-28
C30
C35