## CLIC ML RF unit
Systems |  |  |  | Development needed | Resources needed | Estimated time | Sum of dependencies | Dependencies | Prototyping | Prototype Cost [KCHF] | Units | Unit price | Total cost [kCHF]
LLRF |  |  | 2 | ?? | ?? |  |  |  | no | --
RF amplifier |  |  | 2 | none | Gerry |  |  |  | no | 25 | 1
Klystron |  | HE Klystron | 2 | HE | Igor
Modulator |  | 2 in 1 | 2 | 2in1 | SCANDINOVA
Pulse compressor | BOC K-design |  | 1 | RF design | Igor ? |  |  |  |  | 100
| BOC K-design |  | 1 | Mech. design | PSI ? |  |  |  |  | 100
| Correction cavities K-design |  | 1 | RF design | Igor + China ?
| Temperature stabilization |  | 1 | ?? | ??
RF network | RF Network |  | 1 | RF design | RF eng. | 3 months |  |  | yes
| Flanges |  | 1 | Double height | Mechanical eng. | 3 months |  |  | yes
| Waveguides |  | 1 | Double height | Outside firm |  |  |  | yes
| Hybrid |  | 1 | Double height | RF eng. + Mech eng
| HO Magic T |  | 1 | Simple height | RF eng. + Mech eng
| Directional coupler |  | 1 | Simple height t.b.c. | RF eng. + Mech eng
| Directional coupler |  | 1 | Double height | RF eng. + Mech eng
| Pumping ports |  | 1 | Double height | RF eng. + Mech eng
| RF Loads |  | 1 | RF design ? t.b.c.
| Window |  | 1 | ongoing | Pedro | 3 months |  |  | yes | 50
Pumping systems |  |  | 2 | none | VSC |  |  |  | no | -- | 9
AS | K-Structure | circular disks | 1 | RF design t.b.c. | RF eng. + Mech eng | 2 months + ?
| K-Structure | rectangular disks | 1 | RF design t.b.c. | RF eng. + Mech eng | 2 months + ?
Module | Structure (rectangular disks ?) | Coupler | 1 | RF design for square | RF eng.
|  | Manifolds | 1 | Integrate coupler | Mech. eng.
|  | UP machining | 1 | none
|  | Joining (brazing) | 1 | RF Design + Mech. Design | Mechanical eng. | 6 months |  | 2 brazing steps ?
|  | Wakefield monitors | 1 | Specification, RF design | Beam dyn + RF eng. |  |  | conclusion from present study
|  | No tuning | 1 | Mech. Design
| Vacuum system | Pumps | 1 | Establish pumping requirment | Vacuum group | 3 months
|  | Manifolds | 1 | Common SAS/RF Load vac. manifold | Matthew | 1 month | 4 months | Structure design. RF Load design.
|  | Ports | 1 | Position/number of ports on SAS | RF eng. + Matthew | 2 months | 8 months | Pumping requirement. Structure design
| Girder | Girder | 1 | Define material, dimensions, & machining | Matthew | 1 month | 15 months | SAS supporting system
|  | Aligment sensor pos. | 1 | Design mounting system /arms | Matthew | 1 month |  | Alignment network
| Girder supporting system | - | 1 | Finalise design | Matthew | 3 months | 6 months | Zero backlash joints. Module vibration.
| SAS supporting system | - | 1 | Completing tests and feedback into new design | Matthew | 6 months | 12 months | Zero backlash (univeral) joints | yes
|  | - |  | Verify impact of add-on components (e.g. loads) | Matthew | 3 months | 10 months | Structure design. RF Load design. Pumping requirements.
| SAS cooling system | Cooling circuit | 1 | Circuit design and girder integration | Alice | 2 months | 8 months | Structure design
| SAS RF integration | WG network | 1 | Collaborate with RF team | RF eng. | 3 months |  | Coupler design
|  | Stabalisation | 1 | Integrate stablisiation circuit into module cooling | RF eng. + Matthew | 1 month |  | SAS Cooling circuit
| Module vibration minimisation | - | 1 | Support design & optimisation | Matthew | 3 months |  | Zero backlash (univeral) joints, structure design, WG network definition | yes
Survey | Alignment sensors |  | 1
| Zero backlash (universal) joints |  | 1

## For plots
LLRF |  |  | 2
RF amplifier |  |  | 2
Klystron |  |  | 2
Modulator |  |  | 2
Pulse compressor | BOC |  | 1
| Correcting cavities |  | 1
| Temperature stabilization |  | 1
RF network | Flanges |  | 1
| Waveguides |  | 1
| Hybrid |  | 1
| Directional coupler |  | 1
| Pumping ports |  | 1
| Window |  | 1
Pumping systems |  |  | 2
Module | Structure |  | 6
| Loads |  | 1
| Vacuum manifold |  | 1
| Girder |  | 1
| Alignment sensors |  | 1
| CAM movers |  | 1
| Stabilization |  | 1
| Magnets |  | 1
| Integration |  | 1
| SS cooling circuit definition |  | 1
| Support and alignment for SS |  | 1
|  | LLRF | 2
|  | RF amplifier | 2
|  | Klystron | 2
|  | Modulator | 2
|  | Pulse compressor | 3
|  | RF network | 6
|  | Pumping systems | 2
|  | Module | 16