## Sheet1
ORIGINAL PLAN
Exp | Det | From | To | Days | Notes
ALICE | TPC | 2020-04-27 | 2020-05-08 | 11 | TPC should be disconnected from the gas system 3 weeks after resuming of the activities at P2
ATLAS | AUX | 2020-05-11 | 2020-05-22 | 11 | OFF
ATLAS | RPC | 2020-05-25 | 2020-06-12 | 18 | OFF, remember that we will have 4 new racks and gas channels remapping
CMS | AUX | 2020-06-15 | 2020-06-26 | 11 | CMS RPC in run with freon
LHCb | RICH2 | 2020-06-29 | 2020-07-10 | 11 | In run but we can stop when we want
ATLAS | MM | 2020-07-13 | 2020-07-24 | 11 | System to be ready for October but mixer for August
LHCb | RICH1 | ? | ?
NEW PLAN |  |  |  |  | think to come back around mid/end April
Exp | Det | From week | To | Days
LHCb | RICH2 | 1 | 3 | 15 | Membrane, IR and compressor will not be ready but not necessary to run the system at the beginning
ALICE | TPC | 5 | 6 | 10 | Week 3 and 4 dedicated to electrical modifications
ATLAS | MM | 7 | 8 | 10 | Standard open mode gas system, hardware will be ready later (only mixer in August)
CMS | AUX | 10 | 11 | 10 | CMS RPC in tun with iC4H10, can we do the system?
ATLAS | AUX
ATLAS | RPC
Example if CERN will open 27/04
|  | From | To
LHCb | RICH2 | 2020-04-27 | 2020-05-15 | 18
ALICE | TPC | 2020-05-18 | 2020-05-29 | 11
ATLAS | MM | 2020-06-02 | 2020-06-12 | 10
CMS | AUX | 2020-06-22 | 2020-07-03 | 11
ATLAS | AUX
ATLAS | RPC