## Slide 1: Back up plan from July in 2020
Norihiro DOSHITA

## Slide 2: Activities in July and August
Safety valves control (Magnet, DR)
Magnet helium vessel leak check (Magnet)
Magnet He purging (Magnet)
Magnet test at room temperature with EP-DT(Magnet)
- power converter test
- control test with short cut cable

## Slide 3: Activities in September, October and November
Full magnet commissioning at 4 K (2 months)
- It will save time for the 2020 run.
-- One time is enough.
- Minimum commissioning was foreseen in the original cooling test planed from April 2020.
- See the detail planning in the next page.
New microwave oscillator test
- Installation on the target platform (2 weeks)
Oscillation test
Target Cell and NMR (2 weeks)
4He pump maintenance
Evacuation Pump repair

## Slide 4: Magnet commissioning schedule with EP-DT
 | SEP | SEP | SEP | SEP | OCT | OCT | OCT | OCT | NOV | NOV | NOV | NOV
 | Precooling with LN2 |  | He cooling | MSS Tests | Sol. Dip. Test | Stability Test | Field Rotat. Test | Warm up |  |  |  | 
Planning without DR and material tests
Liquid helium and cooling water required

## Slide 5: Manpower requirement
Michael P : 2.5 months for the magnet
Kaori : 1 week for the cell and NMR
Gerhard R : 1 week for the cell and NMR
: + 1 weeks for MW test
Takahiro : 2 weeks for the MW test

## Slide 6
Sol Dip
-
Sol
Dip
+236 A
+465 A
+80 A
-80 A
+135 A
-465 A
-135 A
-236 A
Allowed region by MSS
To be checked
MSS for field rotation

## Slide 7
Magnet commissioning in 2020 Autumn
Magnet cooling test without target material
 | 2015 | 2018 | 2020
Solenoid: from 0 to Nominal current (both polarities @ bldg 888) | OK | OK | required
Solenoid: from nominal current to 0 (both polarities @ bldg 888) | OK | OK | required
Dipole: from 0 to nominal current (both polarities @ bldg 888) | OK | OK | required
Dipole: from nominal current to 0 | OK | OK | required
Stop procedure (before a procedure completion) | OK | OK | required
Longitudinal field homogeneity | OK | OK | 
From ±2.5T longitudinal to Transverse (both polarities) | OK | New procedure | required
From Transverse (both polarities) to ±2.5T longitudinal | OK | New procedure | required
TE calibration procedure | OK | OK | required
Trim coils checks | OK | OK | required
Very slow discharge (through cables) | OK |  | 
Capability to recover current from a very slow discharge | OK |  | 
Fast Discharge | @ ±50A | @ ±50A | required

## Slide 8
Magnet commissioning in 2020 Spring
Minimum requirements for original cooling test plan
 | 2015 | 2018 | 2020
Solenoid: from 0 to Nominal current (both polarities @ bldg 888) | OK | OK | required
Solenoid: from nominal current to 0 (both polarities @ bldg 888) | OK | OK | required
Dipole: from 0 to nominal current (both polarities @ bldg 888) | OK | OK | 
Dipole: from nominal current to 0 | OK | OK | 
Stop procedure (before a procedure completion) | OK | OK | 
Longitudinal field homogeneity | OK | OK | required
From ±2.5T longitudinal to Transverse (both polarities) | OK | New procedure | 
From Transverse (both polarities) to ±2.5T longitudinal | OK | New procedure | 
TE calibration procedure | OK | OK | required
Trim coils checks | OK | OK | 
Very slow discharge (through cables) | OK |  | 
Capability to recover current from a very slow discharge | OK |  | 
Fast Discharge | @ ±50A | @ ±50A | required