## Slide 1: LHC Experimental Beam Vacuum TW follow-up meeting #4 (06/04/2020)
Josef Sestak; TE-VSC-BVO
06/04/2020

## Slide 2: General points

## Slide 3: General news
Health situation
  Please try to follow https://hse.cern/news-article/coronavirus-information-measures-and-recommendations
  And WHO advice https://www.who.int/emergencies/diseases/novel-coronavirus-2019/advice-for-public
  CERN helpline in case you feel sick +41 22 766 7777.
Administrative situation
  For PJAS
    Please stay in touch with home institutes to be aware of any legislative requests (country imposed).
  For Staff
    “CERN’s preference is that employed members of personnel remain in the local region whilst teleworking. This is for their safety and healthcare, as well as capacity to return to work on short notice once the situation permits. Due to the extraordinary circumstance of the COVID-19 epidemic, members of personnel may choose to go elsewhere for personal reasons; in this case any accidents during travel or telework cannot be considered to be professional in nature.”

## Slide 4: General news from the experiments
We have asked all Technical Coordinators for regular update on situation. So far it is not clear, how the COVID closure affects the schedule (everybody wants to avoid any speculations).
  ALICE – update after 8th of June (status of the SW-A).
  ATLAS – C-side closure schedule will not shift (unless the closure duration is more important).
  CMS – update after 8th of June (management meeting) – installation by Q4-2020.
  LHCb – VELO activities should start as son as the access is renewed.

## Slide 5: General news from production (both CERN and outsourcing)
CERN EN-MME design office is heavily affected on resources.
  We have managed to recover senior designer for CMS job (15.4 – 15.8m support).
CERN TE-VSC design office only for selected jobs.
  We have priority to complete the CMS job.
CERN atelier is closed
  No production works are ongoing.
  MME preparation & outsourcing office runs in remote regime – follow-up needed.
Outsourcing
  All our current orders are on track.
  All new orders – please check the supplier availability before placing a new DAI.

## Slide 6: Progress on tasks from the last week
Within the separate presentation.

## Slide 7: Tasks for this week

## Slide 8: Tasks for this week
Jerome
  Invitation for the internal BVO review for LHCb installation and bake-out (1h by the end of the week);
  ALICE installation procedure.
  Vacuum acceptance report for CMS forward chambers.
Piotr
  SMOG2 functional specification.
Patrick
  Removal report for the CMS vacuum layout (LS2);
Orlando
  CMS supports 3.2 – 3.5m; 10.6m complete the job with Thomas;

## Slide 9: Tasks for this week
Josef
  Follow-up on the ongoing activities;
  Experimental NC list for reinstallation phase;
  Circulate installation procedure for ATLAS vacuum system;
  Invitation for the internal BVO review for ATLAS installation and bake-out (1h by the next week);
  Installation procedure for LHCb VELO vacuum system;
Other business
  Prepare list of workshop activities for Nicola Robert;
  Preparation of data-set for acceptance tests of CMS chambers (A; V; simulations …).