## Slide 1
Alberto Mengoni, EP-UNT
Oliver Aberle, EN-STI-TCD
n_TOF Report
at the 64th Meeting of the INTC

## Slide 2: Outlook
Update for the main LS2 activities
  Horizontal beam line
  Target exchange
  New control room

## Slide 3: Main n_TOF LS2 activities - ongoing
Before lock-down in March,
now it is on the final position ready to receive the new magnet
Old sweeping magnet

## Slide 4: Main n_TOF LS2 activities - ongoing
Cobalt-Samarium permanent magnet
New sweeping magnet

## Slide 5: Main n_TOF LS2 activities - ongoing
New SEM grid
Tank installation in August, instrument in October
Chassis installed,
Cables in place in July/August

## Slide 6: n_TOF spallation target #3
Project well in the target construction phase, having passed a series of reviews during 2018 and 2019
Going ahead with a sliced pure Pb target, cooled by N2 flow at slightly above atmospheric pressure, ~800 m3/h
  Dedicated neutron moderation circuits, with borated water and demineralized (light) water
Matching the physics requirements of the n_TOF collaboration
On good track for target installation during November/December 2020

## Slide 7: Mechanical design overview
M. Timmins & V. Maire n_TOF target #3 PRR 29-05-2019
Production at full speed
n_TOF target #3

## Slide 8
n_TOF target #3
Courtesy T. Coiffet
Blank Assembly done
Metrology ongoing
Tooling for lifting & assembly finished
Cradle assembly

## Slide 9
n_TOF target #3
Upper part milling & EBW done
RT ongoing
Next Step: EBW lower part
Courtesy T. Coiffet
Vessel

## Slide 10
n_TOF target #3
Lead insertion test ok
Milling the stainless-steel insert to adjust the gap
Courtesy T. Coiffet
Vessel

## Slide 11: Modification of the target side shielding
Shieding wall status

## Slide 12: Modification of the target side shielding
Installation of 2 tow bars bellow the shielding -> ½ day
Re-installation of pulley on the floor -> 1h
Change of end stop position -> 1h
Installation of drainage pipe -> 1h
Installation of shielding plates in big hole and round bars -> ½ day
Installation of remaining shielding bricks after target (~35) -> ½ day
Test of opening -> ½ day
Remaining actions

## Slide 13: n_TOF Experiment LS2 Coordination Meeting
Projects followed up until now:
  Experimental Areas Prepartion for the LS2 work. In particular,
    remove all radioactive samples and sources to be stored by RP
    Contamination control perfomed by RP confirms absence of contamination
  Cabling campaign in EAR1 (remove the old sweeping magnet cables, replace the detector cables in the rack/bunker area)
  Implementation of the ASN-OFSP safety recommandations in EAR2
  Consolidation of the gas system in EAR2, hardware installed
  Consolidation of the alignment system
  Upgrade of the n_TOF electronics laboratory and control room
  DAQ upgrade
  Consolidation and R&D program for detectors

## Slide 14: Schedule and coordination
n_TOF Facility Refurbishment Project Schedule: EDMS 2001626
FTN line completion until October
Target manufacturing
Ready for beam

## Slide 15: Summary
Main activities for LS2 - Facility
  Horizontal beam line modifications ongoing
  Target production going well
  New target shielding close to completion
Restart after lock-down smooth and on track
Thank you Enrico!
Welcome Alberto

## Slide 16
Thank you