## Slide 1: 106th Technical Coordination Meeting Update on WP6a
A. Ballarino and P. Cruikshank
11/06/2020

## Slide 2: Table of contents
Topics retained from last PSM:
Baseline for DFX, DFM, DFHX and DFHM cryostats
ECR on DFH design
Space needed for cables in cryostat
DEMO 2 status

## Slide 3: Baseline for DFX, DFM, DFHX and DFHM

## Slide 4
DFM
DFHM
DFHX
DFX
SC Link for Triplets
D1
SC Link for
Matching Sections
Cryostat and leads
Cryostat and leads

## Slide 5: Overview - DFX, DFM, DFHX and DFHM
Design of components at CERN progressed well during the COVID period
Several iterations with WP17 – with meetings on integration aspects on a weekly basis. Forum for discussing and reviewing also interfaces with other WPs
DFX first unit (spare for HL-LHC) designed and being produced via UK1 (Univ. of Southampton). Excellent collaboration between CERN and University of Southampton during all phases – from conceptual to detailed design. All interfaces, in particular with WP9 for cryogenic and operational aspects, discussed and reviewed
DFX and DFM series production via UK2 (Univ. of Southampton) approved at FC of December 2019. Working on writing-up of collaboration agreement
DFHX and DFHM prototypes and series production via collaboration agreement with Uppsala University approved at FC of December 2019. Working on writing-up of collaboration agreement

## Slide 6: DFX - Triplets
2D detailed drawings completed
PRR at CERN/SOTON on 03/03/2020
All materials sourced and Co compliant
COVID-19 affects material procurement
Still expect to meet Q1 2020 delivery
University of Southampton
MgB2
Nb-Ti
LHe
GHe

## Slide 7: DFX - Triplets
Integration drawings updated
Interfaces defined

## Slide 8: DFM – Matching Sections
3D conceptual drawings available and used for integration studies
Elaborated routing of SC Link for connection to DFM
Modifications on D2 bus-bar on-going within WP3: interface to be defined

## Slide 9: DFHX - Triplets
3D Drawings completed. 2D Drawings well advanced
Integration drawings in the tunnel well advanced, with definition of interfaces Detailed Design Review on the 16th of June
MgB2 (25 K)
HTS-REBCO (50 K)
GHe from SC Link

## Slide 10: DFHX - Triplets
Electrical interface with WP6b (current leads to RT bus) defined

## Slide 11: DFHX - Triplets

## Slide 12: DFHM
Adopted same design of DFHX – with two instead of three modules
2D drawings  70 % common to DFHX
Integration studies proceeding well in collaboration with WP17 and WP6b

## Slide 13: ECR on DFH design

## Slide 14: ECR on DFH
1. LHC DFBA cryostat in the HL-LHC gallery. It would have occupied a length of 10 m
2. Intermediate concept of DFHX. Two modules electrical connected via an additional SC Link. It would have occupied a length of about 29 m, including about 12.4 m of SC Link in between the modules
3. HL-LHC DFHX baseline in the HL-LHC gallery. It occupies a length of 5.8 m

## Slide 15: ECR on DFH
2383175 v.1.0, LHC-DFH-EC-0001 v.1.0, WP6a, WP15
No impact on schedule. Cost within estimation

## Slide 16: System lowered in the tunnel after cold tests
Many thanks to the transport team and design
office for the detailed transport study
SC Link
DFHX/DFHM
System cold tested at the surface

## Slide 17: Space requirements

## Slide 18: Updated and quantified space need
Defined: working sequence, volumes and services
for both ITs and MSs systems
Active iteration with the TE department representatives

## Slide 19: Demo 2: status

## Slide 20: Demo 2: a System Demonstrator for the Triplets
Key milestone: the end of the R&D phase
60 m, MgB2
HTS, REBCO
DDFX
SC Link for Triplets, 60 m long
DDFH
Nb-Ti
MgB2
HTS REBCO
25 K
50 K

## Slide 21: Demo 2
Qualification of:
Prototype  100 kA MgB2 industrialized cable assembly for Triplets;
SC Link cryostat final performance;
Assembly operations (spooling, cable integration inside cryostat);
Splices (MgB2 to Nb-Ti in LHe and MgB2 to HTS REBCO in GHe);
Simultaneous powering of different circuits to verify electro-magnetic compatibility;
Cryogenic operation/control parameters.
PC1: up to 18 kA
PC2: up to 7 kA
LHe
50 K
25 K
RT
Short of cables
powered by PC1
Short of cables
powered by PC2
 90 mm

## Slide 22: Demo 2
MgB2
To HTS
Work re-started with limited personnel on the last week of April 2020
System completed and closed by mid-May: performed HV tests of MgB2 cables (20 kV at the company ! between cables and to ground, 10 kV at CERN before and after insertion in the SC Link cryostat), pressure test, leak tightness tests

## Slide 23: Demo 2
Successful cool-down of the full system last week (week 20)
Excellent cryogenic control
Cooled down 1.5 tons of MgB2 cable in a representative final system
p of GHe across the SC Link  2-3 mbar for up to 3 g/s in nominal operating conditions (4.5 K to 25 K)

## Slide 24: Demo 2
Successful powering of 18 kA circuit on 10/06/2020
MgB2: 17 K or 25 K, REBCO: 50 K
Plateau @ 18 kA with no voltage drift and stable low-resistance joints

## Slide 25: Thanks for your attention