## Slide 1: CM and Cryo Meeting
S. Feher
CM and Cryo Meeting
August 13th, 2020

## Slide 2: Preparation for CD3 DOE Review
Pre-Series Production Readiness Review – September 14th
Shipping requirements Review – September (no exact date yet)
CD3 DOE review – November 17
  More details from Giorgio soon
All the docs to be ready for the PPRR – September 7th, 2020
  Need to be uploaded for the Review indico site
Talks to be ready for internal rehearsals September 1st, uploaded September 7th

## Slide 3: Documentation for the DOE Review
Final Design Report – need to be updated if new info available and clean up if needed
LMQXFA FRS – CERN; Done EDMS# 1686197 – released
LQXFA/B Cryostat - (EDMS 1828585) – released
Acceptance plan
  Part B (Cold Mass and Cryostating) HiLumi Docdb # 1127, EDMS no 2323981 LHC-LMQXFA-ES-0007 - released
  Part C (CERN receiving of the Cryo-Assembly) HiLumi Docdb # 1145) EDMS no 1868479 - LHC-LQXFA-ES-0003 – released
Interfaces: ICD re-vised – all approved; ICD 375 EDMS 1868472 - released
CM MIP (Manufacturing Inspection Plan) – EDMS #1866244 - released
CA MIP (Manufacturing Inspection Plan) – US-HiLumi Document 3238-v1; EDMS # 2369656 – Not released
Material list – EDMS 1868473 - LHC-LMQXFA-EP-0001 – released
LMQXFB Q2 Bus Bar FRS – EDMS 2380143; LHC-LMQXFBE-ES-0001 – released
CA traveler - newer version from Delio – not released
Zero magnet test results Roger/Guram/Stoyan

## Slide 4: Documentation for the Pre-Production Readiness Review
FDR to be updated – August 31st
All the drawings to be completed
All interfaces to be completed – ICD review August 27th and September 3rd.
Final design validation test reports not yet finished
  LMQXFA Analysis note Colin/Tony (HiLumi Docdb #2934) – need CERN approval
  Practice Cold mass tests results Thomas/Tony/Rodger
  Weld sample test results Tony/industry
  Short sample test results Dan/Thomas
  Magnetic analysis of the stray field vs bus bar forces Vadim

## Slide 5: Possible charge questions
Scope and interfaces: is the L3 task scope for 302.4.02 and 302.4.03 clearly defined? Are interfaces among these tasks, and with other tasks sufficiently well-defined for executing the pre-series production?
Drawings: are all the assembly and component drawings released?
Manufacturing: are the manufacturing work-flow documents and travelers — including scheduling, personnel needs, floor space, and facilities requirement — appropriate to execute the pre-series production?
QA/QC: are the QA/QC plans adequate? Is there appropriate documentation for quality control procedures, manufacturing and inspection plan, and data reporting (including part and material traceability)? Are the fabrication MIPs complete and approved?
ES&H: Have all hazards been identified and addressed? Are ES&H policy and documentation sufficient for the pre-series production?
Reviews: are all recommendations for these L3 tasks from previous reviews addressed?
Are these L3 tasks ready for pre-series production?