## Slide 1: SPS-crab cavity test stand recommissioning G.Vandoni
SPS main dates
Planning test stand closure
Cooldown & RF conditioning
Summary

## Slide 2: SPS main dates
End normal access: 16th October
19 Oct (week 43)
4 Dec (week 49)
IST
26-30 Oct: SPS closed (Fire)
2-6 Nov: SPS closed (PPS)
SF1 cooling tower maintenance, primary water week 49
Hardware commissioning : 7th Dec - 26th Feb 2021
Cold check-out: 1st March-9th April 2021

## Slide 3: Planning SPS crab closure
Actors in the loop:
BE/RF/PM | G.Cipolla E.Montesinos (C.Julie)
BE/RF/CS | D.Glenat
LLRF | P.Baudrenghien
TE/VSC | C.Pasquino
TE/CRG | J.Metselaar J.Casas Benoit L.Alaux S.Claudet
Survey | V.Rude
AL4030 | F.Monnet
Table | K.Artoos
Tuners | K.Artoos

## Slide 4: Planning SPS crab closure
Actors in the loop:
BE/RF/PM | G.Cipolla E.Montesinos (C.Julie)
BE/RF/CS | D.Glenat
LLRF | P.Baudrenghien
TE/VSC | C.Pasquino
TE/CRG | J.Metselaar J.Casas B.D’Hulster L.Alaux S.Claudet
Survey | V.Rude
AL4030 | F.Monnet
Table | K.Artoos
Tuners | K.Artoos


DONE 90%
DONE 90%
DONE
DONE, leak checked, under vacua

## Slide 5
L.Alaux
Missing instrumentation reconnection and test
Missing X-ray and pressure test for new line at the surface
E.Montesinos
Functionality tests of all circuits & check of signals
K.Artoos
Cable repair
Final check of motor rotation, end switches, programming new load cells
V.Rude
Reconnection of optical fibers
Final position measurement on cavities, in beam
Mutual interlock checks
Vacuum
Cryo
RF power
(Access)
(Table)
Cooldown
K.Artoos
Cycling
C.Pasquino
Reconnection of fixed pumping group and beam vacuum pumpdown
Bleu
Remove chain hoist
RF
Cryo
Tuners
Survey
Table
Vacuum
Transport

## Slide 6: Cooldown & RF conditioning – our requests
Request | Requisites | Link | Duration
Cryogenic commissioning | Power Network Water (raw) Vacuum (beam & insul.) | L.Alaux S.Claudet (G.Vandoni) | 2 weeks (1 may be ¦¦ to RF start)
DSO tests | The above PPS operational Table tested | D.Vaxelaire C.Gaignant (G.Vandoni) | 1 day
RF commissioning & cavity conditioning | The above Water (demi) SPS access closed status Cryomodule cold | E.Montesinos (G.Vandoni) | 5-7 weeks Continuous
Scheduled during Hardware commissioning

## Slide 7: NOTES from meeting
V alkfdvf